Agile Masterclass

Module 3 – Scrum Mastery

Lesson 29: Scrum Introduction – History, Philosophy, Theory, Framework, and Foundations

Learning Objectives

By the end of this lesson, you will understand:

- What Scrum is.

- Why Scrum was created.

- History of Scrum.

- Scrum mindset.

- Scrum theory.

- Scrum pillars.

- Scrum values.

- Scrum framework overview.

- Scrum vs Agile.

- Scrum lifecycle.

- When Scrum works and when it doesn't.

1. What is Scrum?

Simple definition

Scrum is an Agile framework that helps teams develop complex products through iterative development, frequent feedback, and continuous improvement.

Simple meaning:

Scrum helps a team build something complex step-by-step instead of trying to build everything at once.

Simple Real-Life Analogy

Imagine building a house.

Traditional approach:

Plan everything for 1 year.

↓

Build entire house.

↓

Show customer.

Problem:

Customer says:

"I wanted different rooms."

Too late.

Scrum approach:

Build step-by-step:

Sprint 1:

Build foundation.

Show customer.

Get feedback.

Sprint 2:

Build rooms.

Show customer.

Get feedback.

Sprint 3:

Add finishing.

The customer gets involved continuously.

2. Why was Scrum created?

Software development has a problem:

Software is not like manufacturing.

You cannot always predict everything.

Examples:

Customer changes requirements.

Technology changes.

Market changes.

Users discover new needs.

Traditional methods assumed:

"We know everything before starting."

Reality:

"We learn while building."

Scrum was created to manage:

- Complexity.

- Uncertainty.

- Changing requirements.

3. History of Scrum

Scrum originated from research by:

Hirotaka Takeuchi

and

Ikujiro Nonaka

in 1986.

They studied successful Japanese companies.

They found:

High-performing teams worked differently.

They were:

- Cross-functional.

- Collaborative.

- Self-organizing.

They published a famous paper:

"The New New Product Development Game"

The paper introduced the idea of teams working like a rugby "scrum."

Later:

Jeff Sutherland

and

Ken Schwaber

formalized Scrum for software development.

4. Why the name "Scrum"?

The name comes from rugby.

In rugby:

Players form a scrum:

- Work together.

- Move as one unit.

- Adapt quickly.

Software teams should behave similarly.

5. Scrum vs Agile

This is a very common interview question.

Agile

Agile is a mindset.

It is based on:

- Values.

- Principles.

Scrum

Scrum is a framework implementing Agile.

Analogy:

Agile = Religion/philosophy

Scrum = One way of practicing that philosophy

Example:

Agile approaches:

- Scrum.

- Kanban.

- XP.

- Lean.

6. Scrum Theory

Modern Scrum is based on:

Empiricism

Meaning:

Make decisions based on:

- Observation.

- Experience.

- Evidence.

Simple example:

Instead of saying:

"Users will love this feature."

Build a small version.

Measure usage.

Learn.

7. Three Pillars of Scrum

Scrum is built on three pillars.

Pillar 1: Transparency

Everyone should see:

- What is happening.

- Current progress.

- Problems.

Examples:

Visible:

- Product Backlog.

- Sprint Goal.

- Burndown chart.

Healthcare example:

Everyone can see:

AI pharmacovigilance development progress.

Pillar 2: Inspection

Regularly check progress.

Examples:

- Sprint Review.

- Daily Scrum.

- Testing.

Question:

"Are we building the right thing?"

Pillar 3: Adaptation

If something is wrong:

Change.

Example:

AI extraction accuracy is low.

Team adapts:

- Improve model.

- Change approach.

- Add validation.

Scrum Framework Overview

Scrum has:

Accountabilities

Who is responsible?

- Product Owner.

- Scrum Master.

- Developers.

Events

When do we inspect and adapt?

- Sprint.

- Sprint Planning.

- Daily Scrum.

- Sprint Review.

- Sprint Retrospective.

Artifacts

What creates transparency?

- Product Backlog.

- Sprint Backlog.

- Increment.

Scrum Framework Diagram

Product Goal

↓

Product Backlog

↓

Sprint Planning

↓

Sprint

-------------------------

Daily Scrum

Development

Testing

Collaboration

-------------------------

↓

Sprint Review

↓

Sprint Retrospective

↓

Improved Sprint

8. Scrum Characteristics

1. Iterative

Work happens repeatedly.

Example:

Sprint 1:

Basic case management.

Sprint 2:

AI extraction.

Sprint 3:

Signal detection.

2. Incremental

Product grows step-by-step.

3. Time-boxed

Events have fixed duration.

Example:

Sprint:

2 weeks.

4. Adaptive

Teams adjust based on feedback.

9. Scrum Lifecycle Example

Let's build:

AI Pharmacovigilance Platform

Step 1: Product Vision

Goal:

"Reduce manual adverse event processing using AI."

Step 2: Product Backlog

Features:

- Case intake.

- AI extraction.

- MedDRA coding.

- Signal detection.

Step 3: Sprint Planning

Team selects:

Sprint Goal:

"Create automated case intake."

Step 4: Sprint Execution

Developers build.

Tester validates.

BA clarifies requirements.

Step 5: Sprint Review

Stakeholders see working feature.

Feedback collected.

Step 6: Retrospective

Team discusses:

What went well?

What should improve?

10. Scrum Principles

Scrum promotes:

Self-management

Teams decide how to work.

Collaboration

Business and technology work together.

Continuous improvement

Every sprint improves.

Customer focus

Deliver valuable outcomes.

11. When Scrum works best

Scrum works well when:

1. Requirements change

Example:

AI products.

2. Complex problems exist

Example:

Healthcare platforms.

3. Customer feedback is important

4. Cross-functional teams exist

12. When Scrum may not work well

Scrum may struggle when:

1. Work is predictable

Example:

Routine data entry.

2. Teams cannot collaborate

3. No product ownership exists

4. Organization refuses change

13. Scrum Myths

Myth 1:

"Scrum means daily meetings."

Wrong.

Daily Scrum is only one event.

Myth 2:

"Scrum eliminates planning."

Wrong.

Scrum has continuous planning.

Myth 3:

"Scrum Master is a project manager."

Wrong.

Scrum Master is a coach and facilitator.

Myth 4:

"Product Owner tells developers what code to write."

Wrong.

PO defines value, not technical implementation.

14. Scrum in Healthcare

Example:

Hospital Management System.

Sprint 1:

Patient registration.

Sprint 2:

Doctor appointment.

Sprint 3:

Prescription management.

Sprint 4:

Analytics.

Stakeholders provide feedback every sprint.

15. Scrum in Pharmacovigilance

AI Drug Safety Platform:

Product Owner:

Pharmacovigilance manager.

Scrum Team:

- Developers.

- Data scientists.

- QA.

- BA.

Sprint example:

Goal:

"Reduce manual case entry."

Deliver:

AI extraction prototype.

16. Scrum in AI Products

AI development is uncertain.

Scrum helps manage:

- Model experiments.

- User feedback.

- Data issues.

- Changing requirements.

Example:

AI chatbot.

Sprint 1:

Basic conversation.

Sprint 2:

Medical knowledge integration.

Sprint 3:

Safety validation.

Common mistakes

Mistake 1:

Treating Scrum as a checklist.

Wrong.

Scrum is a mindset.

Mistake 2:

Following ceremonies but ignoring values.

Wrong.

Mistake 3:

Product Owner not available.

Problem:

Requirements become unclear.

Best Practices

- Maintain clear product vision.

- Keep backlog prioritized.

- Involve stakeholders.

- Deliver working increments.

- Encourage transparency.

- Improve continuously.

Interview Questions

Q1. What is Scrum?

Answer:

Scrum is an Agile framework that helps teams develop complex products through iterative development, inspection, and adaptation.

Q2. Difference between Agile and Scrum?

Answer:

Agile is a mindset based on values and principles, while Scrum is a framework used to implement Agile.

Q3. What are Scrum pillars?

Answer:

- Transparency

- Inspection

- Adaptation

Q4. Why does Scrum use iterations?

Answer:

Because complex products require continuous feedback and learning.

Q5. What is empiricism?

Answer:

Making decisions based on observation, experience, and evidence.

Mini Quiz

Answer these:

- What is Scrum?

- Who created Scrum?

- Difference between Agile and Scrum?

- What are the three Scrum pillars?

- Why is Scrum useful for AI products?

Practical Assignment

For your AI Pharmacovigilance Platform:

Create:

Product Vision

Example:

"Build an AI-powered system that reduces manual drug safety processing."

Create:

First 3 Sprints

Sprint 1:

Goal:

?

Sprint 2:

Goal:

?

Sprint 3:

Goal:

?

Explain:

- Why did you choose these priorities?

- What feedback would you collect?

Summary

Scrum is:

A framework for managing complex product development through:

✅ Iterations
✅ Collaboration
✅ Feedback
✅ Transparency
✅ Continuous improvement

Core foundation:

Empiricism + Three Pillars + Scrum Values

Key Takeaways

- Scrum is an Agile framework.

- Created from research on high-performing teams.

- Formalized by Jeff Sutherland and Ken Schwaber.

- Uses Sprints to deliver increments.

- Based on transparency, inspection, and adaptation.

- Very useful for AI and healthcare product development.

Lesson 30: Scrum Roles and Accountabilities (Deep Dive)

Learning Objectives

By the end of this lesson, you will understand:

- What Scrum accountabilities are.

- Difference between role and accountability.

- Product Owner responsibilities.

- Scrum Master responsibilities.

- Developer responsibilities.

- Stakeholder involvement.

- How a Scrum team works together.

- Healthcare and AI examples.

- Interview expectations.

1. Understanding Scrum Accountabilities

First, understand one important change.

Older Scrum versions used the word:

Roles

Modern Scrum uses:

Accountabilities

Why?

Because Scrum is not about job titles.

Example:

A person may be:

- Pharmacovigilance expert.

- Business Analyst.

- Product Owner.

The important thing is:

"What responsibility does this person own?"

Simple analogy

Imagine a hospital emergency department.

There are different responsibilities:

- Someone decides treatment priority.

- Someone coordinates workflow.

- Someone performs medical procedures.

The titles may differ, but accountability remains.

Scrum Team Structure

A Scrum Team contains:

- Product Owner

- Scrum Master

- Developers

Together:

They create valuable product increments every Sprint.

Scrum Team Diagram

Scrum Team

|

--------------------------------

Product Owner

Scrum Master

Developers

--------------------------------

Product Increment

2. Product Owner (PO)

Simple definition

The Product Owner is accountable for:

Maximizing the value of the product resulting from the work of the Scrum Team.

Simple meaning:

The Product Owner decides:

- What should be built.

- Why it matters.

- What gives maximum business value.

Real-life analogy

Think about a restaurant.

The chef knows how to cook.

But someone decides:

- Which dishes customers want.

- Which menu items are priorities.

- What customers will pay for.

That person is like a Product Owner.

Product Owner Responsibilities

1. Product Vision

The PO defines:

Where are we going?

Example:

AI Pharmacovigilance Platform vision:

"Reduce manual adverse event processing by 70% using AI."

2. Product Backlog Management

PO owns:

- Creating backlog.

- Ordering backlog.

- Prioritizing backlog.

Example:

Backlog:

Priority 1:

AI case extraction

Priority 2:

MedDRA coding automation

Priority 3:

Dashboard analytics

3. Stakeholder Management

PO communicates with:

- Customers.

- Business leaders.

- Regulatory teams.

- Users.

Example:

Pharma stakeholders say:

"We need faster FDA reporting."

PO converts this into product requirements.

4. Define Product Goals

Example:

Goal:

"Reduce ICSR processing time from 5 days to 1 day."

5. Accept or Reject Work

During Sprint Review:

PO checks:

Does this meet expectations?

Product Owner Does NOT:

❌ Assign tasks to developers.

❌ Manage people.

❌ Decide technical solutions.

❌ Act as project manager.

Product Owner in Healthcare

Example:

Drug Safety Product Owner.

Responsibilities:

- Understand pharmacovigilance workflow.

- Prioritize safety features.

- Work with regulators.

- Define business value.

Product Owner in AI Product

AI Medical Assistant:

PO decides:

Feature:

"Add symptom checking."

But does NOT decide:

Which ML algorithm developers use.

Product Owner Skills

A good PO needs:

Business skills

- Market understanding.

- Strategy.

Communication

- Stakeholder management.

Domain knowledge

Healthcare/pharma knowledge is valuable.

Decision-making

Prioritization.

3. Scrum Master

Simple definition

The Scrum Master is accountable for:

Establishing Scrum and helping everyone understand Scrum theory and practice.

Simple meaning:

Scrum Master is:

- Coach.

- Facilitator.

- Process guide.

Real-life analogy

A cricket coach.

The coach does not play every ball.

The coach:

- Improves team performance.

- Removes obstacles.

- Helps players improve.

Scrum Master Responsibilities

1. Coach the Team

Teaches:

- Scrum principles.

- Agile mindset.

- Continuous improvement.

2. Facilitate Scrum Events

Helps conduct:

- Sprint Planning.

- Daily Scrum.

- Sprint Review.

- Retrospective.

3. Remove Impediments

Example:

Developer cannot access test environment.

Scrum Master helps solve it.

4. Protect Scrum Team

Example:

Stakeholder constantly interrupts developers.

Scrum Master protects focus.

5. Improve Team Effectiveness

Helps team become better.

Scrum Master Does NOT:

❌ Assign tasks.

❌ Manage developers.

❌ Act as boss.

❌ Track employees.

Scrum Master in Healthcare

Example:

AI Pharmacovigilance Team problem:

Regulatory team delays approvals.

Scrum Master helps remove communication barriers.

4. Developers

Simple definition

Developers are:

People who create any aspect of a usable product increment.

Important:

Developer does not only mean programmer.

Developers can include:

- Software engineers.

- Data scientists.

- Test engineers.

- Designers.

- Analysts.

Developer Responsibilities

1. Create Increment

They build working product features.

Example:

Sprint goal:

"Automate adverse event extraction."

Developers create:

AI extraction module.

2. Maintain Quality

Developers follow:

Definition of Done.

3. Plan Their Work

Developers decide:

How to complete sprint work.

4. Collaborate

They work with:

- PO.

- Scrum Master.

- Users.

Developer Does NOT:

❌ Wait for detailed instructions.

❌ Work only individually.

❌ Ignore business needs.

5. Stakeholders

Important:

Stakeholders are NOT Scrum Team members.

But they influence product success.

Who are stakeholders?

Examples:

Healthcare:

- Doctors.

- Patients.

- Pharmacovigilance managers.

- Regulatory authorities.

- Hospital administrators.

Stakeholder Responsibilities

Provide:

- Feedback.

- Requirements.

- Business information.

Stakeholder Example

AI Drug Safety Platform:

Stakeholder:

Safety Officer.

Feedback:

"AI extraction accuracy is insufficient."

PO updates priorities.

6. How Everyone Works Together

Example:

AI Pharmacovigilance Platform

Product Owner

Says:

"We need automated adverse event extraction."

Developers

Decide:

How to build AI extraction.

Scrum Master

Ensures:

Team works effectively.

Stakeholders

Provide:

Feedback and domain knowledge.

Collaboration Flow

Stakeholders

↓

Product Owner

↓

Product Backlog

↓

Developers

↓

Product Increment

↓

Stakeholder Feedback

↓

Improvement

7. Product Owner vs Business Analyst

Important for your career.

Many companies combine these roles.

| Product Owner | Business Analyst |
| --- | --- |
| Owns product value | Analyzes requirements |
| Prioritizes backlog | Clarifies requirements |
| Defines vision | Creates documentation |
| Makes decisions | Facilitates understanding |
| Customer focused | Process focused |

In healthcare:

BA may understand:

- Pharmacovigilance workflows.

- Regulations.

- User needs.

PO decides:

Which features come first.

8. Product Owner vs Product Manager

| Product Owner | Product Manager |
| --- | --- |
| Sprint level | Product strategy |
| Backlog | Roadmap |
| Team collaboration | Market analysis |
| Short-term delivery | Long-term vision |

In many companies:

One person may perform both roles.

Common Mistakes

Mistake 1:

PO = Boss

Wrong.

PO manages product decisions, not people.

Mistake 2:

Scrum Master = Project Manager

Wrong.

Scrum Master coaches Agile practices.

Mistake 3:

Developers only code.

Wrong.

Developers create complete increments.

Best Practices

Product Owner

- Keep backlog clear.

- Prioritize continuously.

- Understand users.

Scrum Master

- Coach instead of command.

- Remove obstacles.

- Encourage improvement.

Developers

- Collaborate.

- Own quality.

- Self-manage.

Interview Questions

Q1. What are the three Scrum accountabilities?

Answer:

- Product Owner

- Scrum Master

- Developers

Q2. What is the main responsibility of Product Owner?

Answer:

Maximize product value by managing and ordering the Product Backlog.

Q3. Is Scrum Master a project manager?

Answer:

No. Scrum Master is a servant leader and Agile coach.

Q4. Can a Business Analyst become a Product Owner?

Answer:

Yes. BA skills like requirement analysis, stakeholder management, and domain knowledge help in the PO role.

Mini Quiz

Answer these:

- What is the main accountability of Product Owner?

- What does Scrum Master do?

- Are developers only programmers?

- Who owns Product Backlog?

- Difference between Product Owner and Product Manager?

Practical Assignment

For your AI Pharmacovigilance Platform:

Define:

Product Owner

Who should be the PO?

What decisions will they make?

Scrum Master

What problems will they solve?

Developers

List team members needed.

Example:

- Frontend developer.

- Backend developer.

- AI engineer.

- QA.

- Data analyst.

Stakeholders

List five stakeholders.

Summary

Scrum has three accountabilities:

Product Owner

Creates value.

Scrum Master

Improves the way of working.

Developers

Create the product.

Together:

They transform ideas into valuable working products.

Key Takeaways

✅ Product Owner owns value
✅ Scrum Master owns Scrum effectiveness
✅ Developers own product creation
✅ Stakeholders provide feedback
✅ Scrum is collaborative, not hierarchical

Lesson 31: Product Owner Deep Dive – Vision, Strategy, Backlog Management, Prioritization, and Real Product Owner Work

Learning Objectives

By the end of this lesson, you will understand:

- What a Product Owner really does daily.

- Product vision creation.

- Product strategy.

- Product goals.

- Backlog ownership.

- Prioritization techniques.

- Stakeholder management.

- Working with developers.

- Product Owner mistakes.

- Healthcare and AI Product Owner examples.

1. What is a Product Owner?

Simple definition

A Product Owner is the person accountable for:

Maximizing the value of the product by deciding what should be built and why.

Simple meaning:

A Product Owner answers three questions:

1. Why are we building this?

Business value.

2. What should we build?

Features.

3. What should we build first?

Priority.

Real-Life Analogy

Imagine you are opening a hospital.

Many people suggest ideas:

Doctor:

"We need electronic prescriptions."

Nurse:

"We need better patient records."

Patient:

"We need online appointments."

Management:

"We need cost reduction."

Someone must decide:

- Which problem is most important?

- Which feature gives maximum value?

- What should happen first?

That person is the Product Owner.

2. Product Owner Mindset

A beginner Product Owner thinks:

"My job is to collect requirements."

Wrong.

A good Product Owner thinks:

"My job is to solve customer problems and maximize business outcomes."

Example:

Customer says:

"We need a chatbot."

Weak PO:

"Create chatbot feature."

Strong PO:

"Why do users need a chatbot?"

Maybe the real problem:

Patients cannot get answers quickly.

Solution could be:

- Better FAQ.

- Search.

- AI assistant.

3. Product Owner Responsibilities Overview

A Product Owner manages:

Vision

|

Strategy

|

Roadmap

|

Backlog

|

Prioritization

|

Sprint Collaboration

|

Feedback

|

Improvement

4. Product Vision

What is Product Vision?

Product vision describes:

The future state we want to create.

It answers:

- Who are we helping?

- What problem are we solving?

- What impact do we want?

Example: AI Pharmacovigilance Platform

Weak vision:

"We want to build AI software."

Strong vision:

"We want to create an AI-powered pharmacovigilance platform that reduces manual case processing time, improves regulatory compliance, and enables faster drug safety decisions."

Product Vision Template

Use:

For [customer]

Who?

↓

Who needs [problem]

Pain point?

↓

Our product provides [solution]

How?

↓

To achieve [business outcome]

Impact?

Example:

For:

Pharmacovigilance teams

Who need:

Faster adverse event processing

Our product provides:

AI-assisted case processing

To achieve:

50% reduction in processing time.

5. Product Strategy

What is Product Strategy?

Product strategy explains:

How we will achieve the vision.

Vision:

Where we want to go.

Strategy:

How we get there.

Example:

Vision:

AI Drug Safety Platform.

Strategy:

Phase 1:

Digitize case processing.

Phase 2:

Add AI extraction.

Phase 3:

Add predictive safety signals.

Phase 4:

Enterprise automation.

Product Strategy Components

1. Target Users

Who uses the product?

Example:

- Drug safety officers.

- Medical reviewers.

- Regulatory teams.

2. Customer Problems

Example:

Manual data entry.

Slow reporting.

Human errors.

3. Differentiation

Why choose us?

Example:

AI-powered automation.

4. Business Goals

Example:

Reduce processing cost by 40%.

6. Product Goal

Definition

A Product Goal describes the future objective of the product.

Example:

Product Goal:

"Create an AI-assisted adverse event processing system that reduces manual review workload."

Difference:

Vision:

Long-term dream.

Goal:

Specific achievement.

7. Product Roadmap

What is a roadmap?

A roadmap shows:

- Major features.

- Timeline.

- Strategic direction.

Example:

AI Pharmacovigilance Roadmap:

Q1

|

Case Management

Q2

|

AI Data Extraction

Q3

|

MedDRA Automation

Q4

|

Signal Detection AI

Roadmap is NOT:

❌ A detailed task list.

❌ Developer schedule.

❌ Fixed forever.

8. Product Backlog Ownership

The Product Owner owns the Product Backlog.

The PO ensures:

Visibility

Everyone understands work.

Ordering

Most valuable items first.

Clarity

Items are understandable.

Product Backlog Example

AI PV Platform:

| Priority | Item |
| --- | --- |
| 1 | User login |
| 2 | Case intake |
| 3 | AI extraction |
| 4 | Medical coding |
| 5 | Signal detection |

9. Backlog Prioritization

This is one of the most important PO skills.

You cannot build everything.

You decide:

"What gives maximum value?"

Technique 1: MoSCoW

Very common.

Must Have

Critical.

Example:

User authentication.

Should Have

Important but not mandatory.

Example:

Advanced dashboard.

Could Have

Nice feature.

Example:

Custom themes.

Won't Have

Not now.

Example:

Mobile app in first release.

Technique 2: Value vs Effort Matrix

Compare:

Business value

vs

Development effort

High Value

|

|  Build First

|

|

|

|________________

Effort

Example:

AI extraction:

High value + medium effort

Build early.

Technique 3: RICE Scoring

Used by many product teams.

Formula:

RICE =

Reach × Impact × Confidence

----------------------------

Effort

Example:

Feature:

AI summarization.

Reach:

1000 users.

Impact:

High.

Confidence:

80%.

Effort:

Medium.

Technique 4: Cost of Delay

Question:

"What happens if we delay this?"

Example:

Regulatory reporting feature.

Delay = compliance risk.

High priority.

10. Stakeholder Management

A Product Owner works with many stakeholders.

Healthcare example:

Stakeholders:

- Pharmacovigilance head.

- Doctors.

- Regulatory affairs.

- IT security.

- Patients.

- Business leadership.

Problem:

Everyone wants different things.

PO responsibility:

Balance:

Customer Need

+

Business Goal

+

Technical Reality

+

Regulatory Requirements

11. Product Owner Daily Activities

A typical day:

Morning

Review metrics.

Check backlog.

Team Discussion

Clarify user stories.

Answer questions.

Stakeholder Meeting

Collect feedback.

Prioritization

Reorder backlog.

Product Thinking

Analyze:

"What problem should we solve next?"

12. Product Owner and Developers

A good PO does not say:

"Build exactly this."

A good PO explains:

Problem:

"Doctors need faster access to patient history."

Developer decides:

Technical solution.

13. Product Owner and Business Analyst

This is important for you.

Many organizations combine these roles.

BA focuses:

"What does the user need?"

PO focuses:

"Which need creates highest value?"

Example:

BA discovers:

Users spend 3 hours entering cases.

PO decides:

AI extraction should be priority.

14. Product Owner in AI Products

AI products require special thinking.

Traditional software:

Requirement → Build → Test

AI:

Problem → Data → Experiment → Learn → Improve

AI Product Owner manages:

- Data availability.

- Model performance.

- User feedback.

- AI risks.

Example:

AI medical chatbot.

PO must consider:

Accuracy.

Safety.

Bias.

Privacy.

15. Product Owner in Pharmacovigilance

Example:

AI ICSR Processing System.

PO decisions:

Should we automate:

- Data extraction?

- Duplicate detection?

- Coding?

- Narrative generation?

Prioritization:

First:

Reduce manual workload.

Later:

Advanced prediction.

Common Product Owner Mistakes

Mistake 1:

Accept every stakeholder request.

Problem:

No priority.

Mistake 2:

Focus only on features.

Problem:

Ignore outcomes.

Mistake 3:

Not understanding users.

Problem:

Build wrong product.

Mistake 4:

Being unavailable to team.

Problem:

Development slows.

Best Practices

A great Product Owner:

✅ Understands users deeply
✅ Maintains clear vision
✅ Prioritizes ruthlessly
✅ Communicates clearly
✅ Uses data for decisions
✅ Collaborates with teams
✅ Focuses on outcomes

Interview Questions

Q1. What is the main responsibility of Product Owner?

Answer:

To maximize product value by managing and ordering the Product Backlog.

Q2. Difference between Product Vision and Product Roadmap?

Answer:

Vision defines future direction; roadmap explains how we plan to achieve it.

Q3. How do you prioritize backlog?

Answer:

Using methods like MoSCoW, RICE, WSJF, Cost of Delay, and Value vs Effort.

Q4. Can Product Owner reject stakeholder requests?

Answer:

Yes. The PO must prioritize based on product value and strategy.

Mini Quiz

Answer these:

- What is the difference between vision and strategy?

- Who owns Product Backlog?

- What does RICE stand for?

- What is the difference between BA and Product Owner?

- Why is AI Product Ownership different from traditional products?

Practical Assignment

Create Product Owner documents for:

AI Pharmacovigilance Platform

1. Product Vision

Write 2–3 sentences.

2. Product Goal

Write one measurable goal.

3. Roadmap

Create:

Phase 1

Phase 2

Phase 3

4. Prioritize these features:

- Login

- AI extraction

- Dashboard

- Signal detection

- Regulatory reports

Use MoSCoW.

Summary

A Product Owner is not a requirement collector.

A Product Owner is:

The person responsible for maximizing product value.

Core responsibilities:

- Vision

- Strategy

- Roadmap

- Backlog

- Prioritization

- Stakeholder alignment

Key Takeaways

✅ PO owns product value
✅ PO manages backlog priority
✅ PO connects users, business, and technology
✅ PO makes difficult trade-offs
✅ AI Product Owners must manage uncertainty and experiments

Lesson 32: Scrum Master Deep Dive – Servant Leadership, Coaching, Facilitation, Impediment Removal, and Agile Team Improvement

Learning Objectives

By the end of this lesson, you will understand:

- What a Scrum Master really does.

- Why Scrum Master is not a Project Manager.

- Servant leadership.

- Coaching techniques.

- Facilitation skills.

- Removing impediments.

- Improving team maturity.

- Scrum Master metrics.

- Healthcare and AI examples.

- Interview expectations.

1. What is a Scrum Master?

Simple definition

A Scrum Master is accountable for:

Establishing Scrum as defined in the Scrum Guide and helping everyone understand Scrum theory and practice.

Simple meaning:

A Scrum Master helps the team become:

- More effective.

- More collaborative.

- More Agile.

Real-life analogy

Think about a football coach.

The coach does not:

❌ Score every goal.

❌ Play every match.

The coach:

✅ Trains players.

✅ Improves teamwork.

✅ Removes obstacles.

✅ Helps the team perform better.

A Scrum Master works similarly.

2. Why Does Scrum Need a Scrum Master?

Without guidance, teams often fall into problems:

Problem 1:

Daily Scrum becomes a status meeting.

Instead of:

"How can we coordinate?"

It becomes:

"Reporting to manager."

Problem 2:

Product Owner gives unclear requirements.

Problem 3:

Team ignores retrospectives.

Problem 4:

External people interrupt the team.

Scrum Master prevents these problems.

3. Scrum Master vs Project Manager

Very common interview question.

| Project Manager | Scrum Master |
| --- | --- |
| Manages project | Coaches team |
| Assigns tasks | Helps self-management |
| Tracks schedule | Improves flow |
| Controls people | Supports people |
| Manages risks | Helps remove impediments |
| Command-and-control | Servant leadership |

Example

Developer says:

"I cannot complete this task because test environment access is blocked."

Project Manager approach:

"Why are you late?"

Scrum Master approach:

"What is blocking you? How can we remove it?"

4. Servant Leadership

This is the foundation of Scrum Master role.

What is Servant Leadership?

A leader who serves the team instead of controlling the team.

Traditional leadership:

Manager

|

|

Employees

Servant leadership:

Team

↑

Scrum Master supports team

Servant Leader Behaviors

A Scrum Master:

Listens

Understands problems.

Coaches

Helps people improve.

Removes barriers

Makes work easier.

Empowers

Allows teams to make decisions.

5. Scrum Master Responsibilities

According to Scrum:

A Scrum Master serves:

- Scrum Team

- Product Owner

- Organization

A. Serving the Scrum Team

1. Coaching self-management

Old style:

Manager assigns tasks.

Agile:

Team decides:

- How to work.

- How to solve problems.

Example:

AI development team.

Instead of:

"Developer A do this."

Team decides:

"Who has the best skills for this work?"

2. Helping team focus on Sprint Goal

Every sprint needs a goal.

Example:

Sprint Goal:

"Automate adverse event data extraction."

Scrum Master ensures:

Team stays focused.

3. Removing impediments

What is an impediment?

Anything preventing progress.

Examples:

Technical:

- Server unavailable.

Process:

- Approval delays.

People:

- Communication problems.

Healthcare example:

AI model testing delayed because clinical dataset approval is pending.

Scrum Master helps resolve.

B. Serving the Product Owner

Scrum Master helps PO by:

1. Backlog management coaching

Helps PO understand:

- User stories.

- Prioritization.

- Refinement.

2. Stakeholder collaboration

Helps create better communication.

3. Product planning

Supports:

- Release planning.

- Sprint planning.

C. Serving the Organization

Scrum Master helps organization:

- Adopt Agile mindset.

- Remove organizational blockers.

- Improve processes.

6. Scrum Events Facilitation

Scrum Master facilitates events.

Important:

Facilitate ≠ Control.

Sprint Planning

Scrum Master ensures:

- Clear Sprint Goal.

- Right participants.

- Product Backlog ready.

Daily Scrum

Scrum Master ensures:

Purpose is collaboration.

Not reporting.

Sprint Review

Helps:

- Stakeholder participation.

- Feedback collection.

Sprint Retrospective

Most important improvement event.

Team discusses:

What went well?

What failed?

What should change?

7. Coaching Techniques

A Scrum Master is a coach.

Technique 1: Asking Powerful Questions

Instead of:

"Why did you fail?"

Ask:

"What prevented success?"

Technique 2: Active Listening

Understand before responding.

Technique 3: Facilitation

Help teams reach decisions.

Technique 4: Teaching

Explain Agile concepts.

8. Scrum Master in AI Product Development

AI projects have uncertainty.

Problems:

- Data quality issues.

- Model accuracy problems.

- Changing requirements.

Example:

AI Pharmacovigilance Platform.

Problem:

AI extraction accuracy is only 70%.

Scrum Master helps team:

- Run experiments.

- Improve collaboration.

- Remove blockers.

9. Scrum Master in Pharmacovigilance

Example:

Drug Safety AI Team.

Blocker:

Medical reviewers are not available for validation.

Scrum Master:

Coordinates with stakeholders.

Creates process.

Removes delay.

10. Scrum Master Metrics

A Scrum Master does not measure individual performance.

Important metrics:

1. Velocity Trend

Shows team capacity trend.

Not employee productivity.

2. Cycle Time

How long work takes.

3. Sprint Predictability

Did team achieve Sprint Goal?

4. Escaped Defects

Quality measurement.

5. Team Health

Collaboration.

Morale.

Continuous improvement.

11. Scrum Master Anti-Patterns

Mistake 1:

Acting as manager.

Wrong.

Mistake 2:

Running every meeting forever.

Wrong.

Team should become independent.

Mistake 3:

Solving every problem personally.

Wrong.

Coach team to solve problems.

Mistake 4:

Tracking people.

Wrong.

Focus on system improvement.

12. Scrum Master Career Skills

Important skills:

Agile Knowledge

- Scrum.

- Kanban.

- Lean.

Communication

- Facilitation.

- Conflict resolution.

Leadership

- Coaching.

- Mentoring.

Domain Understanding

Healthcare knowledge is valuable.

13. Scrum Master vs Business Analyst

Important for your career.

| Scrum Master | Business Analyst |
| --- | --- |
| Improves process | Understands requirements |
| Coaches team | Analyzes business needs |
| Removes blockers | Defines requirements |
| Facilitates collaboration | Creates documentation |

14. Scrum Master vs Product Owner

| Scrum Master | Product Owner |
| --- | --- |
| How work happens | What gets built |
| Process owner | Product value owner |
| Team effectiveness | Product success |

Interview Questions

Q1. What is the role of Scrum Master?

Answer:

A Scrum Master helps the Scrum Team understand and apply Scrum, removes impediments, and improves team effectiveness.

Q2. Is Scrum Master a manager?

Answer:

No. Scrum Master is a servant leader and coach.

Q3. What are Scrum Master responsibilities?

Answer:

- Coaching team.

- Facilitating Scrum events.

- Removing impediments.

- Helping Product Owner.

- Supporting Agile adoption.

Q4. How do you handle team conflicts?

Answer:

Facilitate discussion, encourage collaboration, identify root causes, and help the team reach solutions.

Mini Quiz

Answer these:

- What is servant leadership?

- Difference between Scrum Master and Project Manager?

- What is an impediment?

- Why should Scrum Master not assign tasks?

- How does Scrum Master help AI teams?

Practical Assignment

For your:

AI Pharmacovigilance Platform

Imagine you are Scrum Master.

Create:

5 possible impediments:

Example:

"Medical validation team unavailable."

For each:

Write:

- Problem.

- Impact.

- How Scrum Master resolves it.

Create:

Sprint Retrospective Questions

- What went well?

- What did not go well?

- What improvement action will we take?

Summary

A Scrum Master is:

Not a manager.

Not a task controller.

A:

✅ Coach
✅ Facilitator
✅ Servant leader
✅ Improvement catalyst

The Scrum Master's goal:

Help the team become better every sprint.

Key Takeaways

- Scrum Master owns Scrum effectiveness.

- Scrum Master enables self-management.

- Scrum Master removes obstacles.

- Scrum Master coaches people.

- Scrum Master improves team performance.

- Scrum Master does not manage individuals.

Lesson 33: Developers in Scrum – Cross-Functional Teams, Self-Management, Definition of Done, Quality Ownership, and Engineering Practices

Learning Objectives

By the end of this lesson, you will understand:

- Who Developers are in Scrum.

- Why Scrum uses the term "Developers."

- Developer responsibilities.

- Cross-functional teams.

- Self-management.

- How Developers work with PO and Scrum Master.

- Definition of Done.

- Quality ownership.

- Technical practices.

- Healthcare and AI examples.

1. Who are Developers in Scrum?

Simple definition

In Scrum:

Developers are the people who create any aspect of a usable product Increment.

Important:

Developer does not only mean programmer.

A Developer can be:

- Software engineer.

- Data scientist.

- UX designer.

- Tester.

- Database engineer.

- Automation engineer.

- Data analyst.

- Technical writer (if contributing to product value).

Real-life analogy

Imagine building a hospital.

The "developers" are not only construction workers.

They include:

- Architect.

- Electrician.

- Plumber.

- Safety inspector.

Everyone who creates part of the hospital contributes to the final outcome.

2. Why Scrum uses the word "Developers"?

Earlier Scrum used:

"Development Team"

Modern Scrum uses:

"Developers"

Why?

Because the word "development" created confusion.

Many thought:

Only coding.

But Scrum means:

Anyone creating value.

Example:

AI healthcare product:

Creating the product requires:

- AI engineer.

- Data scientist.

- Frontend developer.

- Pharmacovigilance expert.

- QA engineer.

All are Developers in Scrum terminology.

3. Developer Accountability

According to Scrum:

Developers are accountable for:

1. Creating a plan for the Sprint

They decide:

How will we achieve the Sprint Goal?

2. Creating quality

They ensure:

The product increment meets Definition of Done.

3. Adapting their plan daily

They adjust based on:

- New information.

- Technical challenges.

- Feedback.

4. Holding each other accountable

The team owns success together.

4. Developers are NOT Task Workers

Traditional thinking:

Manager assigns tasks.

Manager

↓

Developer A: Build login

Developer B: Build database

Scrum thinking:

Team receives a goal.

Sprint Goal:

Create secure user authentication

↓

Developers decide:

Who does what?

How?

When?

This is called:

Self-Management

5. Self-Managing Teams

What is self-management?

A team decides:

- Who performs the work.

- How work is done.

- How problems are solved.

It does NOT mean:

"No leadership."

It means:

Leadership creates an environment where teams can succeed.

Example

Sprint Goal:

"Create AI adverse event extraction."

The team decides:

Developer 1:

Data pipeline.

Developer 2:

NLP model.

Developer 3:

API integration.

QA:

Validation testing.

6. Cross-Functional Teams

Definition

A cross-functional team has all skills needed to create a complete product increment.

Bad structure:

Development Team

↓

Testing Team

↓

Business Team

↓

Deployment Team

Problems:

- Handoffs.

- Waiting.

- Delays.

Agile structure:

ONE Scrum Team

Developer

QA

Designer

BA

Data Expert

Domain Expert

Healthcare Example

Hospital AI Platform team:

Members:

- Backend developer.

- Frontend developer.

- ML engineer.

- QA engineer.

- Healthcare analyst.

- UX designer.

The team can deliver complete features.

7. Developers and Product Owner Relationship

Product Owner:

Defines:

"What problem should we solve?"

Developers decide:

"How will we solve it?"

Example:

PO:

"We need faster pharmacovigilance case processing."

Developers decide:

Solution:

- AI extraction.

- Workflow automation.

- Database optimization.

Wrong relationship:

PO:

"Use Python and TensorFlow."

Why wrong?

PO should define value, not technical implementation.

8. Developers and Scrum Master Relationship

Scrum Master helps Developers:

- Remove blockers.

- Improve collaboration.

- Learn Scrum.

- Improve processes.

Scrum Master does NOT:

- Assign tasks.

- Evaluate individual performance.

- Control technical decisions.

9. Definition of Done (DoD)

This is one of the most important Scrum concepts.

Simple definition

Definition of Done describes:

The conditions that must be completed before work can be considered finished.

Without Definition of Done:

Developer:

"I completed coding."

Tester:

"But testing is pending."

Business:

"But documentation is missing."

Definition of Done creates shared understanding.

Example: Login Feature

Not Done:

❌ Code written.

Done:

✅ Code completed.

✅ Unit tests passed.

✅ Security testing completed.

✅ User acceptance completed.

✅ Documentation updated.

10. Definition of Done in Healthcare

Example:

AI Pharmacovigilance Feature:

"AI extracts adverse events."

Done means:

✅ Model developed.

✅ Accuracy tested.

✅ Medical validation completed.

✅ Audit trail created.

✅ Regulatory requirements checked.

✅ Documentation completed.

11. Definition of Done vs Acceptance Criteria

Very common interview question.

Definition of Done

Applies to:

Entire product work.

Created by:

Scrum Team.

Example:

Every feature requires:

- Testing.

- Review.

- Documentation.

Acceptance Criteria

Applies to:

Specific user story.

Created by:

Product Owner/team.

Example:

User Story:

"As a safety officer, I want AI extraction so that I reduce manual entry."

Acceptance Criteria:

- System extracts patient age.

- System identifies adverse event.

- Confidence score displayed.

Comparison

| Definition of Done | Acceptance Criteria |
| --- | --- |
| Product quality standard | Feature requirement |
| Applies to all stories | Applies to one story |
| Team responsibility | Story-specific |
| Defines completeness | Defines correctness |

12. Quality Ownership

In Scrum:

Quality is everyone's responsibility.

Not:

"Testing team's responsibility."

Traditional:

Developer → Tester → Quality

Agile:

Everyone owns quality.

Example:

AI healthcare system:

Developer:

Writes clean code.

Data scientist:

Validates model.

QA:

Tests functionality.

Domain expert:

Checks medical accuracy.

13. Engineering Practices in Scrum

Scrum does not prescribe technical practices.

But successful teams often use:

1. Continuous Integration (CI)

Frequently integrate code.

2. Automated Testing

Reduce manual errors.

3. Code Reviews

Improve quality.

4. Refactoring

Improve code quality.

5. Automated Deployment

Deliver faster.

14. Developers in AI Product Development

AI products are different from traditional software.

Developers handle:

- Data pipelines.

- Model training.

- Testing.

- Deployment.

- Monitoring.

Example:

AI Drug Safety Platform.

Developers work on:

- NLP extraction.

- Duplicate detection.

- Signal algorithms.

- Reporting automation.

15. Developers in Pharmacovigilance

Example:

Feature:

"Automatically identify adverse events from reports."

Team responsibilities:

AI engineer:

Build model.

Backend developer:

Create API.

QA:

Validate workflow.

PV expert:

Verify medical correctness.

Common Mistakes

Mistake 1:

Developers only write code.

Wrong.

They create product value.

Mistake 2:

Manager assigns every task.

Wrong.

Scrum teams self-manage.

Mistake 3:

Quality belongs only to QA.

Wrong.

Everyone owns quality.

Mistake 4:

Done means "coding finished."

Wrong.

Done means complete usable increment.

Best Practices

Developers should:

✅ Understand product goals
✅ Collaborate with PO
✅ Participate in planning
✅ Own quality
✅ Improve continuously
✅ Communicate blockers early

Interview Questions

Q1. Who are Developers in Scrum?

Answer:

Developers are people responsible for creating any aspect of a usable product increment.

Q2. Are Developers only programmers?

Answer:

No. Anyone contributing to creating product value can be a Developer.

Q3. What is Definition of Done?

Answer:

A shared understanding of what conditions must be satisfied before work is considered complete.

Q4. Difference between Acceptance Criteria and Definition of Done?

Answer:

Acceptance Criteria defines requirements for a specific story, while Definition of Done defines quality standards for all work.

Q5. Who assigns tasks in Scrum?

Answer:

Developers self-manage and decide how to organize their work.

Mini Quiz

Answer these:

- What does Developer mean in Scrum?

- What is self-management?

- Who owns quality in Scrum?

- Difference between DoD and Acceptance Criteria?

- Why are cross-functional teams important?

Practical Assignment

Design the Scrum Development Team for:

AI Pharmacovigilance Platform

Create team members:

Example:

- Backend Developer

- Frontend Developer

- AI/ML Engineer

- Data Engineer

- QA Engineer

- Pharmacovigilance Expert

- UX Designer

Create:

Definition of Done

For an AI case processing feature.

Example:

- Code complete.

- AI accuracy validated.

- Testing completed.

- Security reviewed.

- Medical approval completed.

Create:

Acceptance Criteria

For:

User Story:

"As a safety officer, I want AI to extract adverse events from case reports."

Summary

Developers are the creators of product value.

They:

✅ Build increments
✅ Own quality
✅ Self-manage work
✅ Collaborate with Product Owner
✅ Improve continuously

Key Takeaways

- Developer ≠ only programmer.

- Scrum Developers are cross-functional contributors.

- Teams decide how work is done.

- Quality belongs to everyone.

- Definition of Done creates transparency.

- Self-management is a core Agile principle.

Lesson 34: Scrum Artifacts Deep Dive – Product Backlog, Sprint Backlog, Increment, Product Goal, Sprint Goal, and Transparency

Learning Objectives

By the end of this lesson, you will understand:

- What Scrum artifacts are.

- Why Scrum needs artifacts.

- Product Backlog in detail.

- Sprint Backlog in detail.

- Increment in detail.

- Product Goal.

- Sprint Goal.

- Artifact commitments.

- Transparency in Scrum.

- Healthcare and AI examples.

- Interview-level understanding.

1. What are Scrum Artifacts?

Simple definition

Scrum artifacts are:

Information sources that provide transparency about the product, work, and progress.

Simple meaning:

Artifacts help everyone answer:

- What are we building?

- What are we working on now?

- What is completed?

Real-life analogy

Imagine building a hospital.

You need:

Blueprint

What hospital should become.

↓

Current construction plan

What workers are doing today.

↓

Completed building section

What has been finished.

In Scrum:

Blueprint → Product Backlog

Current plan → Sprint Backlog

Completed section → Increment

Scrum Artifacts Overview

Product Goal

↓

Product Backlog

↓

Sprint Planning

↓

Sprint Goal

↓

Sprint Backlog

↓

Increment

2. Three Scrum Artifacts

Scrum officially defines three artifacts:

1. Product Backlog

Commitment:

Product Goal

2. Sprint Backlog

Commitment:

Sprint Goal

3. Increment

Commitment:

Definition of Done

3. Product Backlog

Definition

Product Backlog is:

An ordered list of everything needed to improve the product.

Simple meaning:

It is the complete list of:

- Features.

- Improvements.

- Bugs.

- Technical work.

- Research.

Example:

AI Pharmacovigilance Platform Product Backlog:

1. User Login

2. Case Intake

3. AI Data Extraction

4. MedDRA Coding

5. Duplicate Detection

6. Signal Detection

7. Compliance Dashboard

8. Reporting

4. Who owns Product Backlog?

Answer:

Product Owner

The Product Owner is accountable for:

- Creating backlog clarity.

- Ordering backlog.

- Maximizing value.

Important:

Developers contribute.

Stakeholders provide input.

But PO owns the outcome.

5. Product Backlog Characteristics

A good backlog is:

Ordered

Highest value first.

Visible

Everyone understands priorities.

Dynamic

Changes based on learning.

Refined

Items become clearer over time.

6. Product Backlog Items (PBIs)

A Product Backlog contains:

- User stories.

- Features.

- Bugs.

- Improvements.

- Technical debt.

- Research items.

Example:

User Story:

"As a safety officer, I want AI to extract adverse events from reports so that manual processing time is reduced."

7. Product Goal

New Scrum concept.

Definition:

Product Goal describes:

The future state of the product that the Scrum Team wants to achieve.

Simple meaning:

The destination.

Example:

Product Goal:

"Create an AI-powered pharmacovigilance platform that reduces manual case processing by 60%."

Product Vision vs Product Goal

| Product Vision | Product Goal |
| --- | --- |
| Long-term direction | Specific objective |
| Inspirational | Achievable target |
| Years | Months/quarters |

Example:

Vision:

"Transform drug safety using AI."

Goal:

"Automate adverse event extraction within 6 months."

8. Backlog Refinement

What is refinement?

The process of improving backlog items.

Activities:

- Add details.

- Split large items.

- Estimate effort.

- Clarify acceptance criteria.

Example:

Before refinement:

"Build AI module"

Too big.

After refinement:

Split into:

- Upload case document.

- Extract patient information.

- Extract adverse event.

- Show confidence score.

9. Sprint Backlog

Definition:

Sprint Backlog is:

The set of Product Backlog items selected for the Sprint plus the plan for delivering them.

Simple meaning:

The team's current work.

Example:

Sprint Goal:

"Create automated case intake."

Sprint Backlog:

✓ Create upload interface

✓ Extract PDF text

✓ Store case data

✓ Validate extracted fields

10. Who owns Sprint Backlog?

Answer:

Developers

Because they decide:

- How work gets done.

- How tasks are organized.

Product Owner:

Provides priorities.

Developers:

Create Sprint plan.

11. Sprint Goal

Definition:

Sprint Goal is:

A single objective for the Sprint.

Why?

Without Sprint Goal:

Team only completes random tasks.

Example:

Bad:

"Complete login, dashboard, reports."

Good:

"Enable safety officers to access the case management system."

Sprint Goal Benefits

Provides:

- Focus.

- Flexibility.

- Team alignment.

12. Increment

Definition:

Increment is:

A usable, valuable piece of the product created during a Sprint.

Important:

Increment must be:

- Usable.

- Tested.

- Meets Definition of Done.

Example:

Sprint 1:

Increment:

Working login system.

Sprint 2:

Increment:

Case upload feature.

Sprint 3:

Increment:

AI extraction feature.

13. Can there be multiple increments?

Yes.

A Sprint may create:

- One increment.

- Multiple increments.

Example:

AI Platform Sprint:

Increment 1:

Case upload.

Increment 2:

AI extraction.

Increment 3:

Audit trail.

14. Increment vs Release

Important interview question.

Increment:

Completed product improvement.

Release:

Making product available to users.

Example:

Sprint 1:

AI extraction completed.

Increment created.

After testing:

Company releases it.

Release happens.

15. Definition of Done as Artifact Commitment

Every Increment must meet:

Definition of Done.

Example:

AI Feature:

Done means:

✅ Code complete

✅ Tested

✅ AI accuracy validated

✅ Security checked

✅ Documentation complete

16. Transparency in Scrum

Artifacts exist for transparency.

Without transparency:

Problems remain hidden.

Example:

Dashboard shows:

Sprint progress.

Backlog priorities.

Quality status.

Everyone understands reality.

17. Healthcare Example

Hospital Management System

Product Goal:

"Create digital patient management platform."

Product Backlog:

- Registration.

- Appointment.

- Prescription.

- Billing.

Sprint Goal:

"Enable online appointment booking."

Increment:

Working appointment booking.

18. AI Product Example

AI Medical Assistant

Product Goal:

"Provide safe AI-powered patient assistance."

Sprint Goal:

"Enable symptom-based conversations."

Increment:

Working chatbot prototype.

19. Pharmacovigilance Example

AI Drug Safety Platform

Product Goal:

"Reduce manual safety processing."

Sprint Goal:

"Automate case data extraction."

Increment:

AI extraction module.

Common Mistakes

Mistake 1:

Backlog is a task list.

Wrong.

It represents product value.

Mistake 2:

Sprint Backlog cannot change.

Wrong.

Developers adapt during Sprint.

Mistake 3:

Increment means unfinished work.

Wrong.

Increment must be usable.

Mistake 4:

PO assigns Sprint tasks.

Wrong.

Developers decide.

Best Practices

Product Backlog

✅ Keep prioritized
✅ Add clear acceptance criteria
✅ Remove outdated items

Sprint Backlog

✅ Maintain Sprint Goal
✅ Update daily
✅ Collaborate

Increment

✅ Always meet DoD
✅ Maintain quality
✅ Deliver value

Interview Questions

Q1. What are Scrum artifacts?

Answer:

Product Backlog, Sprint Backlog, and Increment.

Q2. Who owns Product Backlog?

Answer:

Product Owner.

Q3. Who creates Sprint Backlog?

Answer:

Developers during Sprint Planning.

Q4. What is Sprint Goal?

Answer:

A single objective that provides focus for the Sprint.

Q5. Difference between Increment and Release?

Answer:

Increment is completed product work; release is making it available to users.

Mini Quiz

Answer:

- What are the three Scrum artifacts?

- Who owns Product Backlog?

- What is Product Goal?

- What is Sprint Goal?

- What makes an Increment complete?

Practical Assignment

Create Scrum artifacts for:

AI Pharmacovigilance Platform

Product Goal:

Write one.

Product Backlog:

Create 10 items.

Sprint Goal:

Create Sprint 1 goal.

Sprint Backlog:

Select 5 items.

Increment:

Define what will be delivered.

Summary

Scrum artifacts create transparency.

Three artifacts:

Product Backlog

The complete product plan.

Sprint Backlog

The team's current plan.

Increment

The completed valuable product.

Key Takeaways

✅ Product Backlog = What needs to be built
✅ Sprint Backlog = What we build now
✅ Increment = What is completed
✅ Product Goal = Future direction
✅ Sprint Goal = Current objective
✅ Definition of Done = Quality standard

Lesson 34a – Sprint Backlog & Increment (Deep Dive)

Learning Objectives

By the end of this lesson, you will understand:

- What Sprint Backlog is

- Why Sprint Backlog exists

- Components of Sprint Backlog

- How Sprint Backlog is created

- How Sprint Backlog evolves during the Sprint

- What an Increment is

- Definition of Valuable Increment

- Increment vs Product Backlog

- Increment vs Release

- Healthcare examples

- Pharmacovigilance examples

- AI Product examples

- Common mistakes

- Best Practices

- Interview Questions

- Mini Quiz

- Practical Assignment

1. Recap

Before understanding Sprint Backlog, remember the three Scrum Artifacts.

Product Backlog

↓

Sprint Backlog

↓

Increment

Think of Scrum like preparing for an examination.

Product Backlog

Complete syllabus.

Sprint Backlog

Chapters you will study this week.

Increment

Knowledge you actually gained.

2. What is Sprint Backlog?

Scrum Guide Definition

The Sprint Backlog is composed of:

- Sprint Goal

- Selected Product Backlog Items

- Actionable plan for delivering them.

Simple Meaning

The Sprint Backlog is the team's plan for achieving the Sprint Goal.

It answers three questions:

- What are we building?

- Why are we building it?

- How will we build it?

3. Why Does Scrum Need Sprint Backlog?

Imagine an AI healthcare platform has 300 features.

Example Product Backlog

Login

Dashboard

AI Extraction

Reports

Notifications

Audit Logs

Signal Detection

Drug Coding

User Roles

Analytics

...

Can a team build all 300 features in one Sprint?

No.

Instead they choose only a few.

Example

Sprint Goal

"Create basic AI Case Intake."

Sprint Backlog

Login

Upload PDF

Extract Patient Name

Store Case

Unit Testing

Everything else stays in Product Backlog.

4. Components of Sprint Backlog

A Sprint Backlog has three parts.

A. Sprint Goal

The reason behind the Sprint.

Example

"Enable automatic case intake."

B. Selected Product Backlog Items

Example

User Login

Upload Medical Report

OCR Integration

Save Case

Basic Dashboard

C. Delivery Plan

Developers decide:

- Who works on what

- Sequence

- Technical approach

- Testing

- Deployment

Important

The Product Owner does NOT create this plan.

Developers own it.

5. Who Owns Sprint Backlog?

Very common interview question.

Product Owner owns

Product Backlog

Developers own

Sprint Backlog

Scrum Master

Facilitates the process.

6. How Sprint Backlog is Created

During Sprint Planning.

Example

Step 1

Product Owner presents highest-priority items.

↓

Step 2

Developers discuss effort.

↓

Step 3

Team selects work.

↓

Step 4

Sprint Goal is created.

↓

Step 5

Developers prepare execution plan.

↓

Sprint starts.

7. Sprint Backlog Example

Suppose we are building an AI Pharmacovigilance Platform.

Sprint Goal

"Automate adverse event intake."

Sprint Backlog

| ID | User Story |
| --- | --- |
| PB-12 | Upload PDF |
| PB-18 | Extract Patient Name |
| PB-21 | Detect Adverse Event |
| PB-23 | Save Case |
| PB-29 | Unit Tests |
| PB-31 | API Integration |

Developers may further divide work.

Example

Frontend

Backend API

Database

Testing

Deployment

8. Sprint Backlog is NOT Fixed

One common misconception.

Wrong

Sprint Backlog never changes.

Correct

Sprint Backlog evolves every day.

Example

Day 2

Developers discover OCR library has limitations.

They decide to

Replace OCR library.

Add preprocessing.

Remove unnecessary task.

Sprint Goal remains unchanged.

Sprint Backlog changes.

This is perfectly acceptable.

9. Can New Work be Added?

Yes.

Only if it helps achieve Sprint Goal.

Example

Sprint Goal

"AI extracts patient name."

During development

Developers discover preprocessing is required.

New task

"Image Enhancement"

is added.

This supports Sprint Goal.

Allowed.

10. Can Work be Removed?

Yes.

If unnecessary.

Example

Originally planned

Manual validation screen.

Later

AI performs validation automatically.

Manual screen removed.

Sprint Goal still achieved.

11. Product Backlog vs Sprint Backlog

| Product Backlog | Sprint Backlog |
| --- | --- |
| Entire product work | Current Sprint work |
| Owned by Product Owner | Owned by Developers |
| Long-term | Short-term |
| Prioritized | Selected |
| Changes continuously | Evolves during Sprint |

Interview Question

Which backlog changes more often?

Answer

Sprint Backlog.

12. What is Increment?

Scrum Guide

An Increment is a concrete stepping stone toward the Product Goal.

Simple Meaning

An Increment is working product created during a Sprint.

Not

Design

Documentation only

Ideas

Slides

Meetings

It must be usable.

13. Increment Example

Sprint 1

Working Login

↓

Increment

Sprint 2

Upload Cases

↓

New Increment

Sprint 3

AI Extraction

↓

New Increment

Every Sprint produces another usable Increment.

14. Characteristics of a Good Increment

A good Increment is

✔ Working

✔ Tested

✔ Integrated

✔ Valuable

✔ Meets Definition of Done

Example

AI Drug Safety Platform

Increment

Upload PDF

OCR works

Patient extracted

Stored in database

Tests passed

Documentation complete

This is a usable Increment.

15. Increment vs Release

Many beginners confuse these.

Increment

Working product.

Release

Product delivered to customers.

Example

Sprint 1

Working Login

↓

Increment

Sprint 2

Dashboard

↓

Increment

Sprint 3

Reports

↓

Increment

Company releases all three together.

One Release.

Many Increments.

16. Increment in Healthcare

Hospital Management System

Sprint 1

Patient Registration

Increment

Working registration module.

Sprint 2

Appointment Booking

Increment

Working appointment scheduling.

Sprint 3

Prescription Module

Increment

Doctors can generate prescriptions.

17. Increment in Pharmacovigilance

AI Drug Safety Platform

Sprint 1

Case Intake

Increment

Working upload system.

Sprint 2

AI Extraction

Increment

Automatic entity extraction.

Sprint 3

MedDRA Coding

Increment

Automatic coding engine.

Each Sprint delivers business value.

18. Increment in AI Products

AI Medical Assistant

Sprint 1

Basic chatbot.

Sprint 2

Medical knowledge.

Sprint 3

Drug interaction detection.

Sprint 4

Voice assistant.

Every Sprint creates another Increment.

19. Common Mistakes

Mistake 1

Treat Sprint Backlog as fixed.

Wrong.

It evolves daily.

Mistake 2

Product Owner assigns tasks.

Wrong.

Developers decide how work is done.

Mistake 3

Increment means "code written."

Wrong.

Code is not enough.

Increment must satisfy Definition of Done.

Mistake 4

Every Sprint must produce a Release.

Wrong.

Every Sprint produces an Increment.

Release happens when business decides.

20. Best Practices

✔ Keep Sprint Goal clear.

✔ Keep Sprint Backlog visible.

✔ Update Sprint Backlog daily.

✔ Deliver one usable Increment every Sprint.

✔ Never compromise Definition of Done.

✔ Focus on value rather than completing tasks.

21. Interview Questions

Q1. Who owns the Sprint Backlog?

Answer: Developers own the Sprint Backlog.

Q2. Can Sprint Backlog change during the Sprint?

Answer: Yes. Developers continuously update it as they learn more, provided changes support the Sprint Goal.

Q3. What is an Increment?

Answer: A usable, tested, integrated piece of the product that meets the Definition of Done and contributes toward the Product Goal.

Q4. Difference between Product Backlog and Sprint Backlog?

Answer:

- Product Backlog contains all planned product work.

- Sprint Backlog contains only the work selected for the current Sprint.

Q5. Difference between Increment and Release?

Answer:

- Every Sprint should produce an Increment.

- A Release is a business decision to make one or more Increments available to users.

Mini Quiz

- Who owns the Sprint Backlog?

- Can Sprint Backlog change during a Sprint?

- What are the three components of a Sprint Backlog?

- What is an Increment?

- Does every Increment have to be released to customers?

Practical Assignment

For your AI Pharmacovigilance Platform:

1. Define a Sprint Goal

Example:

"Enable automated adverse event case intake from PDF reports."

2. Create a Sprint Backlog

Include at least six Product Backlog Items.

3. Describe the Increment

Explain what working functionality will be available at the end of the Sprint.

4. Identify two tasks that may be added during the Sprint and explain why they still support the Sprint Goal.

Summary

The Sprint Backlog is the Developers' living plan for achieving the Sprint Goal. It includes the Sprint Goal, selected Product Backlog Items, and the work needed to deliver them. It evolves throughout the Sprint as the team learns more.

An Increment is the usable outcome of the Sprint. Every Increment must meet the Definition of Done, be integrated with previous work, and move the product closer to its Product Goal.

Key Takeaways

- Sprint Backlog is owned by Developers.

- It contains the Sprint Goal, selected work, and the implementation plan.

- The Sprint Backlog changes throughout the Sprint as needed.

- Every Sprint should produce one or more usable Increments.

- An Increment is not just code—it must meet the Definition of Done.

- Many Increments can be combined into a single Release.

- In healthcare, pharmacovigilance, and AI products, delivering valuable Increments each Sprint reduces risk, enables rapid feedback, and supports continuous improvement.

Lesson 35: Scrum Events Deep Dive – Sprint, Sprint Planning, Daily Scrum, Sprint Review, Sprint Retrospective, and Backlog Refinement

Learning Objectives

By the end of this lesson, you will understand:

- Why Scrum uses events.

- The purpose of each event.

- Participants.

- Duration.

- Inputs and outputs.

- Common mistakes.

- Healthcare examples.

- AI Product examples.

- Interview answers.

1. What are Scrum Events?

Simple definition

Scrum Events are:

Formal opportunities for inspection and adaptation.

Simple meaning:

Scrum events help teams:

- Check progress.

- Get feedback.

- Improve.

Real-life analogy

Imagine a medical research team.

They don't wait until the end of a 5-year study to check results.

They regularly review:

- Data.

- Safety.

- Progress.

Then adjust.

Scrum works similarly.

Scrum Events Overview

There are five Scrum events:

Sprint

|

--------------------------------

Sprint Planning

↓

Daily Scrum

↓

Sprint Review

↓

Sprint Retrospective

--------------------------------

2. The Sprint

The Sprint is the container for all Scrum events.

Definition

A Sprint is:

A fixed-length period during which the team creates a valuable product Increment.

Typical duration:

2–4 weeks.

Most companies:

2 weeks.

Sprint Characteristics

A Sprint has:

Fixed duration

Example:

14 days.

Sprint Goal

A clear objective.

Product Increment

Working output.

Sprint Example

AI Pharmacovigilance Platform:

Sprint duration:

2 weeks.

Sprint Goal:

"Enable automated case document upload."

Increment:

Working upload and storage feature.

What happens inside a Sprint?

Day 1

Sprint Planning

↓

Days 2-13

Development

Testing

Daily Scrum

↓

Day 14

Review

↓

Retrospective

3. Sprint Planning

Purpose

Sprint Planning answers:

Two questions:

Why is this Sprint valuable?

What can be done?

How will we do it?

Participants

Mandatory:

- Product Owner

- Scrum Master

- Developers

Stakeholders:

Usually not required.

Sprint Planning Activities

Step 1: Define Sprint Goal

Example:

"Create AI-powered case extraction capability."

Step 2: Select Backlog Items

Team chooses items.

Step 3: Create Sprint Plan

Developers decide approach.

Inputs for Sprint Planning

- Product Backlog.

- Product Goal.

- Previous performance.

- Team capacity.

Outputs

- Sprint Goal.

- Sprint Backlog.

Example

Product Backlog:

- Login

- AI extraction

- Dashboard

- Reports

Team selects:

AI extraction.

Sprint Goal:

"Reduce manual case entry using AI."

Common Mistakes

Mistake 1:

PO assigns tasks.

Wrong.

Developers decide.

Mistake 2:

Selecting too much work.

Problem:

Sprint fails.

4. Daily Scrum

Purpose

Daily Scrum is:

A 15-minute event for Developers to inspect progress toward the Sprint Goal.

Important:

It is NOT:

A status report to manager.

Participants

Main participants:

Developers.

Others may attend.

Traditional Questions

Many teams use:

- What did I do yesterday?

- What will I do today?

- Any blockers?

Modern Scrum focuses on:

"How can we collaborate better to achieve Sprint Goal?"

Example

Sprint Goal:

AI extraction.

Discussion:

Developer:

"Model accuracy improved."

Tester:

"Need more validation data."

Team adjusts.

Common Mistakes

❌ Reporting to Scrum Master.

❌ Long discussions.

❌ Talking about individual tasks only.

5. Sprint Review

Purpose

Inspect the Increment and adapt the Product Backlog.

Simple meaning:

Show what was built and collect feedback.

Participants

- Scrum Team.

- Stakeholders.

Activities

Team demonstrates working product.

Example:

AI Pharmacovigilance Demo:

Before:

Manual case entry.

After:

AI extracts patient details automatically.

Stakeholder feedback:

"Need support for PDF reports."

PO updates backlog.

Sprint Review is NOT:

❌ Presentation meeting.

❌ Approval meeting.

❌ Status meeting.

It is:

A collaboration session.

6. Sprint Retrospective

Purpose

Improve the team's way of working.

Question:

"What should we change for the next Sprint?"

Participants

Only:

Scrum Team.

Includes:

- Product Owner.

- Scrum Master.

- Developers.

Common Retrospective Format

What went well?

Example:

"Communication improved."

What did not go well?

Example:

"Testing started too late."

What will we improve?

Example:

"Start testing from day 3."

Difference: Review vs Retrospective

Very common interview question.

| Sprint Review | Sprint Retrospective |
| --- | --- |
| Product focused | Process focused |
| Stakeholders attend | Scrum Team only |
| Review product | Improve teamwork |
| External feedback | Internal improvement |

7. Backlog Refinement

Important:

Backlog Refinement is NOT an official Scrum event.

But widely practiced.

Purpose

Improve future backlog items.

Activities:

- Clarify requirements.

- Add acceptance criteria.

- Split stories.

- Estimate.

Example

Large story:

"Build AI system."

Split into:

- Upload documents.

- Extract data.

- Validate output.

- Generate report.

8. Healthcare Example

Hospital Management System

Sprint:

2 weeks.

Sprint Planning:

Goal:

"Enable patient registration."

Daily Scrum:

Discuss:

- Development progress.

- Issues.

Sprint Review:

Show registration module.

Retrospective:

Improve testing process.

9. Pharmacovigilance Example

AI Drug Safety Platform:

Sprint Goal:

"Automate adverse event extraction."

Sprint Planning:

Select:

- Document upload.

- NLP extraction.

- Validation workflow.

Daily Scrum:

Discuss:

- Model accuracy.

- Data issues.

Sprint Review:

PV experts test system.

Retrospective:

Improve AI validation process.

10. AI Product Example

AI Medical Assistant:

Sprint Goal:

"Improve chatbot response accuracy."

Sprint Review:

Users test responses.

Feedback:

"Need better medical explanations."

Backlog updated.

Common Scrum Event Mistakes

Mistake 1:

Sprint Review = Demo only.

Wrong.

It is feedback and collaboration.

Mistake 2:

Retrospective = Complaint session.

Wrong.

It must create improvement actions.

Mistake 3:

Daily Scrum = Manager meeting.

Wrong.

It is team coordination.

Mistake 4:

Sprint Planning only selects tasks.

Wrong.

It creates Sprint Goal and plan.

Best Practices

Sprint Planning

✅ Clear Sprint Goal
✅ Realistic commitment
✅ Team involvement

Daily Scrum

✅ Focus on Sprint Goal
✅ Solve collaboration issues
✅ Keep short

Sprint Review

✅ Demonstrate working product
✅ Invite feedback

Retrospective

✅ Create action items
✅ Follow up improvements

Interview Questions

Q1. What are Scrum Events?

Answer:

Sprint, Sprint Planning, Daily Scrum, Sprint Review, Sprint Retrospective.

Q2. Difference between Sprint Review and Retrospective?

Answer:

Sprint Review improves the product through stakeholder feedback; Retrospective improves the team's process.

Q3. Who attends Daily Scrum?

Answer:

Developers. Others may attend but Developers are responsible.

Q4. What happens in Sprint Planning?

Answer:

The team defines Sprint Goal, selects backlog items, and creates a plan.

Q5. Why are Scrum events time-boxed?

Answer:

To create regular opportunities for inspection and adaptation without wasting time.

Mini Quiz

Answer:

- What is the purpose of Sprint?

- Who owns Sprint Backlog?

- Difference between Review and Retrospective?

- Is Backlog Refinement an official Scrum event?

- Why is Daily Scrum not a status meeting?

Practical Assignment

Create Scrum events for:

AI Pharmacovigilance Platform

Sprint duration:

Choose:

1 week / 2 weeks / 4 weeks

Create:

Sprint Goal

Sprint Planning agenda

Daily Scrum example discussion

Sprint Review participants

Retrospective improvement actions

Summary

Scrum Events create a rhythm of:

Plan

↓

Build

↓

Inspect

↓

Improve

Key Takeaways

✅ Sprint creates value
✅ Planning creates direction
✅ Daily Scrum creates alignment
✅ Review creates feedback
✅ Retrospective creates improvement

Lesson 35a – Sprint Planning (Complete Guide)

Learning Objectives

By the end of this lesson, you will understand:

- What is Sprint Planning?

- Purpose of Sprint Planning

- Scrum Guide definition

- Inputs to Sprint Planning

- Outputs of Sprint Planning

- Three key topics of Sprint Planning

- Roles and responsibilities

- Capacity Planning

- Forecasting work

- Task Breakdown

- Handling dependencies

- Healthcare examples

- Pharmacovigilance examples

- AI Product examples

- Common mistakes

- Best Practices

- Interview Questions

- Mini Quiz

- Practical Assignment

1. Introduction

Imagine a cricket team walking onto the field without discussing:

- Batting order

- Bowling strategy

- Field placement

- Target score

The chances of winning would be very low.

Software development is similar.

Before a Sprint begins, the Scrum Team must decide:

- What should be built?

- Why is it important?

- How will it be built?

This discussion is called Sprint Planning.

Sprint Planning ensures that everyone starts the Sprint with the same understanding and a clear objective.

2. Scrum Guide Definition

The Scrum Guide defines Sprint Planning as:

Sprint Planning initiates the Sprint by laying out the work to be performed for the Sprint. This resulting plan is created by the collaborative work of the entire Scrum Team.

In simple terms:

Sprint Planning is the meeting where the Scrum Team decides what value will be delivered during the upcoming Sprint and how it will be accomplished.

3. Why is Sprint Planning Important?

Without Sprint Planning:

- Developers start different tasks.

- Priorities are unclear.

- Work exceeds team capacity.

- Sprint Goals are missed.

- Stakeholders receive unpredictable results.

With Sprint Planning:

✔ Everyone knows the goal.

✔ Work is realistic.

✔ Team commitment improves.

✔ Risks are identified early.

4. When Does Sprint Planning Happen?

Sprint Planning is always the first event of a Sprint.

Previous Sprint Ends

│

▼

Sprint Planning

│

▼

Sprint Starts

No development should begin before Sprint Planning is complete.

5. Timebox

Sprint Planning is timeboxed.

Maximum duration:

| Sprint Length | Planning Time |
| --- | --- |
| 1 Week | ~2 Hours |
| 2 Weeks | ~4 Hours |
| 1 Month | Up to 8 Hours |

Longer meetings usually indicate poor backlog preparation.

6. Who Attends Sprint Planning?

Entire Scrum Team

Product Owner

- Explains priorities

- Clarifies requirements

- Presents Product Backlog

Developers

- Estimate effort

- Ask questions

- Select work

- Break stories into tasks

Scrum Master

- Facilitates meeting

- Ensures Scrum rules are followed

- Removes obstacles

Stakeholders normally do not attend unless invited to clarify requirements.

7. Inputs to Sprint Planning

Sprint Planning requires several inputs.

Product Backlog

Ordered list of work.

Product Goal

Long-term direction.

Previous Sprint Results

Lessons learned.

Team Capacity

Available working hours.

Velocity

Historical delivery data.

Definition of Done

Quality standard.

Business Priorities

Highest-value work.

8. Three Topics of Sprint Planning

According to the Scrum Guide, Sprint Planning addresses three important questions.

Topic 1 – Why is this Sprint valuable?

The Product Owner explains:

- Business objective

- Customer value

- Priority

Together the Scrum Team creates the Sprint Goal.

Example:

"Allow patients to schedule appointments online."

Topic 2 – What can be Done?

Developers forecast which Product Backlog Items can be completed.

Factors considered:

- Team capacity

- Complexity

- Dependencies

- Velocity

The selected items become the Sprint Backlog.

Topic 3 – How will the work get Done?

Developers create a plan.

They:

- Break stories into tasks.

- Identify dependencies.

- Discuss architecture.

- Decide implementation approach.

This creates the execution plan.

9. Sprint Planning Workflow

Product Backlog

│

▼

Business Priority

│

▼

Sprint Goal

│

▼

Select Stories

│

▼

Estimate Work

│

▼

Capacity Check

│

▼

Task Breakdown

│

▼

Sprint Backlog

10. Capacity Planning

One of the biggest mistakes in Scrum is assuming everyone is available full-time.

Example:

Team:

6 Developers

Sprint:

10 Working Days

Working Hours:

8 hours/day

Raw Capacity

6 × 10 × 8

= 480 hours

But:

- Meetings

- Holidays

- Training

- Leave

- Production support

Actual Capacity

≈ 380 hours

Sprint Planning must consider actual, not theoretical, capacity.

11. Forecasting Work

Developers forecast—not promise—what can be completed.

Forecast depends on:

- Velocity

- Capacity

- Story complexity

- Risk

Scrum encourages realistic forecasting rather than unrealistic commitments.

12. Example

AI Healthcare Platform

Product Backlog

- Login

- OCR

- AI Extraction

- Dashboard

- Reports

- Notifications

Capacity

40 Story Points

Stories Selected

- Login (8)

- OCR (13)

- AI Extraction (13)

Total

34 Story Points

The remaining capacity is reserved for unforeseen work.

13. Task Breakdown

Large User Story

"Upload Medical Report"

Developers divide into:

- Database

- Backend API

- UI

- Validation

- Unit Tests

- Integration Tests

Breaking work into smaller tasks improves visibility and collaboration.

14. Managing Dependencies

Dependencies increase Sprint risk.

Example

AI Feature depends on:

- OCR API

- Authentication Service

- Database

- Cloud Storage

If these dependencies are not identified during Sprint Planning, the Sprint may be delayed.

15. Healthcare Example

Hospital Appointment System

Sprint Goal

"Enable appointment booking."

Stories

- Search Doctors

- Calendar

- Booking

- SMS Confirmation

Capacity

28 Story Points

Forecast

26 Story Points

Remaining buffer handles unforeseen issues.

16. Pharmacovigilance Example

AI Drug Safety Platform

Sprint Goal

"Automatically classify Individual Case Safety Reports (ICSRs)."

Selected Stories

- Upload Case

- OCR Processing

- Patient Extraction

- MedDRA Coding

- Case Validation

Dependencies

- NLP Engine

- MedDRA Dictionary

- Database

- Regulatory Rules

Planning identifies all dependencies before development begins.

17. AI Product Example

Medical AI Assistant

Sprint Goal

"Generate patient-friendly summaries."

Stories

- Prompt Engineering

- LLM Integration

- Hallucination Detection

- Evaluation Dashboard

Capacity

32 Story Points

Forecast

30 Story Points

Developers reserve spare capacity for model tuning.

18. Common Mistakes

Mistake 1

Selecting too much work.

Result:

Sprint failure.

Mistake 2

Ignoring team capacity.

Leads to burnout.

Mistake 3

No Sprint Goal.

Developers work on unrelated features.

Mistake 4

Product Owner assigns technical tasks.

Task planning belongs to Developers.

Mistake 5

Stories without Definition of Ready.

Confusion begins immediately.

Mistake 6

Ignoring dependencies.

Blocked work delays the Sprint.

19. Best Practices

✔ Prepare Product Backlog before Sprint Planning.

✔ Ensure stories satisfy the Definition of Ready.

✔ Create one clear Sprint Goal.

✔ Select work based on capacity.

✔ Leave a small capacity buffer.

✔ Break stories into manageable tasks.

✔ Clarify dependencies early.

✔ Encourage questions from the entire team.

20. Interview Questions

Q1. What is Sprint Planning?

Answer: Sprint Planning is the Scrum event where the Scrum Team collaboratively determines the Sprint Goal, selects Product Backlog Items, and creates a plan for delivering them during the Sprint.

Q2. Who participates in Sprint Planning?

Answer: The entire Scrum Team: Product Owner, Developers, and Scrum Master.

Q3. What are the three topics discussed during Sprint Planning?

Answer:

- Why is this Sprint valuable?

- What can be done this Sprint?

- How will the chosen work get done?

Q4. Who decides how the work will be implemented?

Answer: Developers.

Q5. Why is capacity planning important?

Answer: Capacity planning helps the team select a realistic amount of work, improving predictability and reducing the risk of overcommitting.

21. Real-World Case Study

AI Pharmacovigilance Platform

Your team is planning a two-week Sprint.

Business Goal

Reduce the manual effort required to process adverse event reports.

Team Capacity

- 5 Developers

- 1 QA Engineer

- 1 Data Scientist

Total available capacity:

42 Story Points

Selected User Stories

| Story | Points |
| --- | --- |
| Upload PDF | 5 |
| OCR Processing | 8 |
| Patient Extraction | 8 |
| Adverse Event Detection | 13 |
| Unit Testing | 3 |
| Integration Testing | 5 |

Total:

42 Story Points

The team also identifies dependencies:

- OCR API availability

- MedDRA terminology service

- Test dataset from the regulatory team

Because these are discussed during Sprint Planning, mitigation plans are prepared before the Sprint begins.

Mini Quiz

- What is the primary purpose of Sprint Planning?

- Who attends Sprint Planning?

- What are the three topics defined by the Scrum Guide?

- Why should capacity planning be performed?

- Who is responsible for deciding how the work will be completed?

Practical Assignment

For your AI Pharmacovigilance Platform:

Part 1 – Define a Sprint Goal

Create a clear Sprint Goal that delivers measurable business value.

Part 2 – Build a Sprint Plan

Select 8–10 Product Backlog Items and estimate them using Story Points.

Part 3 – Calculate Capacity

Assume:

- 6 team members

- 10 working days

- One public holiday

- One developer on leave for 2 days

Calculate the team's available capacity.

Part 4 – Identify Risks

List at least five dependencies or risks and describe how they would be addressed during Sprint Planning.

Summary

Sprint Planning is the event that launches every Sprint. During this collaborative session, the Scrum Team establishes the Sprint Goal, selects Product Backlog Items based on value and capacity, and creates a practical plan for delivering them. Effective Sprint Planning reduces uncertainty, aligns the team around shared objectives, and increases the likelihood of delivering a valuable Increment.

Key Takeaways

- Sprint Planning is the first event of every Sprint.

- The entire Scrum Team participates.

- The meeting answers three questions:

  - Why is the Sprint valuable?

  - What can be done?

  - How will it get done?

- Capacity planning and realistic forecasting are essential.

- Developers own the implementation plan.

- A well-run Sprint Planning session lays the foundation for a successful Sprint and a valuable Increment.

Lesson 35b – Daily Scrum (Complete Guide)

Learning Objectives

By the end of this lesson, you will understand:

- What is Daily Scrum?

- Purpose of Daily Scrum

- Scrum Guide definition

- Who attends Daily Scrum?

- Timebox

- Traditional Three Questions vs Scrum Guide

- Daily Scrum workflow

- Common formats of Daily Scrum

- Impediments

- Daily Scrum in Remote Teams

- Healthcare examples

- Pharmacovigilance examples

- AI Product examples

- Common mistakes

- Best Practices

- Interview Questions

- Mini Quiz

- Practical Assignment

1. Introduction

Imagine a Formula 1 racing team.

Every lap, engineers monitor:

- Car performance

- Fuel usage

- Tire condition

- Weather

- Competition

If they waited until the race ended to discuss problems, they would lose.

Software development is no different.

Small problems become major delays if they remain unnoticed.

The Daily Scrum allows the Scrum Team to inspect progress every day and adapt their plan before issues become bigger.

It is not a status meeting for management.

It is a planning meeting for the Developers.

2. Scrum Guide Definition

According to the Scrum Guide:

The purpose of the Daily Scrum is to inspect progress toward the Sprint Goal and adapt the Sprint Backlog as necessary, adjusting the upcoming planned work.

Notice what the definition emphasizes:

- Inspect progress

- Sprint Goal

- Adapt plan

It does not mention reporting status to the Scrum Master or Product Owner.

3. Why is Daily Scrum Important?

Without Daily Scrum

Day 1

Developer A discovers an API issue.

Day 3

Developer B unknowingly depends on the same API.

Day 5

QA discovers integration failures.

The entire Sprint is delayed.

With Daily Scrum

The issue is identified immediately.

Developers collaborate.

Alternative solutions are discussed.

Sprint Goal remains achievable.

4. Characteristics of Daily Scrum

Every Daily Scrum has these characteristics:

✔ Happens every working day

✔ Same time

✔ Same place (or virtual room)

✔ Maximum 15 minutes

✔ Developers inspect progress

✔ Sprint Backlog may be updated

✔ Sprint Goal remains the focus

5. Who Attends?

Mandatory

Developers

The Scrum Guide specifies that the Daily Scrum is for the Developers.

Scrum Master

Optional.

Usually attends to:

- Coach

- Facilitate

- Remove impediments

The Scrum Master does not lead the meeting unless necessary.

Product Owner

Optional.

May attend if helpful.

Should avoid turning it into a status meeting.

Stakeholders

Normally do not attend.

6. Timebox

Maximum duration

15 minutes

Regardless of team size.

Long discussions are parked.

Developers continue those discussions after the Daily Scrum.

7. Daily Scrum is NOT a Status Meeting

Many organizations misunderstand Daily Scrum.

Wrong

Developers report progress to the Scrum Master.

Correct

Developers coordinate with one another.

The audience is the Development Team—not management.

8. Traditional Three Questions

Historically many Scrum Teams use three questions.

- What did I complete yesterday?

- What will I do today?

- What blockers do I have?

These questions remain useful.

However...

9. Scrum Guide Perspective

The latest Scrum Guide does not require the three questions.

Instead,

Developers may use any structure that helps inspect progress toward the Sprint Goal.

Examples:

- Kanban board

- Sprint Backlog

- Task board

- Flow diagram

- Burndown chart

The goal is adaptation—not answering fixed questions.

10. Daily Scrum Workflow

Yesterday's Progress

│

▼

Current Sprint Status

│

▼

Identify Blockers

│

▼

Adjust Sprint Backlog

│

▼

Plan Next 24 Hours

11. Example

Sprint Goal

"Implement AI-powered patient extraction."

Developer A

Finished OCR integration.

Developer B

Working on patient extraction.

Developer C

Blocked by API authentication.

Decision

Developer A helps Developer C after the meeting.

Problem solved early.

12. Impediments

An impediment is anything slowing the team.

Examples

Technical

- API failure

- Database issue

- Build errors

Business

- Missing requirements

- Product Owner unavailable

Organizational

- Approval delays

- Infrastructure unavailable

External

- Vendor outage

- Regulatory changes

Daily Scrum helps identify these quickly.

13. Updating Sprint Backlog

During Daily Scrum Developers may decide to:

Add tasks

Remove tasks

Split work

Reassign work

Pair program

Adjust priorities within the Sprint Goal

The Sprint Backlog evolves continuously.

14. Healthcare Example

Hospital Management System

Sprint Goal

"Online Appointment Booking"

Day 5

Developer notices SMS gateway fails.

Daily Scrum discussion

Decision

One developer integrates a backup SMS provider.

Sprint continues successfully.

15. Pharmacovigilance Example

AI Drug Safety Platform

Sprint Goal

"Automatic ICSR classification."

Developer reports

MedDRA API latency.

Decision

Implement caching temporarily.

Problem resolved before affecting delivery.

16. AI Product Example

Medical AI Assistant

Sprint Goal

"Generate patient-friendly summaries."

Developer

Prompt accuracy is only 75%.

Data Scientist

Suggests prompt refinement.

ML Engineer

Provides additional training examples.

Entire team adapts the plan.

17. Remote Daily Scrum

Modern Scrum Teams are often distributed.

Tools commonly used

- Microsoft Teams

- Slack

- Google Meet

- Zoom

Best Practices

✔ Cameras encouraged

✔ Shared Sprint Board

✔ Screen sharing

✔ Stable internet

✔ Clear facilitator if needed

Remote teams should maintain the same discipline as co-located teams.

18. Common Daily Scrum Formats

Format 1

Traditional Three Questions

Format 2

Walk the Sprint Backlog

Discuss work item by work item.

Format 3

Walk the Kanban Board

Start from highest-priority work.

Format 4

Focus on Sprint Goal

Discuss only work affecting Sprint Goal.

Modern Scrum Teams increasingly prefer this approach.

19. Signs of an Effective Daily Scrum

✔ Finishes within 15 minutes

✔ Team members collaborate

✔ Problems identified early

✔ Sprint Backlog updated

✔ Clear plan for next 24 hours

✔ No unnecessary reporting

20. Signs of a Poor Daily Scrum

❌ Team reports to manager

❌ Meeting lasts 45 minutes

❌ Detailed technical debates

❌ No collaboration

❌ Same blockers every day

❌ Developers multitask during meeting

❌ Sprint Goal never mentioned

21. Common Mistakes

Mistake 1

Treating Daily Scrum as attendance.

Wrong.

Mistake 2

Problem solving during the meeting.

Long discussions belong after the meeting.

Mistake 3

Scrum Master dominates.

Daily Scrum belongs to Developers.

Mistake 4

Ignoring blockers.

Small problems become Sprint failures.

Mistake 5

Skipping Daily Scrum because "everyone is busy."

Communication breakdown follows.

22. Best Practices

✔ Keep meeting under 15 minutes.

✔ Focus on Sprint Goal.

✔ Encourage collaboration.

✔ Update Sprint Backlog.

✔ Remove impediments quickly.

✔ Continue technical discussions afterward.

✔ Rotate facilitation when appropriate.

✔ Use visual task boards.

23. Interview Questions

Q1. What is the purpose of the Daily Scrum?

Answer: To inspect progress toward the Sprint Goal and adapt the Sprint Backlog by planning the next day's work.

Q2. Who must attend the Daily Scrum?

Answer: Developers. The Scrum Master and Product Owner may attend if helpful, but the event belongs to the Developers.

Q3. How long should a Daily Scrum last?

Answer: It is timeboxed to a maximum of 15 minutes.

Q4. Are the three traditional questions mandatory?

Answer: No. The Scrum Guide does not prescribe them. Teams may use any format that helps inspect progress toward the Sprint Goal.

Q5. What should happen if a technical discussion requires 30 minutes?

Answer: Park the discussion and continue it immediately after the Daily Scrum with only the relevant people.

24. Real-World Case Study

AI Pharmacovigilance Platform

Sprint Goal

Deliver automatic extraction of adverse events from uploaded case reports.

Day 6

During the Daily Scrum:

Developer 1

OCR accuracy has fallen after a library update.

Developer 2

The validation service is waiting for OCR output.

Developer 3

Suggests rolling back to the previous OCR version while investigating.

Decision

- Roll back OCR library.

- Continue validation using the stable version.

- Create a follow-up task to evaluate the new library after the Sprint.

The Daily Scrum prevented multiple downstream delays and protected the Sprint Goal.

Mini Quiz

- What is the main purpose of the Daily Scrum?

- Who owns the Daily Scrum?

- What is the maximum duration of a Daily Scrum?

- Are the traditional three questions required by the Scrum Guide?

- What should happen to long technical discussions?

Practical Assignment

For your AI Pharmacovigilance Platform:

Part 1 – Conduct a Mock Daily Scrum

Assume your Sprint Goal is:

"Automatically classify Individual Case Safety Reports."

Write Daily Scrum updates for:

- Backend Developer

- Frontend Developer

- AI Engineer

- QA Engineer

Part 2 – Identify Blockers

List five possible impediments that could arise during this Sprint and explain how the team would address each one.

Part 3 – Sprint Adaptation

Suppose the OCR service becomes unavailable on Day 4.

Describe:

- How this issue would be discussed during the Daily Scrum.

- How the Sprint Backlog would be adjusted.

- How the team would protect the Sprint Goal.

Summary

The Daily Scrum is a short, focused planning event held every working day during the Sprint. Its purpose is to inspect progress toward the Sprint Goal, identify impediments, and adapt the Sprint Backlog as needed. Rather than serving as a status report for managers, it enables Developers to coordinate their work, improve collaboration, and respond quickly to change.

Key Takeaways

- The Daily Scrum is for the Developers.

- It is timeboxed to 15 minutes.

- The objective is to inspect progress toward the Sprint Goal and adapt the plan.

- The traditional three questions are optional, not required by the Scrum Guide.

- Technical problem-solving should occur after the Daily Scrum.

- Effective Daily Scrums improve transparency, collaboration, and the team's ability to deliver a valuable Increment.

Lesson 35c – Sprint Review (Complete Guide)

Learning Objectives

By the end of this lesson, you will understand:

- What is Sprint Review?

- Purpose of Sprint Review

- Scrum Guide definition

- Who attends Sprint Review?

- Sprint Review agenda

- Demonstrating the Increment

- Collecting stakeholder feedback

- Product Backlog adaptation

- Sprint Review vs Sprint Retrospective

- Healthcare examples

- Pharmacovigilance examples

- AI Product examples

- Common mistakes

- Best Practices

- Interview Questions

- Mini Quiz

- Practical Assignment

1. Introduction

Imagine you are building a hospital management system.

After working for two weeks, your team has completed an online appointment booking feature.

Now imagine two scenarios.

Scenario A

The team immediately starts working on the next feature without showing anyone the completed work.

After two months, hospital staff say:

"This isn't how we book appointments."

Months of work are wasted.

Scenario B

At the end of the Sprint, doctors, nurses, administrators, and hospital managers review the feature.

They immediately suggest improvements.

The team updates the Product Backlog before the next Sprint.

Result:

The product continuously moves closer to customer expectations.

This is the purpose of the Sprint Review.

2. Scrum Guide Definition

According to the Scrum Guide:

The purpose of the Sprint Review is to inspect the outcome of the Sprint and determine future adaptations.

Notice the keywords:

- Inspect

- Outcome

- Adaptation

The Sprint Review is not just a software demo.

It is a collaborative working session focused on maximizing product value.

3. Why is Sprint Review Important?

Without Sprint Review

- Customers see the product too late.

- Wrong assumptions continue.

- Expensive rework increases.

- Product loses market fit.

With Sprint Review

✔ Stakeholders inspect the Increment.

✔ Feedback is collected early.

✔ Product Backlog is updated.

✔ Business priorities are adjusted.

4. When Does Sprint Review Occur?

Sprint Review is conducted at the end of every Sprint, before the Sprint Retrospective.

Sprint Development

│

▼

Sprint Review

│

▼

Sprint Retrospective

│

▼

Next Sprint Planning

5. Timebox

Maximum duration

| Sprint Length | Sprint Review |
| --- | --- |
| 1 Week | 1 Hour |
| 2 Weeks | 2 Hours |
| 1 Month | Up to 4 Hours |

The meeting should remain focused on valuable discussion rather than lengthy presentations.

6. Who Attends?

Mandatory

Entire Scrum Team

- Product Owner

- Developers

- Scrum Master

Stakeholders

May include:

- Customers

- Business leaders

- Users

- Compliance officers

- Sales teams

- Marketing teams

- Operations

Unlike Daily Scrum, stakeholder participation is encouraged.

7. Objectives of Sprint Review

The Sprint Review answers questions such as:

- What was completed?

- Does the Increment meet customer needs?

- What feedback do stakeholders have?

- Has the market changed?

- Have priorities changed?

- What should be built next?

8. Sprint Review Agenda

A typical Sprint Review includes:

Step 1

Welcome and Sprint Goal

Step 2

Review completed Product Backlog Items

Step 3

Demonstrate the Increment

Step 4

Collect stakeholder feedback

Step 5

Discuss market and business changes

Step 6

Update Product Backlog

Step 7

Identify next priorities

9. Demonstrating the Increment

The Increment should be:

✔ Working

✔ Integrated

✔ Tested

✔ Meeting the Definition of Done

Never demonstrate:

- Mockups pretending to be complete

- Half-built features

- Untested code

The goal is to demonstrate real product value.

10. Example

Sprint Goal

"Allow patients to book appointments online."

Developers demonstrate:

✔ Search doctors

✔ Select time slot

✔ Book appointment

✔ Receive confirmation SMS

Hospital staff test the feature live.

Immediate feedback:

"Doctors should be searchable by specialty."

The Product Owner creates a new Product Backlog Item.

11. Feedback During Sprint Review

Stakeholder feedback may include:

Business

- New requirements

User Experience

- Simpler navigation

Compliance

- Additional audit logging

Performance

- Faster loading

Security

- Multi-factor authentication

Every suggestion is evaluated.

Not every suggestion is accepted immediately.

12. Product Backlog Adaptation

One major outcome of Sprint Review is adapting the Product Backlog.

Possible changes:

- Add new User Stories

- Reprioritize features

- Remove unnecessary work

- Split large stories

- Change Product Goal if needed

This keeps the product aligned with current business needs.

13. Sprint Review is NOT an Acceptance Meeting

Many companies misunderstand Sprint Review.

Wrong

Manager approves completed work.

Correct

Entire Scrum Team and stakeholders inspect the Increment and collaborate on future direction.

Acceptance decisions are governed by the Definition of Done and Product Owner responsibilities, not by a formal approval ceremony.

14. Healthcare Example

Hospital Management System

Sprint Goal

Patient Appointment Booking

During Sprint Review

Doctors request:

- Emergency appointments

- Color-coded schedules

- SMS reminders

Product Owner updates Product Backlog accordingly.

15. Pharmacovigilance Example

AI Drug Safety Platform

Sprint Goal

Automatic extraction of patient information.

Stakeholders:

- Safety Scientists

- Regulatory Affairs

- Pharmacovigilance Managers

Feedback:

- Extract reporter qualification.

- Improve confidence score display.

- Highlight uncertain predictions.

These become future Product Backlog Items.

16. AI Product Example

Medical AI Assistant

Sprint Goal

Generate patient-friendly summaries.

Doctors review generated summaries.

Feedback:

- Avoid complex terminology.

- Display confidence indicators.

- Cite medical references.

The Product Backlog is updated before the next Sprint.

17. Sprint Review vs Sprint Retrospective

| Sprint Review | Sprint Retrospective |
| --- | --- |
| Focuses on Product | Focuses on Team |
| Stakeholders attend | Only Scrum Team |
| Reviews Increment | Reviews process |
| Collects customer feedback | Identifies team improvements |
| Updates Product Backlog | Updates working practices |

Easy way to remember:

Sprint Review

"Are we building the right product?"

Sprint Retrospective

"Are we building the product the right way?"

18. Benefits of Sprint Review

✔ Early customer feedback

✔ Better Product Backlog

✔ Higher customer satisfaction

✔ Reduced project risk

✔ Increased transparency

✔ Stronger stakeholder engagement

✔ Better product-market fit

19. Common Mistakes

Mistake 1

Treating Sprint Review as a presentation.

It should be an interactive discussion.

Mistake 2

Demonstrating incomplete features.

Only demonstrate Done work.

Mistake 3

Ignoring stakeholder feedback.

Feedback is the primary purpose.

Mistake 4

Turning the meeting into a blame session.

Sprint Review is about improving the product, not judging individuals.

Mistake 5

Not updating the Product Backlog afterward.

Without adaptation, valuable feedback is lost.

20. Best Practices

✔ Demonstrate real working software.

✔ Invite relevant stakeholders.

✔ Encourage open discussion.

✔ Focus on business outcomes.

✔ Capture actionable feedback.

✔ Update the Product Backlog immediately.

✔ Compare outcomes with the Sprint Goal.

✔ Discuss changes in the market or customer needs.

21. Interview Questions

Q1. What is the purpose of the Sprint Review?

Answer: To inspect the Increment, gather stakeholder feedback, and adapt the Product Backlog to maximize future product value.

Q2. Who attends the Sprint Review?

Answer: The Scrum Team and relevant stakeholders such as customers, business representatives, and users.

Q3. Is Sprint Review only a product demonstration?

Answer: No. Demonstrating the Increment is one part of the meeting. The primary purpose is collaboration, inspection, and adaptation.

Q4. What is the main output of a Sprint Review?

Answer: Feedback that may lead to updates or reprioritization of the Product Backlog.

Q5. Can incomplete work be demonstrated?

Answer: Ideally, no. The Sprint Review focuses on the completed Increment that satisfies the Definition of Done.

22. Real-World Case Study

AI Pharmacovigilance Platform

Sprint Goal

Enable automatic extraction of patient demographics from adverse event reports.

Demonstration

The team demonstrates:

- PDF upload

- OCR extraction

- Patient name detection

- Age extraction

- Gender extraction

Stakeholder Feedback

Regulatory Affairs:

"The system should also capture the reporter's country."

Safety Scientists:

"Display confidence scores for extracted entities."

Medical Review Team:

"Flag missing mandatory fields."

Product Backlog Updates

New Product Backlog Items are created:

- Reporter country extraction

- Confidence score visualization

- Mandatory field validation

The Sprint Review ensures the product evolves based on real user needs rather than assumptions.

Mini Quiz

- What is the primary purpose of the Sprint Review?

- Who typically attends the Sprint Review?

- What is the main output of the Sprint Review?

- Should incomplete work be demonstrated?

- What is the difference between Sprint Review and Sprint Retrospective?

Practical Assignment

For your AI Pharmacovigilance Platform:

Part 1 – Prepare a Sprint Review

Your Sprint delivered:

- PDF Upload

- OCR

- Patient Information Extraction

- MedDRA Coding

Create a 10-minute Sprint Review agenda.

Part 2 – Stakeholder Feedback

Assume feedback from:

- Pharmacovigilance Manager

- Medical Reviewer

- Regulatory Affairs Lead

List five new Product Backlog Items that arise from their feedback.

Part 3 – Product Backlog Adaptation

Prioritize the new backlog items using:

- Business Value

- Regulatory Risk

- Customer Impact

Explain your prioritization decisions.

Summary

The Sprint Review is the Scrum event where the Scrum Team and stakeholders inspect the completed Increment, discuss progress toward the Product Goal, and identify opportunities for improvement. It is a collaborative working session—not merely a demonstration—that ensures the product evolves based on feedback, changing business priorities, and market needs.

Key Takeaways

- The Sprint Review occurs at the end of every Sprint.

- It focuses on inspecting the Increment and adapting the Product Backlog.

- Relevant stakeholders actively participate.

- The outcome is valuable feedback and an updated Product Backlog.

- Sprint Review improves transparency, customer satisfaction, and product-market alignment.

- It differs from the Sprint Retrospective, which focuses on improving the team's way of working rather than the product itself.

Lesson 35d – Sprint Retrospective (Complete Guide)

Learning Objectives

By the end of this lesson, you will understand:

- What is Sprint Retrospective?

- Purpose of Sprint Retrospective

- Scrum Guide definition

- Why continuous improvement matters

- Who attends Sprint Retrospective?

- Sprint Retrospective agenda

- Root Cause Analysis

- 5 Whys Technique

- Fishbone (Ishikawa) Diagram

- Action Items

- Improvement Backlog

- Sprint Review vs Sprint Retrospective

- Healthcare examples

- Pharmacovigilance examples

- AI Product examples

- Common mistakes

- Best Practices

- Interview Questions

- Mini Quiz

- Practical Assignment

1. Introduction

Imagine two cricket teams.

Team A

Loses a match.

Immediately starts preparing for the next match.

No discussion.

No learning.

No improvement.

The same mistakes continue.

Team B

After every match they discuss:

- What worked?

- What failed?

- What should improve?

- What should stop?

- What should continue?

Within a few months, they become a much stronger team.

This is exactly why Scrum includes the Sprint Retrospective.

The Sprint Review improves the product.

The Sprint Retrospective improves the team.

2. Scrum Guide Definition

According to the Scrum Guide:

The purpose of the Sprint Retrospective is to plan ways to increase quality and effectiveness.

Notice the focus:

- Quality

- Effectiveness

- Continuous Improvement

The Retrospective is not about blaming people.

It is about improving the system.

3. Why is Sprint Retrospective Important?

Without Retrospectives

Problems repeat.

Communication breaks.

Velocity decreases.

Technical debt grows.

Team morale drops.

With Retrospectives

✔ Continuous improvement

✔ Better collaboration

✔ Higher quality

✔ Faster delivery

✔ Better team morale

4. When Does Sprint Retrospective Happen?

Sprint Retrospective is the last Scrum Event in every Sprint.

Sprint Planning

│

Daily Scrum

│

Development

│

Sprint Review

│

Sprint Retrospective

│

Next Sprint Planning

Every Sprint ends with learning.

5. Timebox

Maximum duration

| Sprint Length | Retrospective |
| --- | --- |
| 1 Week | 45 Minutes |
| 2 Weeks | 1.5 Hours |
| 1 Month | Up to 3 Hours |

6. Who Attends?

Only the Scrum Team.

- Product Owner

- Scrum Master

- Developers

Stakeholders do not attend.

Why?

The team must feel psychologically safe to discuss mistakes openly.

7. Purpose of Sprint Retrospective

The Scrum Team reflects on:

- People

- Process

- Tools

- Communication

- Quality

- Collaboration

- Sprint Goal achievement

Then identifies improvements for the next Sprint.

8. Typical Sprint Retrospective Agenda

Step 1

Welcome

Step 2

Review Sprint Goal

Step 3

Discuss

What went well?

Step 4

Discuss

What didn't go well?

Step 5

Identify root causes.

Step 6

Create improvement actions.

Step 7

Assign ownership.

Step 8

Close meeting.

9. The Three Questions

Many teams structure Retrospectives using three simple questions.

What went well?

Examples

- Good collaboration

- Fast testing

- Clear requirements

What didn't go well?

Examples

- Build failures

- API delays

- Poor estimation

What should we improve?

Examples

- Better documentation

- Earlier testing

- Pair programming

10. Root Cause Analysis

Symptoms are not problems.

Example

Bug discovered.

Symptom.

Real question

Why?

Root Cause Analysis identifies the actual problem.

11. 5 Whys Technique

Problem

Sprint delayed.

Why?

Testing finished late.

Why?

Developers completed coding late.

Why?

Requirements changed.

Why?

Acceptance Criteria unclear.

Why?

Product Backlog refinement was insufficient.

Root Cause

Poor backlog refinement.

12. Fishbone (Ishikawa) Diagram

Fishbone analysis groups causes.

Problem

│

------------------------------------

│        │        │        │

People  Process  Tools  Technology

Example

Problem

Low AI accuracy.

Possible causes

People

- Lack of ML expertise

Process

- Poor data validation

Tools

- Wrong framework

Technology

- Outdated model

This helps identify multiple contributing factors instead of focusing on a single issue.

13. Action Items

Every Retrospective should produce measurable improvements.

Bad Action

"Improve communication."

Good Action

"Start code reviews within 24 hours of opening a Pull Request."

Another example

Bad

"Reduce bugs."

Good

"Increase automated unit test coverage from 65% to 80%."

Action items should be SMART:

- Specific

- Measurable

- Achievable

- Relevant

- Time-bound

14. Improvement Backlog

Many mature Scrum Teams maintain an Improvement Backlog.

Example

| Improvement | Priority |
| --- | --- |
| Automate Testing | High |
| Improve Documentation | Medium |
| Faster Code Reviews | High |
| CI/CD Pipeline | High |
| Better Sprint Refinement | Medium |

Improvement work is treated like product work.

15. Sprint Review vs Sprint Retrospective

| Sprint Review | Sprint Retrospective |
| --- | --- |
| Improve Product | Improve Team |
| Stakeholders attend | Only Scrum Team |
| Discuss customer value | Discuss working process |
| Update Product Backlog | Update Improvement Actions |
| External feedback | Internal reflection |

Easy Memory Trick

Sprint Review

Building the Right Product

Sprint Retrospective

Building the Product Right

16. Healthcare Example

Hospital Appointment System

Sprint Goal achieved.

Retrospective discussion

What went well

- Doctors gave quick feedback.

What didn't

- Testing delayed.

Improvement

- QA joins development earlier.

Next Sprint quality improves.

17. Pharmacovigilance Example

AI Drug Safety Platform

Sprint Goal

Automatic Adverse Event Detection.

Problem

False positives increased.

Retrospective

5 Whys reveals

Training data contains duplicate reports.

Improvement

Automated dataset validation before model training.

Next Sprint

AI quality improves significantly.

18. AI Product Example

Medical AI Assistant

Problem

Hallucinations increased.

Retrospective

Root Cause

Prompt templates inconsistent.

Improvement

Create standardized prompt library.

Result

More reliable AI responses.

19. Psychological Safety

One of the most important aspects of a successful Retrospective is psychological safety.

Team members should feel comfortable saying:

- "I made a mistake."

- "I need help."

- "Our process isn't working."

Without fear of blame or punishment.

The goal is learning—not assigning fault.

20. Common Retrospective Formats

Format 1

Start

Stop

Continue

Format 2

Mad

Sad

Glad

Format 3

Liked

Learned

Lacked

Longed For

Format 4

4Ls

- Liked

- Learned

- Lacked

- Longed For

Different formats keep discussions engaging while encouraging honest feedback.

21. Common Mistakes

Mistake 1

Blaming individuals.

Retrospectives focus on improving systems and processes.

Mistake 2

No action items.

Discussion without action changes nothing.

Mistake 3

Repeating the same problems every Sprint.

Improvement actions should be tracked.

Mistake 4

Managers dominating discussions.

The Scrum Team should speak freely.

Mistake 5

Skipping Retrospectives when the Sprint was successful.

Even successful teams can improve.

22. Best Practices

✔ Create a psychologically safe environment.

✔ Focus on facts instead of opinions.

✔ Celebrate successes.

✔ Identify one or two high-impact improvements.

✔ Assign ownership for every action.

✔ Review previous Retrospective action items.

✔ Track improvement over time.

✔ Encourage every team member to participate.

23. Interview Questions

Q1. What is the purpose of the Sprint Retrospective?

Answer: To inspect how the last Sprint went and identify practical improvements that increase quality and effectiveness in future Sprints.

Q2. Who attends the Sprint Retrospective?

Answer: Only the Scrum Team—Product Owner, Scrum Master, and Developers.

Q3. What is the main output of a Sprint Retrospective?

Answer: Actionable improvement items that the team commits to implementing in future Sprints.

Q4. What is the difference between Sprint Review and Sprint Retrospective?

Answer: Sprint Review focuses on the product and stakeholder feedback, while Sprint Retrospective focuses on improving the team's processes, collaboration, and effectiveness.

Q5. Why is psychological safety important?

Answer: It encourages honest discussion, learning from mistakes, and continuous improvement without fear of blame.

24. Real-World Case Study

AI Pharmacovigilance Platform

Sprint Goal

Automatically classify Individual Case Safety Reports (ICSRs).

Sprint Outcome

The feature was delivered successfully.

However:

- Velocity dropped by 20%.

- Developers worked overtime.

- QA found many late defects.

Retrospective Discussion

What Went Well

- OCR accuracy improved.

- Regulatory requirements were met.

- Customer satisfaction was high.

What Didn't Go Well

- Stories were too large.

- Testing started too late.

- AI model retraining took longer than expected.

Root Cause Analysis

The team identified that Product Backlog refinement was insufficient, leading to oversized User Stories.

Improvement Actions

- Split large User Stories during refinement.

- Include QA in design discussions.

- Automate AI model validation.

- Schedule model retraining overnight.

These actions become part of the team's Improvement Backlog for the next Sprint.

Mini Quiz

- What is the purpose of the Sprint Retrospective?

- Who attends the Sprint Retrospective?

- What is the difference between a Sprint Review and a Sprint Retrospective?

- What is the purpose of the 5 Whys technique?

- Why should every Retrospective end with action items?

Practical Assignment

For your AI Pharmacovigilance Platform:

Part 1 – Conduct a Sprint Retrospective

Assume your Sprint delivered:

- OCR

- AI Extraction

- MedDRA Coding

Document:

- Five things that went well.

- Five things that didn't go well.

- Five improvement ideas.

Part 2 – Root Cause Analysis

Choose one major Sprint problem (e.g., delayed AI model training) and perform a 5 Whys Analysis.

Part 3 – Fishbone Exercise

Create a Fishbone Diagram for the problem:

"Low AI extraction accuracy."

Categorize causes into:

- People

- Process

- Technology

- Data

- Tools

- Environment

Part 4 – Improvement Plan

Create three SMART improvement actions that will be implemented in the next Sprint and explain how you will measure their success.

Summary

The Sprint Retrospective is the final Scrum event of every Sprint and serves as the team's structured opportunity to inspect its way of working. By reflecting on successes, challenges, and root causes, the Scrum Team identifies concrete improvements that increase quality, collaboration, and effectiveness. Continuous improvement—not perfection—is the essence of a successful Retrospective.

Key Takeaways

- The Sprint Retrospective focuses on improving the team, not evaluating individuals.

- It is attended only by the Scrum Team.

- The event should produce specific, measurable improvement actions.

- Techniques such as 5 Whys and Fishbone Analysis help uncover root causes.

- Psychological safety is essential for honest and productive discussions.

- Teams that consistently act on Retrospective insights become more predictable, efficient, and capable of delivering higher-quality products over time.

Lesson 35e – Backlog Refinement (Complete Guide)

Learning Objectives

By the end of this lesson, you will understand:

- What is Backlog Refinement?

- Why Backlog Refinement is important

- Scrum Guide definition

- Product Backlog Refinement process

- Responsibilities of the Product Owner and Developers

- INVEST Model

- User Story Splitting Techniques

- Acceptance Criteria

- Estimation Preparation

- Definition of Ready connection

- Common Refinement Techniques

- Healthcare examples

- Pharmacovigilance examples

- AI Product examples

- Common mistakes

- Best Practices

- Interview Questions

- Mini Quiz

- Practical Assignment

1. Introduction

Imagine a chef preparing a wedding dinner for 500 guests.

One day before the event, he still hasn't:

- Selected ingredients

- Finalized recipes

- Ordered vegetables

- Checked equipment

- Assigned responsibilities

Can the cooking start smoothly?

Probably not.

Now imagine another chef.

Weeks before the event, he continuously:

- Updates recipes

- Orders ingredients

- Removes unavailable dishes

- Estimates cooking time

- Discusses risks

Cooking begins without confusion.

Backlog Refinement works exactly the same way.

It continuously prepares work before Sprint Planning.

2. What is Backlog Refinement?

Backlog Refinement is the ongoing activity of reviewing, updating, clarifying, estimating, and prioritizing Product Backlog Items so they are ready for future Sprints.

Simple Meaning

Backlog Refinement is preparing tomorrow's work today.

Instead of waiting until Sprint Planning, the team continuously improves the Product Backlog.

3. Scrum Guide Definition

The Scrum Guide states:

Product Backlog refinement is the act of breaking down and further defining Product Backlog Items into smaller, more precise items.

Notice the important words:

- Breaking down

- Defining

- Clarifying

- Ongoing activity

It is not listed as an official Scrum Event.

It is a continuous activity.

4. Why is Backlog Refinement Important?

Without refinement:

Sprint Planning becomes chaotic.

Example

Product Owner

"Build AI."

Developers ask:

- Which AI?

- Which model?

- Which dataset?

- Which users?

- What is success?

Nobody knows.

Sprint Planning lasts six hours.

Sprint starts late.

With Backlog Refinement

Everything is already clear.

Sprint Planning becomes fast and productive.

5. Objectives of Backlog Refinement

During refinement, the team:

✔ Clarifies requirements

✔ Splits large stories

✔ Removes obsolete items

✔ Updates priorities

✔ Adds acceptance criteria

✔ Estimates stories

✔ Identifies dependencies

✔ Improves understanding

6. Who Participates?

Product Owner

Responsible for:

- Prioritization

- Business value

- Clarifying requirements

Developers

Responsible for:

- Technical discussion

- Complexity

- Estimation

- Risks

Scrum Master

Facilitates discussion.

Ensures collaboration.

Stakeholders

May participate when business clarification is needed.

7. When Should Refinement Happen?

Unlike Sprint Planning,

Backlog Refinement has no fixed schedule.

Most teams conduct:

- One session every week

- One or two sessions per Sprint

Many teams spend approximately 5–10% of Sprint capacity on refinement.

8. Backlog Refinement Workflow

Product Backlog

│

▼

Review Stories

│

▼

Clarify Requirements

│

▼

Split Large Stories

│

▼

Add Acceptance Criteria

│

▼

Estimate Stories

│

▼

Prioritize

│

▼

Ready for Sprint Planning

9. Example

Original Story

Build AI Case Processing.

Too large.

After Refinement

Story 1

Upload PDF

Story 2

OCR Processing

Story 3

Patient Extraction

Story 4

Adverse Event Detection

Story 5

MedDRA Coding

Story 6

Case Validation

Sprint Planning becomes much easier.

10. INVEST Model

Good User Stories usually follow the INVEST principle.

| Letter | Meaning |
| --- | --- |
| I | Independent |
| N | Negotiable |
| V | Valuable |
| E | Estimable |
| S | Small |
| T | Testable |

Independent

Stories should not depend heavily on each other.

Bad

"Generate report after dashboard."

Good

Separate stories.

Negotiable

Stories should allow discussion.

Requirements are not contracts.

Valuable

Every story should deliver business value.

Example

"Export patient report"

adds value.

Changing button color usually does not.

Estimable

Developers should be able to estimate effort.

If nobody understands the story,

it isn't ready.

Small

A story should fit inside one Sprint.

Large stories become Epics.

Testable

Acceptance Criteria should make testing possible.

11. Acceptance Criteria

Example

Story

"As a doctor, I want patient search."

Acceptance Criteria

✔ Search by Patient ID

✔ Search by Name

✔ Search within 2 seconds

✔ No duplicate results

Now developers understand exactly what success means.

12. Story Splitting Techniques

One of the most important Product Manager skills.

Suppose

Epic

"AI Drug Safety Platform"

Possible split

- Login

- Upload Case

- OCR

- NLP Extraction

- MedDRA Coding

- Duplicate Detection

- Dashboard

- Reports

Smaller stories improve estimation and delivery.

13. Estimation Preparation

Stories should be estimated before Sprint Planning.

Methods include

- Story Points

- Planning Poker

- T-Shirt Sizes

- Relative Estimation

Detailed estimation techniques are covered in Lesson 42.

14. Refinement and Definition of Ready

Backlog Refinement prepares stories for the Definition of Ready.

Example

During Refinement

✔ Requirements clarified

✔ Acceptance Criteria added

✔ Dependencies identified

✔ Estimate completed

The story now satisfies the Definition of Ready.

Sprint Planning becomes much smoother.

15. Healthcare Example

Hospital Management System

Epic

Appointment Management

Refinement creates

- Search Doctor

- Calendar View

- Book Appointment

- Cancel Appointment

- SMS Notification

- Email Reminder

Each story is small enough for estimation and Sprint Planning.

16. Pharmacovigilance Example

AI Drug Safety Platform

Epic

Automatic Case Processing

Refined Stories

- Upload ICSR

- OCR

- Patient Extraction

- Drug Identification

- MedDRA Coding

- Seriousness Detection

- Medical Review Screen

Each story has clear acceptance criteria.

17. AI Product Example

Medical AI Assistant

Epic

Patient Consultation

Refined Stories

- Login

- Voice Input

- LLM Integration

- Medical Knowledge Retrieval

- Drug Interaction Detection

- Summary Generation

- Feedback Collection

Large features become manageable work items.

18. Benefits of Backlog Refinement

✔ Better Sprint Planning

✔ Better estimates

✔ Fewer requirement changes

✔ Smaller stories

✔ Faster delivery

✔ Better collaboration

✔ Reduced project risk

✔ Improved Product Backlog quality

19. Common Mistakes

Mistake 1

No refinement sessions.

Sprint Planning becomes chaotic.

Mistake 2

Stories too large.

Impossible to estimate accurately.

Mistake 3

No acceptance criteria.

Developers interpret requirements differently.

Mistake 4

Product Owner works alone.

Refinement should be collaborative.

Mistake 5

Estimating without understanding requirements.

Poor estimates follow.

Mistake 6

Keeping obsolete stories.

The Product Backlog should remain current.

20. Best Practices

✔ Refine continuously.

✔ Keep Product Backlog ordered.

✔ Split Epics early.

✔ Write clear User Stories.

✔ Add measurable acceptance criteria.

✔ Estimate collaboratively.

✔ Remove obsolete work.

✔ Ensure stories meet the Definition of Ready.

21. Interview Questions

Q1. What is Product Backlog Refinement?

Answer: An ongoing activity where the Scrum Team clarifies, estimates, splits, prioritizes, and prepares Product Backlog Items for future Sprints.

Q2. Is Backlog Refinement an official Scrum Event?

Answer: No. It is an ongoing activity recommended by the Scrum Guide, but it is not one of the formal Scrum events.

Q3. Who participates in Backlog Refinement?

Answer: The Product Owner, Developers, and Scrum Master. Stakeholders may join when additional business clarification is needed.

Q4. Why is the INVEST model important?

Answer: It helps ensure User Stories are well-formed, estimable, valuable, and suitable for inclusion in a Sprint.

Q5. Why should Epics be split?

Answer: Smaller stories are easier to understand, estimate, implement, test, and deliver within a single Sprint.

22. Real-World Case Study

AI Pharmacovigilance Platform

The Product Owner initially creates the following backlog item:

"Build an AI system to automate pharmacovigilance."

The Developers explain that the story is too large to estimate.

During Backlog Refinement, the team decomposes it into:

| Refined Story | Story Points |
| --- | --- |
| Upload PDF | 3 |
| OCR Extraction | 5 |
| Patient Identification | 5 |
| Drug Extraction | 8 |
| Adverse Event Detection | 8 |
| MedDRA Coding | 13 |
| Quality Dashboard | 8 |

The team also:

- Defines acceptance criteria.

- Identifies dependencies on the OCR service and MedDRA terminology.

- Estimates each story using Story Points.

- Confirms that the highest-priority stories satisfy the Definition of Ready.

As a result, Sprint Planning is completed efficiently, and the team starts development with minimal ambiguity.

Mini Quiz

- What is the purpose of Backlog Refinement?

- Is Backlog Refinement a formal Scrum event?

- What does the INVEST model stand for?

- Why are acceptance criteria important?

- Why should large User Stories be split before Sprint Planning?

Practical Assignment

For your AI Pharmacovigilance Platform:

Part 1 – Epic Decomposition

Take the Epic:

"Automate Individual Case Safety Report (ICSR) Processing."

Break it into 10–12 User Stories.

Part 2 – Apply INVEST

Evaluate each User Story against the INVEST criteria.

Identify any stories that violate the model and explain how you would improve them.

Part 3 – Write Acceptance Criteria

Choose three User Stories and write 4–5 measurable acceptance criteria for each.

Part 4 – Definition of Ready Assessment

Using the Definition of Ready created in Lesson 35, determine whether each User Story is ready for Sprint Planning. If not, list the missing information.

Summary

Backlog Refinement is a continuous collaborative activity that keeps the Product Backlog healthy, prioritized, and actionable. By clarifying requirements, splitting large Epics, defining acceptance criteria, estimating effort, and applying frameworks like INVEST, Scrum Teams reduce uncertainty and improve Sprint Planning. Effective refinement ensures that high-priority Product Backlog Items are ready to enter a Sprint and deliver business value efficiently.

Key Takeaways

- Backlog Refinement is not a formal Scrum event, but it is an essential Scrum practice.

- Its purpose is to prepare Product Backlog Items for future Sprints.

- Effective refinement includes clarification, estimation, prioritization, and story splitting.

- The INVEST model is a widely used guideline for writing high-quality User Stories.

- Refinement directly supports the Definition of Ready and leads to more predictable Sprint Planning.

- Teams that refine their backlog continuously spend less time resolving ambiguity during Sprint Planning and more time delivering value.

Lesson 36: Scrum Values and Mindset – Commitment, Focus, Openness, Respect, Courage, and Building High-Performing Agile Teams

Learning Objectives

By the end of this lesson, you will understand:

- Why Scrum Values exist.

- Five Scrum Values.

- How values influence behavior.

- Agile mindset.

- Psychological safety.

- High-performing teams.

- Healthcare examples.

- AI Product examples.

- Interview-level answers.

1. Why Does Scrum Need Values?

Simple explanation

Scrum provides:

- Roles.

- Events.

- Artifacts.

But these alone do not create successful teams.

Example:

A team can do:

✅ Daily Scrum
✅ Sprint Planning
✅ Sprint Review

but still fail because:

- People hide problems.

- Nobody challenges decisions.

- Teams blame each other.

Values create the behavior needed for Scrum to succeed.

Real-life analogy

A hospital has:

- Doctors.

- Nurses.

- Equipment.

- Procedures.

But without values like:

- Responsibility.

- Respect.

- Communication.

Patient care suffers.

Scrum works the same way.

2. The Five Scrum Values

Scrum has five values:

- Commitment

- Focus

- Openness

- Respect

- Courage

Diagram:

Scrum Values

|

---------------------------------

Commitment   Focus   Openness

Respect      Courage

---------------------------------

3. Value 1: Commitment

Meaning

The team commits to achieving goals and supporting each other.

Important:

Commitment does NOT mean:

"I promise to complete every task."

It means:

"We commit to achieving the Sprint Goal."

Example

Sprint Goal:

"Automate adverse event extraction."

Developer faces technical problem.

Commitment means:

Team works together to solve it.

Healthcare Example

AI Pharmacovigilance team:

Problem:

Model accuracy is low.

Bad behavior:

"AI engineer failed."

Good behavior:

"Team will improve the model together."

Product Owner Example

PO commits to:

- Clear priorities.

- Product success.

4. Value 2: Focus

Meaning

The team focuses on the most important work.

Without focus:

Everything becomes priority.

Example:

Stakeholders request:

- Dashboard.

- Mobile app.

- AI chatbot.

- Analytics.

- Reports.

Focused PO decides:

First:

"Reduce manual case processing."

AI Example

Instead of building 20 AI features:

Focus on:

One valuable problem.

Focus means:

- Clear Sprint Goal.

- Limited Work in Progress.

- Avoid distractions.

5. Value 3: Openness

Meaning

The team is open about:

- Progress.

- Problems.

- Risks.

- Learning.

Example:

Developer says:

"The AI model accuracy is only 65%."

Bad culture:

"Who made this mistake?"

Agile culture:

"How can we improve?"

Healthcare Example

A safety team discovers:

AI incorrectly identifies adverse events.

Openness allows:

Early correction.

6. Value 4: Respect

Meaning

Team members respect:

- Skills.

- Opinions.

- Experience.

Respect means:

A developer respects medical expertise.

A pharmacist respects technical expertise.

Example

Pharmacovigilance expert:

"This classification is medically incorrect."

Developer:

"Let's understand the requirement."

Not:

"Your opinion doesn't matter."

7. Value 5: Courage

Meaning

Having courage to:

- Speak difficult truths.

- Challenge assumptions.

- Make decisions.

Example:

Team realizes:

"The current AI approach will not work."

Courage means:

Admitting early and changing direction.

Healthcare Example

AI system risk:

Incorrect medical recommendation.

Team must have courage to stop deployment.

8. Scrum Values in Daily Work

Example:

Sprint Planning:

Commitment

Team commits to Sprint Goal.

Focus

Ignore unrelated work.

Openness

Discuss risks.

Respect

Listen to each other.

Courage

Raise concerns.

9. Agile Mindset

Now connect Scrum with Agile thinking.

Traditional Mindset

Thinking:

"We need complete requirements before starting."

Agile Mindset

Thinking:

"We learn by building and getting feedback."

Traditional:

Change is a problem.

Agile:

Change is learning.

Traditional:

Success = completing tasks.

Agile:

Success = delivering customer value.

10. Fixed Mindset vs Agile Mindset

| Fixed Mindset | Agile Mindset |
| --- | --- |
| Avoid mistakes | Learn from mistakes |
| Follow plan blindly | Adapt based on feedback |
| Individual success | Team success |
| Hide problems | Expose problems |
| Deliver features | Deliver value |

11. Psychological Safety

Very important for Agile teams.

Definition:

A team environment where people feel safe to:

- Share ideas.

- Report problems.

- Admit mistakes.

Example:

Developer says:

"I introduced a bug."

Healthy team:

"Let's fix it and improve process."

Unhealthy team:

"Who caused this?"

12. High-Performing Scrum Teams

Characteristics:

1. Shared Goal

Everyone understands purpose.

2. Trust

People depend on each other.

3. Collaboration

Teams solve problems together.

4. Continuous Improvement

Every Sprint becomes better.

5. Ownership

People take responsibility.

13. Scrum Values in Product Management

A Product Owner uses values:

Commitment

Commit to customer outcomes.

Focus

Prioritize valuable features.

Openness

Accept feedback.

Respect

Trust team expertise.

Courage

Say no to low-value requests.

14. Scrum Values in AI Products

AI development has uncertainty.

Values become even more important.

Example:

AI Medical Assistant.

Problem:

Model produces incorrect answers.

Commitment:

Improve safety.

Focus:

Fix critical issues.

Openness:

Share model limitations.

Respect:

Listen to medical experts.

Courage:

Delay release if unsafe.

15. Pharmacovigilance Example

AI Drug Safety Platform.

Situation:

AI extracts wrong adverse events.

Wrong approach:

Hide errors until release.

Agile approach:

Team discusses openly.

Actions:

- Improve training data.

- Add validation.

- Increase human review.

Common Mistakes

Mistake 1:

Values are just words on a wall.

Wrong.

They guide decisions.

Mistake 2:

Commitment means forcing overtime.

Wrong.

Commitment means shared responsibility.

Mistake 3:

Openness means blaming people.

Wrong.

Openness requires psychological safety.

Mistake 4:

Courage means taking unnecessary risks.

Wrong.

Courage means making responsible decisions.

Best Practices

Build Scrum culture by:

✅ Encourage honest communication
✅ Celebrate learning
✅ Focus on outcomes
✅ Respect expertise
✅ Improve continuously

Interview Questions

Q1. What are Scrum Values?

Answer:

Commitment, Focus, Openness, Respect, and Courage.

Q2. Why are Scrum Values important?

Answer:

They guide team behavior and enable effective use of Scrum practices.

Q3. Difference between Agile mindset and traditional mindset?

Answer:

Agile focuses on adaptation, collaboration, and customer value, while traditional approaches focus on fixed plans and predefined requirements.

Q4. What is psychological safety?

Answer:

A culture where team members feel safe sharing ideas, concerns, and mistakes without fear.

Mini Quiz

Answer:

- What are the five Scrum Values?

- Does commitment mean completing every task?

- Why is openness important?

- What is psychological safety?

- How does courage help AI product teams?

Practical Assignment

You are the Scrum Master of:

AI Pharmacovigilance Platform

Create examples:

Commitment:

What will the team commit to?

Focus:

What should the team avoid?

Openness:

What problems should be openly discussed?

Respect:

How will technical and medical teams collaborate?

Courage:

What difficult decision may the team need to take?

Summary

Scrum is not successful because of:

- Meetings.

- Jira boards.

- Sprint duration.

It succeeds because of:

Values + Mindset + Collaboration

Key Takeaways

✅ Commitment creates ownership
✅ Focus creates value delivery
✅ Openness creates transparency
✅ Respect creates collaboration
✅ Courage enables improvement

Lesson 36a – Sprint (Complete Guide)

Learning Objectives

By the end of this lesson, you will understand:

- What is a Sprint?

- Why Scrum uses Sprints

- Sprint characteristics

- Sprint lifecycle

- Sprint timebox

- Sprint Goal

- Why Sprint duration should remain consistent

- Can a Sprint be cancelled?

- Who can cancel a Sprint?

- Sprint vs Waterfall phase

- Healthcare examples

- Pharmacovigilance examples

- AI Product examples

- Common mistakes

- Best Practices

- Interview Questions

- Mini Quiz

- Practical Assignment

1. Introduction

The Sprint is the heartbeat of Scrum.

Everything in Scrum revolves around the Sprint.

Without a Sprint, there is no Scrum.

Think of a Sprint as a mini-project that delivers a valuable improvement to the product.

Instead of waiting months to deliver software, Scrum delivers value every few weeks.

2. Scrum Guide Definition

According to the Scrum Guide:

A Sprint is a fixed-length event of one month or less during which a usable and valuable Increment is created.

Key words:

- Fixed-length

- One month or less

- Valuable

- Increment

Every Sprint must produce value.

3. Why Does Scrum Use Sprints?

Imagine building a Hospital Management System using the traditional approach.

Planning → Design → Development → Testing → Deployment

Time required:

12 months

Problem:

If users dislike the product after 12 months, enormous effort has already been spent.

Scrum reduces this risk.

Instead:

Sprint 1 → Registration Module

Sprint 2 → Appointment Module

Sprint 3 → Billing

Sprint 4 → Reports

Users provide feedback after every Sprint.

The product continuously improves.

4. Sprint Characteristics

Every Sprint has these characteristics:

✔ Fixed duration

✔ Clear Sprint Goal

✔ Sprint Planning

✔ Daily Scrum

✔ Development

✔ Sprint Review

✔ Sprint Retrospective

✔ Working Increment

A Sprint is not just coding—it includes all Scrum events needed to inspect and adapt.

5. Sprint Lifecycle

Product Backlog

│

▼

Sprint Planning

│

▼

Sprint Starts

│

▼

Daily Scrum (Every Day)

│

▼

Development & Testing

│

▼

Sprint Review

│

▼

Sprint Retrospective

│

▼

Next Sprint

This cycle repeats continuously.

6. Sprint Duration

According to the Scrum Guide:

A Sprint lasts one month or less.

Most organizations choose:

| Sprint Length | Common Usage |
| --- | --- |
| 1 Week | Fast-moving startups |
| 2 Weeks | Most common |
| 3 Weeks | Medium-sized teams |
| 4 Weeks | Large enterprise products |

There is no universally "best" duration.

The right duration depends on:

- Product complexity

- Team size

- Feedback frequency

- Regulatory requirements

7. Why Keep Sprint Length Consistent?

Suppose:

Sprint 1 = 2 weeks

Sprint 2 = 5 days

Sprint 3 = 1 month

Sprint 4 = 10 days

Problems:

- Velocity becomes unreliable.

- Forecasting becomes difficult.

- Stakeholders lose predictability.

Keeping Sprint length constant improves planning and measurement.

8. What Happens During a Sprint?

A Sprint is not just a development phase.

During a Sprint:

- Developers build features.

- Testers verify functionality.

- Designers refine interfaces.

- Product Owner clarifies requirements.

- Scrum Master removes impediments.

- Stakeholders may answer questions when needed.

At the end:

A usable Increment is demonstrated.

9. Sprint Goal

Every Sprint has one primary objective.

Example:

Hospital System

Sprint Goal:

"Enable patients to book appointments online."

Everything selected for the Sprint should support this goal.

If a task doesn't contribute to the Sprint Goal, it should usually not be included.

10. Sprint Example

AI Pharmacovigilance Product

Sprint Duration:

2 Weeks

Sprint Goal:

"Automatically extract patient demographics from uploaded safety reports."

Sprint Backlog:

- PDF Upload

- OCR Integration

- Patient Name Extraction

- Age Detection

- Gender Detection

- Database Storage

- Unit Tests

Increment:

A working feature that extracts patient demographics automatically.

11. Sprint Timeboxing

Timeboxing means every Scrum event has a maximum duration.

Example for a 2-week Sprint:

| Event | Maximum Time |
| --- | --- |
| Sprint Planning | 4 Hours |
| Daily Scrum | 15 Minutes |
| Sprint Review | 2 Hours |
| Sprint Retrospective | 1.5 Hours |

Timeboxing prevents endless meetings and encourages focus.

12. Can Requirements Change During a Sprint?

Yes—but carefully.

The Sprint Goal should remain stable.

However:

- Developers may adjust implementation details.

- Sprint Backlog may evolve.

- Technical tasks may change.

What should not happen?

The Product Owner should not continuously add unrelated work that jeopardizes the Sprint Goal.

13. Can a Sprint Be Cancelled?

Yes.

But only in rare situations.

According to the Scrum Guide:

Only the Product Owner has the authority to cancel a Sprint.

Typically when:

- The Sprint Goal becomes obsolete.

- Business priorities change dramatically.

- Regulations change.

- A major market event occurs.

14. Example of Sprint Cancellation

Imagine your AI healthcare product is building:

"COVID Vaccination Certificate Module."

Mid-Sprint:

Government withdraws the regulation.

The Sprint Goal is no longer valuable.

The Product Owner may cancel the Sprint and re-plan the work.

15. Sprint vs Waterfall Phase

| Waterfall | Scrum Sprint |
| --- | --- |
| Long phases | Short cycles |
| Feedback at the end | Feedback every Sprint |
| Large releases | Frequent Increments |
| Difficult to change | Easy to adapt |
| High risk | Lower risk |

16. Healthcare Example

Hospital Appointment System

Sprint 1

Patient Registration

Sprint 2

Doctor Availability

Sprint 3

Appointment Booking

Sprint 4

Prescription Module

After every Sprint:

Doctors test the functionality and provide feedback.

The product evolves continuously.

17. Pharmacovigilance Example

Drug Safety Platform

Sprint 1

Case Intake

Sprint 2

Duplicate Detection

Sprint 3

MedDRA Coding

Sprint 4

Signal Detection Dashboard

Regulatory experts review each Increment before moving forward.

This reduces compliance risks.

18. AI Product Example

AI Medical Assistant

Sprint 1

Chat Interface

Sprint 2

Medical Knowledge Retrieval

Sprint 3

Drug Interaction Detection

Sprint 4

Voice Conversation

Each Sprint delivers a usable enhancement instead of waiting for the entire system to be complete.

19. Benefits of Sprints

✔ Faster feedback

✔ Reduced project risk

✔ Better transparency

✔ Continuous improvement

✔ Early value delivery

✔ Easier prioritization

✔ Higher customer satisfaction

20. Common Mistakes

Mistake 1

Treating the Sprint as just a deadline.

A Sprint is a complete inspect-and-adapt cycle.

Mistake 2

Changing the Sprint Goal every few days.

This destroys focus.

Mistake 3

Adding unlimited work during the Sprint.

This leads to scope creep and missed goals.

Mistake 4

Skipping Sprint Review because "everyone is busy."

This eliminates valuable stakeholder feedback.

Mistake 5

Skipping the Retrospective.

Teams lose opportunities to improve.

21. Best Practices

✔ Maintain a consistent Sprint duration.

✔ Define a clear Sprint Goal.

✔ Deliver one usable Increment every Sprint.

✔ Protect the team from unnecessary interruptions.

✔ Encourage daily collaboration.

✔ Inspect and adapt after every Sprint.

✔ Keep stakeholders engaged throughout development.

22. Interview Questions

Q1. What is a Sprint?

Answer: A Sprint is a fixed-length Scrum event of one month or less during which the Scrum Team creates a usable and valuable Increment.

Q2. What is the maximum Sprint duration?

Answer: One month.

Q3. Who can cancel a Sprint?

Answer: Only the Product Owner, when the Sprint Goal becomes obsolete.

Q4. Can Sprint Backlog change during the Sprint?

Answer: Yes. Developers may update the Sprint Backlog as they learn more, provided changes support the Sprint Goal.

Q5. Why should Sprint duration remain consistent?

Answer: Consistent Sprint lengths improve predictability, velocity tracking, planning accuracy, and stakeholder expectations.

23. Sprint Metrics

Common metrics used to evaluate Sprint performance include:

- Sprint Goal Achievement

- Velocity

- Burndown Chart

- Burnup Chart

- Escaped Defects

- Team Capacity Utilization

- Cycle Time

- Lead Time

These metrics help teams inspect progress and improve future Sprints.

Mini Quiz

- What is the maximum duration of a Sprint according to the Scrum Guide?

- Who has the authority to cancel a Sprint?

- Why is a Sprint Goal important?

- Why should Sprint duration remain consistent?

- Name three benefits of working in Sprints.

Practical Assignment

For your AI Pharmacovigilance Platform:

Part 1 – Design a Sprint

- Sprint Duration

- Sprint Goal

- Team Members

- Sprint Backlog

- Expected Increment

Part 2 – Risk Analysis

Identify five risks that could affect your Sprint (e.g., unavailable datasets, regulatory changes, API failures, team absences) and propose mitigation strategies.

Part 3 – Reflection

Suppose your Product Owner requests a major new feature halfway through the Sprint.

- Should it be added?

- Would it affect the Sprint Goal?

- What would your recommendation be as a Product Manager?

Summary

A Sprint is the core execution cycle in Scrum. It is a fixed-length period of one month or less during which the Scrum Team works toward a Sprint Goal and produces a valuable Increment. Sprints create a regular cadence for planning, building, reviewing, and improving, enabling teams to deliver value frequently while adapting to change through continuous feedback.

Key Takeaways

- A Sprint is the foundation of Scrum.

- Every Sprint is timeboxed and lasts one month or less.

- Each Sprint has a clear Sprint Goal and ends with a usable Increment.

- Sprint duration should remain consistent for better predictability.

- Only the Product Owner can cancel a Sprint if the Sprint Goal becomes obsolete.

- Regular Sprints reduce risk, accelerate feedback, and support continuous product improvement across domains such as healthcare, pharmacovigilance, and AI.

Lesson 37: User Stories in Scrum – How to Write Effective User Stories, INVEST, Acceptance Criteria & Real Product Examples

1. What is a User Story?

A User Story is a simple description of a product requirement written from the perspective of the user.

Instead of writing technical requirements:

❌ "Create API endpoint for customer login"

Agile teams write:

✅ "As a customer, I want to log into my account so that I can access my personal dashboard."

The focus shifts from what the system does to why the user needs it.

2. User Story Format (3 Important Parts)

The standard Scrum format:

As a [user/persona]
I want [goal/action]
So that [business value/benefit]

Example 1: Banking App

As a bank customer
I want to transfer money online
So that I can send payments without visiting a branch.

Breakdown:

| Part | Meaning |
| --- | --- |
| As a | Who needs it? |
| I want | What functionality is needed? |
| So that | Why does it matter? |

3. User Story vs Requirement

Traditional requirement:

System should allow users to reset passwords.

Agile User Story:

As a registered user, I want to reset my password so that I can regain access to my account if I forget it.

Why is the second better?

Because the team understands:

- Who needs it

- What problem exists

- Why it has value

4. INVEST Principle

A good user story follows the INVEST rule.

I – Independent

A story should be developed separately.

Bad:

Build complete e-commerce checkout system.

Too large.

Better:

- Add cart functionality

- Add address selection

- Add payment option

- Add order confirmation

N – Negotiable

A story is not a fixed contract.

Example:

User Story:

As a customer, I want product recommendations.

The team can discuss:

- AI recommendations?

- Based on history?

- Based on popular products?

The solution is negotiable.

V – Valuable

Every story must provide user/business value.

Bad:

As a developer, I want to create a database table.

This has technical value, but no direct user value.

Better:

As a customer, I want my order history saved so that I can view previous purchases.

E – Estimable

The team should understand enough to estimate effort.

Example:

❌ "Improve performance"

Too vague.

Better:

✅ "As a user, I want the dashboard to load within 3 seconds so that I can quickly view my data."

S – Small

A story should fit inside one sprint.

Large story:

As a patient, I want an online healthcare platform.

Break into:

- Register account

- Search doctors

- Book appointment

- Upload medical records

- Make payment

T – Testable

A story must have clear acceptance criteria.

Example:

User Story:

As a customer, I want to receive an OTP during login so that my account remains secure.

Test:

✔ OTP should be sent
✔ OTP should expire after 5 minutes
✔ Wrong OTP should show error message

5. User Story Size: Epic → Feature → Story → Task

Agile uses hierarchy.

Epic

Large business objective.

Example:

Improve Patient Healthcare Experience

↓

Features

Major capabilities:

- Online appointment booking

- Doctor consultation

- Prescription management

↓

User Stories

Example:

As a patient, I want to book an appointment online so that I can consult a doctor easily.

↓

Tasks

Development activities:

- Create appointment database

- Design booking screen

- Create API

- Test workflow

6. Acceptance Criteria

Acceptance Criteria define when a story is considered complete.

A common format:

Given – When – Then

Example:

User Story:

As a customer, I want to login securely so that my account is protected.

Acceptance Criteria:

Given the user has a registered account

When the user enters correct username and password

Then the user should successfully login

Another:

Given the user enters wrong password

When login button is clicked

Then an error message should appear

7. Real Product Example: Amazon

Epic:

Online Shopping Experience

User Story 1:

As a customer, I want to search products so that I can find items quickly.

Acceptance Criteria:

- Search box available

- Results displayed

- Relevant products shown

User Story 2:

As a customer, I want to filter products by price so that I can buy within my budget.

Acceptance Criteria:

- Price filter available

- Products update after selection

User Story 3:

As a customer, I want order tracking so that I know delivery status.

Acceptance Criteria:

- Tracking number displayed

- Delivery status updated

8. Healthcare / Pharmacovigilance Example (Relevant to Your Domain)

Epic:

AI Pharmacovigilance Case Processing Platform

Feature:

ICSR Management

User Story:

As a Pharmacovigilance Associate, I want AI to extract adverse event information from source documents so that I can process safety cases faster.

Acceptance Criteria:

Given a medical document is uploaded

When AI extraction runs

Then patient, drug, event and seriousness information should be extracted

Another:

As a Safety Reviewer, I want duplicate case detection so that duplicate reports are not processed twice.

Acceptance Criteria:

- Compare patient details

- Compare drug information

- Show similarity score

- Allow reviewer decision

9. Common Mistakes in Writing User Stories

Mistake 1: Writing tasks instead of stories

❌ Create database table

✅ As a user, I want my information stored securely so that I can access my history.

Mistake 2: Too big stories

❌ Build complete banking app

Break into smaller stories.

Mistake 3: Missing business value

❌ As a user, I want a button.

Why?

The button itself has no value.

Mistake 4: Writing from developer perspective

❌ As a developer, I want React components.

The user does not care about technology.

10. Product Manager / Business Analyst Skill

A strong BA or Product Manager should be able to convert:

Business Problem → Epic → Feature → User Stories → Acceptance Criteria

Example:

Business Problem:

"Patients wait too long for appointments."

↓

Epic:

Digital Appointment System

↓

Feature:

Online Booking

↓

User Story:

"As a patient, I want to book appointments online so that I can avoid waiting on phone calls."

↓

Acceptance Criteria:

- Doctor availability shown

- Appointment confirmation generated

- Reminder sent

Lesson 37 Practical Exercise

Create 5 user stories for this product:

AI Pharmacovigilance Platform

Use format:

As a ______
I want ______
So that ______

Create stories for:

- Login module

- AI Data Extraction

- MedDRA Coding

- Duplicate Detection

- Compliance Dashboard

Lesson 38: Product Backlog Management – Prioritization, MoSCoW, RICE Scoring & Product Decision Making

1. What is a Product Backlog?

A Product Backlog is a prioritized list of everything needed to improve a product.

It contains:

- New features

- User stories

- Bugs

- Technical improvements

- Research tasks

- Compliance requirements

The Product Owner owns and manages the backlog.

Example: AI Pharmacovigilance Platform Backlog

| Priority | Backlog Item | Type |
| --- | --- | --- |
| 1 | Upload adverse event report | User Story |
| 2 | AI extraction of patient/drug/event data | Feature |
| 3 | Duplicate case detection | Feature |
| 4 | MedDRA coding automation | Feature |
| 5 | Dashboard improvements | Enhancement |
| 6 | Database optimization | Technical |

The backlog is not just a list — it is ordered by business value.

2. Product Backlog vs Sprint Backlog

Many beginners confuse these.

Product Backlog

The complete list of future work.

Example:

Login

Registration

AI Extraction

Reports

Analytics

Mobile App

Notifications

Sprint Backlog

The selected items for the current sprint.

Example:

Sprint 1:

✔ Login

✔ Registration

✔ User Profile

Sprint 2:

✔ AI Extraction

✔ Document Upload

3. Who Prioritizes the Backlog?

Product Owner

Responsible for:

- Business value

- Customer needs

- Market requirements

- ROI

Developers

Help with:

- Technical complexity

- Dependencies

- Risk estimation

Scrum Master

Ensures:

- Proper Scrum process

- Team collaboration

4. Why Prioritization is Important?

Because resources are limited.

You cannot build everything immediately.

Example:

A healthcare startup has:

100 requested features

But only:

- 5 developers

- 3 months timeline

- Limited budget

Decision required:

"What creates maximum value first?"

5. MoSCoW Prioritization Technique

One of the most common BA/Product Manager techniques.

MoSCoW:

M – Must Have

Critical features.

Without this product cannot work.

Example: Hospital App

Must Have:

✔ Patient registration
✔ Doctor appointment booking
✔ Medical record storage

S – Should Have

Important but not mandatory.

Example:

- Appointment reminders

- Patient feedback

C – Could Have

Nice-to-have features.

Example:

- Dark mode

- Chat stickers

- Custom themes

W – Won't Have (Currently)

Not planned now.

Example:

- VR doctor consultation

- Blockchain records

Example: AI Pharmacovigilance Platform

Must Have

| Feature | Reason |
| --- | --- |
| Login | Security |
| Case creation | Core workflow |
| Adverse event extraction | Main AI value |
| Audit trail | Regulatory requirement |

Should Have

Feature

Duplicate detection

MedDRA suggestion

Automated reports

Could Have

Feature

Voice-based case entry

AI chatbot assistant

Won't Have Now

Feature

Fully autonomous regulatory submission

6. RICE Prioritization Framework

Used by modern Product Managers.

RICE =

R → Reach

How many users will benefit?

Example:

Feature affects:

10,000 users/month

Reach = 10,000

I → Impact

How much improvement?

Scale:

| Impact | Score |
| --- | --- |
| Massive | 3 |
| High | 2 |
| Medium | 1 |
| Low | 0.5 |

C → Confidence

How sure are we?

Example:

Based on customer data:

90% confidence

Confidence = 0.9

E → Effort

How much work required?

Example:

Developer effort:

2 person-months

Formula:

RICE Score = (Reach × Impact × Confidence) / Effort

Example

Two features:

Feature A: AI Document Extraction

Reach:

5000 users

Impact:

3

Confidence:

0.8

Effort:

4

Calculation:

(5000 × 3 × 0.8) / 4

= 3000

Feature B: Dark Mode

Reach:

5000

Impact:

0.5

Confidence:

1

Effort:

1

(5000 × 0.5 × 1)/1

=2500

Feature A gets higher priority.

7. Value vs Effort Matrix

Another popular method.

5

Four quadrants:

Quick Wins

High Value + Low Effort

Build first.

Example:

- Add export to CSV

- Add email notification

Major Projects

High Value + High Effort

Plan carefully.

Example:

- AI case processing engine

Fill-ins

Low Value + Low Effort

Do when time available.

Example:

- UI improvements

Avoid

Low Value + High Effort

Usually reject.

Example:

- Complex feature nobody requested

8. Prioritization Example: Healthcare AI Product

Suppose backlog:

| Feature | Value | Effort |
| --- | --- | --- |
| AI adverse event extraction | High | High |
| Dashboard color change | Low | Low |
| Duplicate detection | High | Medium |
| User profile photo | Low | Low |
| Regulatory report generation | Very High | High |

Priority:

- Regulatory reports

- AI extraction

- Duplicate detection

- UI improvements

- Profile photo

9. Product Manager Thinking

A Product Manager does not ask:

❌ "Can we build this?"

They ask:

✅ "Should we build this?"

Decision factors:

Customer Value

Does it solve a real problem?

Business Value

Will it:

- Increase revenue?

- Reduce cost?

- Improve retention?

Risk

Could it create:

- Regulatory problems?

- Security issues?

- Compliance failures?

Effort

How much:

- Time?

- Money?

- Engineering resources?

10. Real Interview Question

Question:

"Your users request 50 features. How will you decide what to build first?"

Good Product Manager answer:

"I will prioritize features based on customer impact, business value, urgency, regulatory requirements, effort, and technical feasibility. I will use frameworks like MoSCoW or RICE scoring and validate decisions using user feedback and data."

Lesson 38 Practical Exercise

For your AI Pharmacovigilance Platform, create a priority list.

Classify these using MoSCoW:

- Login System

- AI adverse event extraction

- Dark mode

- Duplicate detection

- Regulatory compliance dashboard

- AI chatbot assistant

- Audit trail

- Voice case entry

Lesson 39: Agile Estimation Techniques – Story Points, Planning Poker, Fibonacci, Velocity & Sprint Capacity

1. Why Do Agile Teams Estimate?

Before starting a sprint, the team needs to answer:

- How much work can we complete?

- How complex is each requirement?

- Can we deliver within the sprint?

Traditional approach:

"How many hours will this take?"

Agile approach:

"How complex is this compared to other work?"

Agile focuses on relative estimation.

2. What are Story Points?

A Story Point is a unit used to estimate the overall complexity of a user story.

It considers:

- Effort required

- Complexity

- Uncertainty

- Risk

- Technical difficulty

It does not directly mean hours.

Example

Two developers estimate:

Story A:

As a user, I want to change my profile picture.

Estimate:

2 Story Points

Because:

- Simple UI

- Simple database update

- Low risk

Story B:

As a doctor, I want AI to summarize patient history.

Estimate:

8 Story Points

Because:

- AI integration

- Data processing

- Accuracy concerns

- Testing complexity

3. Story Points vs Hours

Many beginners confuse this.

| Story Points | Hours |
| --- | --- |
| Relative measurement | Actual time |
| Team-based | Individual-based |
| Includes uncertainty | Only effort |
| Used for forecasting | Used for tracking |

Example:

A senior developer may complete a 5-point story in 2 days.

A junior developer may need 5 days.

The story point remains 5.

4. Fibonacci Sequence in Agile

Most Scrum teams use:

1, 2, 3, 5, 8, 13, 21

Why?

Because uncertainty increases with complexity.

Difference between:

1 and 2 = small

Difference between:

8 and 13 = significant

Meaning Example

1 Point

Very easy.

Example:

Change button text.

2 Points

Small change.

Example:

Add profile field.

3 Points

Moderate.

Example:

Create password reset.

5 Points

Complex.

Example:

Payment integration.

8 Points

Very complex.

Example:

AI document extraction module.

13+ Points

Too large.

Break into smaller stories.

5. Planning Poker

Planning Poker is a team estimation technique.

Participants:

- Product Owner

- Developers

- QA

- Scrum Master

Process:

Step 1

Product Owner explains story.

Example:

"As a PV associate, I want AI to extract adverse event data from PDF reports."

Step 2

Everyone selects a card:

1

2

3

5

8

13

Step 3

Everyone reveals cards together.

Example:

Developer A:

5

Developer B:

8

QA:

13

Step 4

Discussion happens.

Question:

Why did QA select 13?

Answer:

"Testing AI accuracy and edge cases will be difficult."

Step 5

Team agrees:

Final estimate:

8 points

6. Why Not Let the Product Owner Estimate?

Because estimation requires technical understanding.

Product Owner explains:

What and Why

Developers estimate:

How

7. Velocity

Velocity is the amount of work a Scrum team completes in one sprint.

Formula:

Velocity =

Total Story Points Completed

Example:

Sprint 1:

Completed:

Login = 3 points

Registration = 5 points

Profile = 2 points

Velocity:

3 + 5 + 2 = 10 points

8. Sprint Capacity

Capacity means how much time the team actually has available.

Example:

Team:

- 5 developers

- Sprint duration: 2 weeks

- Working days: 10

Total:

5 × 10 = 50 person-days

But:

Meetings, holidays, support work:

20% loss

Available:

50 × 80%

=40 person-days

9. Velocity Forecasting Example

Previous sprints:

| Sprint | Completed Points |
| --- | --- |
| Sprint 1 | 25 |
| Sprint 2 | 30 |
| Sprint 3 | 28 |

Average velocity:

(25+30+28)/3

=27.6

Next sprint capacity:

≈ 28 points

The team should not commit 60 points.

10. Example: AI Pharmacovigilance Sprint Planning

Sprint duration:

2 weeks

Team velocity:

30 points

Backlog:

| User Story | Points |
| --- | --- |
| Login | 3 |
| Case Creation | 5 |
| PDF Upload | 3 |
| AI Extraction | 13 |
| Audit Trail | 5 |
| Reports | 8 |

Total:

37 points

Cannot fit everything.

Sprint selection:

Login             3

Case Creation     5

PDF Upload        3

Audit Trail       5

Reports           8

Total = 24 points

AI Extraction moves to next sprint.

11. Common Estimation Mistakes

Mistake 1:

Assigning points based on developer speed.

Wrong:

"Rahul is fast, give him fewer points."

Correct:

Points belong to the story.

Mistake 2:

Using story points as performance metrics.

Wrong:

"Developer completed only 20 points."

Agile does not measure individual productivity.

Mistake 3:

Large stories.

Wrong:

"Build complete AI platform"

Estimate:

50 points ❌

Break:

- Upload document

- Extract data

- Validate fields

- Generate case

12. BA/Product Manager Interview Questions

Q1. What are story points?

Answer:

"Story points are a relative estimation technique used by Agile teams to measure complexity, effort, risk, and uncertainty of user stories rather than measuring exact hours."

Q2. Why Fibonacci numbers?

Answer:

"Because larger items have more uncertainty. Fibonacci numbers create natural separation between small and complex work."

Q3. Velocity increased from 25 to 40. Is the team better?

Answer:

Not necessarily.

Possible reasons:

- Stories were smaller

- Estimates changed

- Team added members

- More experience

Velocity is for planning, not performance ranking.

13. Practical Exercise

For your AI Pharmacovigilance Platform, estimate Story Points:

| User Story | Your Estimate |
| --- | --- |
| User Login | ? |
| Upload Safety Report PDF | ? |
| AI Data Extraction | ? |
| MedDRA Auto Coding | ? |
| Duplicate Detection | ? |
| Compliance Dashboard | ? |

Use:

1,2,3,5,8,13

Think like a Product Manager + BA.

Lesson 39a – Story Points & Planning Poker (Master Estimation in Scrum)

Learning Objectives

By the end of this lesson, you will understand:

- What are Story Points?

- Why Scrum uses Story Points instead of hours

- History of Story Points

- Relative Estimation

- Fibonacci Sequence

- T-Shirt Sizing

- Affinity Estimation

- Planning Poker

- Story Point Calibration

- Factors affecting Story Points

- Common estimation mistakes

- Team Velocity connection

- Healthcare examples

- Pharmacovigilance examples

- AI Product examples

- Best Practices

- Interview Questions

- Mini Quiz

- Practical Assignment

1. Introduction

Imagine you ask two people:

How long will it take to climb a mountain?

Person A:

5 hours.

Person B:

8 hours.

Person C:

Depends on weather.

Person D:

Depends on experience.

Who is correct?

Actually...

Everyone might be.

Software estimation is exactly like this.

Humans are poor at predicting exact time, especially for creative work like software development.

Instead of estimating hours, Scrum estimates relative effort.

That is why Story Points were introduced.

2. What are Story Points?

Story Points measure the relative effort required to complete a User Story.

Notice the word:

Relative

Story Points do NOT measure:

❌ Hours

❌ Days

❌ Calendar time

Instead they compare one story with another.

Example

Story A

Login Page

3 Story Points

Story B

AI Disease Prediction

13 Story Points

This means:

Story B requires much more effort than Story A.

Not necessarily more time.

3. Why Doesn't Scrum Estimate in Hours?

Imagine two developers.

Senior Developer

Completes a task in 4 hours.

Junior Developer

Needs 12 hours.

If estimates were in hours:

Which estimate is correct?

Both.

This makes planning inconsistent.

Story Points solve this problem.

They estimate:

- Complexity

- Risk

- Uncertainty

- Effort

Instead of time.

4. History of Story Points

Story Points became popular through Extreme Programming (XP) and later Agile methodologies.

The concept was refined by Agile practitioners such as Ron Jeffries, Mike Cohn, and others, who promoted relative estimation instead of time-based estimation.

Today Story Points are one of the most common Agile estimation techniques.

5. Relative Estimation

Instead of asking:

"How many hours?"

Ask:

"Compared to another story, how difficult is this?"

Example

Reference Story

Login Screen

= 3 Story Points

Compare

Patient Dashboard

Looks twice as difficult.

Estimate

= 5 Story Points

AI NLP Engine

Looks four times harder.

Estimate

= 13 Story Points

The team compares work rather than predicting exact duration.

6. What Determines Story Points?

Story Points consider multiple factors.

Complexity

Business logic

Example

Simple Login

Low complexity

Amount of Work

Number of screens

Number of APIs

Database work

Testing effort

Risk

Unknown technology

External APIs

Security

Compliance

Uncertainty

Requirements unclear

AI model behavior unknown

New framework

Poor documentation

Story Points represent the combination of all these factors.

7. Fibonacci Sequence

Most Scrum Teams use:

Sequence

1

2

3

5

8

13

21

34

55

89

Notice

The gap keeps increasing.

Why?

Because uncertainty grows with larger work.

Large stories become difficult to estimate precisely.

8. Why Not Use 1–100?

Suppose two Developers estimate:

Developer A

42

Developer B

43

Meaningless difference.

Instead

Choose

34

Much easier.

Larger work has larger uncertainty.

Fibonacci naturally reflects uncertainty.

9. Story Point Scale

Typical interpretation

| Story Points | Meaning |
| --- | --- |
| 1 | Very Small |
| 2 | Small |
| 3 | Moderate |
| 5 | Medium |
| 8 | Large |
| 13 | Very Large |
| 21+ | Epic (should usually be split) |

Generally, stories estimated at 21 Story Points or higher should be decomposed into smaller User Stories before entering a Sprint.

10. Example

Hospital Management System

| Story | Story Points |
| --- | --- |
| Login | 2 |
| Search Doctor | 3 |
| Appointment Booking | 5 |
| Online Payment | 8 |
| AI Appointment Recommendation | 13 |

Notice

Points increase with complexity.

11. What is Planning Poker?

Planning Poker is a collaborative estimation technique.

Each participant receives cards.

Example

1

2

3

5

8

13

21

34

Everyone estimates independently.

All cards are revealed simultaneously.

Discussion begins if estimates differ.

12. Why Simultaneous Voting?

Imagine

Senior Developer

"I think it's 13."

Everyone else says

13

Even if they disagree.

This is called

Anchoring Bias.

Planning Poker prevents this.

Everyone votes secretly first.

Then discusses differences.

13. Planning Poker Workflow

User Story Presented

│

▼

Questions

│

▼

Individual Thinking

│

▼

Secret Vote

│

▼

Reveal Cards

│

▼

Discuss Differences

│

▼

Vote Again

│

▼

Consensus

14. Example Planning Poker Session

Story

Patient Search

Developer A

3

Developer B

5

Developer C

8

Discussion

Developer C explains

Search includes OCR indexing.

Others didn't know.

Second Vote

5

5

5

Consensus achieved.

15. Story Point Calibration

Every Scrum Team creates its own internal reference.

Example

Reference Story

Simple Login

2 Points

Now compare everything against Login.

Dashboard

Twice as difficult

5 Points

AI Prediction

Much harder

13 Points

Consistency matters more than perfection.

16. T-Shirt Sizing

Sometimes teams estimate using:

| Size | Meaning |
| --- | --- |
| XS | Very Small |
| S | Small |
| M | Medium |
| L | Large |
| XL | Very Large |

Later

Convert

XS → 1

S → 2

M → 5

L → 8

XL → 13

Useful during early product planning when detailed requirements are unavailable.

17. Affinity Estimation

Affinity Estimation is useful when hundreds of stories require estimation.

Process

Place stories on a board.

Arrange from easiest to hardest.

Assign Story Points later.

This method is much faster than Planning Poker for large backlogs.

18. Story Points vs Hours

| Story Points | Hours |
| --- | --- |
| Relative effort | Exact time |
| Team-based | Individual-based |
| Includes uncertainty | Ignores uncertainty |
| Stable over time | Varies by developer |
| Used in Scrum | Less preferred in Scrum |

19. Healthcare Example

Hospital System

Stories

Login

2

Doctor Search

3

Appointment Booking

5

Medical History

8

AI Disease Prediction

13

The team uses Planning Poker to estimate each story.

20. Pharmacovigilance Example

AI Drug Safety Platform

Stories

Upload PDF

3

OCR

5

Patient Extraction

8

MedDRA Coding

13

Signal Detection Dashboard

21

Because 21 is too large,

the Product Owner splits it into:

- Dashboard UI

- Signal Charts

- Filters

- Export Reports

Each story is re-estimated individually.

21. AI Product Example

Medical AI Assistant

Stories

Prompt Library

5

Voice Input

8

LLM Integration

8

Medical Knowledge Graph

13

Clinical Decision Support

21

The team decides to split Clinical Decision Support into smaller User Stories before Sprint Planning.

22. Common Estimation Mistakes

Mistake 1

Estimating in hours instead of relative effort.

Mistake 2

Comparing Story Points across different teams.

Story Points are team-specific.

Mistake 3

Senior developer dominates estimation.

Planning Poker avoids this.

Mistake 4

Treating Story Points as productivity metrics.

Never judge individual developers using Story Points.

Mistake 5

Large User Stories remain unbroken.

Anything above approximately 21 Story Points usually requires splitting.

23. Best Practices

✔ Estimate collaboratively.

✔ Use reference stories.

✔ Prefer Fibonacci numbers.

✔ Discuss uncertainty.

✔ Split large stories.

✔ Never compare Story Points between teams.

✔ Review estimates during refinement.

✔ Focus on consistency, not precision.

24. Interview Questions

Q1. What are Story Points?

Answer: Story Points are a relative unit of estimation used to measure the effort, complexity, risk, and uncertainty of completing a User Story.

Q2. Why doesn't Scrum estimate in hours?

Answer: Hours vary based on individual skills and circumstances. Story Points provide a more consistent, team-based measure of relative effort.

Q3. Why is the Fibonacci sequence commonly used?

Answer: As work becomes larger, uncertainty increases. Fibonacci numbers naturally reflect this growing uncertainty.

Q4. What is Planning Poker?

Answer: Planning Poker is a collaborative estimation technique where team members independently estimate User Stories using Story Point cards, reveal their estimates simultaneously, discuss differences, and reach consensus.

Q5. Can Story Points be compared between teams?

Answer: No. Story Points are calibrated within each Scrum Team and should never be used to compare productivity across different teams.

25. Real-World Case Study

AI Pharmacovigilance Platform

The Product Owner presents a User Story:

"As a Drug Safety Associate, I want the system to automatically identify adverse events from uploaded ICSRs so that manual review time is reduced."

First Planning Poker Vote

| Team Member | Estimate |
| --- | --- |
| Developer A | 5 |
| Developer B | 8 |
| AI Engineer | 13 |
| QA Engineer | 8 |

Discussion

The AI Engineer explains:

- NLP model training is required.

- Medical terminology mapping is complex.

- Existing training data needs cleaning.

The team realizes the work is more complex than initially thought.

Second Vote

| Team Member | Estimate |
| --- | --- |
| Developer A | 8 |
| Developer B | 8 |
| AI Engineer | 8 |
| QA Engineer | 8 |

Consensus:

8 Story Points

The story is accepted into the refined Product Backlog.

Mini Quiz

- What do Story Points measure?

- Why are Story Points preferred over hours in Scrum?

- What four major factors influence Story Point estimation?

- Why does Planning Poker use simultaneous voting?

- Why shouldn't Story Points be compared across Scrum Teams?

Practical Assignment

For your AI Pharmacovigilance Platform:

Part 1 – Estimate User Stories

Estimate the following using Story Points:

- User Login

- Upload ICSR PDF

- OCR Processing

- Patient Information Extraction

- Drug Name Extraction

- MedDRA Coding

- Duplicate Case Detection

- Signal Detection Dashboard

Explain why you assigned each estimate.

Part 2 – Conduct a Planning Poker Session

Assume a team of:

- Product Owner

- Scrum Master

- Backend Developer

- Frontend Developer

- AI Engineer

- QA Engineer

Simulate two rounds of Planning Poker for three User Stories and show how consensus is reached.

Part 3 – Apply the INVEST Model

Choose three User Stories and verify whether they satisfy:

- Independent

- Negotiable

- Valuable

- Estimable

- Small

- Testable

If not, explain how you would improve them.

Part 4 – Calibration Exercise

Select one simple User Story as your team's reference story (e.g., Login = 2 Story Points). Estimate five additional stories relative to this baseline and justify your reasoning.

Summary

Story Points are a relative estimation technique that measures the effort required to complete a User Story by considering complexity, effort, risk, and uncertainty rather than time. Planning Poker is the most widely used collaborative estimation method, helping Scrum Teams reach consensus while minimizing bias. Together, they improve forecasting, support Sprint Planning, and form the basis for measuring Velocity, which will be covered in the next lesson.

Key Takeaways

- Story Points estimate relative effort, not time.

- They account for complexity, effort, risk, and uncertainty.

- The Fibonacci sequence reflects increasing uncertainty as work grows.

- Planning Poker encourages collaborative estimation and reduces anchoring bias.

- Story Points are team-specific and should never be compared across teams.

- Story Points and Planning Poker are foundational concepts for understanding Velocity and Capacity Planning.

Lesson 39b– Velocity & Capacity Planning (Master Sprint Forecasting)

Learning Objectives

By the end of this lesson, you will understand:

- What is Velocity?

- What is Capacity Planning?

- Difference between Velocity and Capacity

- Why Scrum uses Velocity

- How Velocity is calculated

- Average Velocity

- Forecasting Future Sprints

- Capacity Calculation

- Team Availability

- Focus Factor

- Vacation and Holiday Planning

- Velocity vs Productivity

- Velocity Anti-patterns

- Healthcare examples

- Pharmacovigilance examples

- AI Product examples

- Best Practices

- Interview Questions

- Mini Quiz

- Practical Assignment

1. Introduction

Imagine you own a delivery company.

You want to know:

- How many parcels can your team deliver next week?

- Should you accept another 200 orders?

- Do you need more staff?

Without historical data, you can only guess.

Now imagine you know:

Last week:

150 deliveries

Week before:

145 deliveries

Week before:

152 deliveries

You can confidently predict next week's capacity.

This is exactly how Velocity works in Scrum.

Velocity helps Scrum Teams make data-driven forecasts, not guesses.

2. What is Velocity?

Velocity is the total number of Story Points completed during a Sprint.

Important:

Velocity counts only work that meets the Definition of Done.

If a User Story is incomplete, its Story Points are not counted.

Scrum Definition (Practical)

Velocity is a historical measure used by Scrum Teams to forecast how much work they are likely to complete in future Sprints.

Notice:

Velocity is based on history, not promises.

3. Example of Velocity

Sprint 1

| Story | Points | Done? |
| --- | --- | --- |
| Login | 3 | ✅ |
| Dashboard | 5 | ✅ |
| Reports | 8 | ❌ |

Velocity

3 + 5

= 8 Story Points

The unfinished 8-point story is not included.

4. Why is Velocity Important?

Velocity helps answer questions like:

- How much work can we realistically take into the next Sprint?

- When will the product be finished?

- Are we overcommitting?

- Do we need to split User Stories?

Without Velocity:

Planning becomes guesswork.

With Velocity:

Planning becomes evidence-based.

5. Velocity is Historical

Velocity cannot be predicted before a team has completed Sprints.

Example

Sprint 1

22

Sprint 2

25

Sprint 3

24

Average Velocity

24 Story Points

Future Sprint

≈24 Story Points

Notice:

Velocity is learned over time.

6. Velocity Formula

Velocity = Total Story Points completed

Example

Completed Stories

5

8

3

2

Velocity

= 18 Story Points

Simple.

7. Average Velocity

Teams rarely have identical Velocity every Sprint.

Example

| Sprint | Velocity |
| --- | --- |
| Sprint 1 | 22 |
| Sprint 2 | 25 |
| Sprint 3 | 21 |
| Sprint 4 | 24 |

Average Velocity

(22 + 25 + 21 + 24)

÷ 4

= 23 Story Points

Average Velocity provides a more stable forecast.

8. Forecasting Using Velocity

Suppose

Product Backlog

230 Story Points

Average Velocity

23

Forecast

230

÷ 23

= 10 Sprints

This helps Product Managers estimate release timelines.

Remember:

This is a forecast—not a guarantee.

9. What is Capacity Planning?

Velocity answers:

How much has the team completed in the past?

Capacity Planning answers:

How much can the team realistically work on in the upcoming Sprint?

Capacity considers current availability.

10. Capacity vs Velocity

| Velocity | Capacity |
| --- | --- |
| Historical | Future |
| Based on completed work | Based on available time |
| Story Points | Available effort |
| Used for forecasting | Used for Sprint Planning |

Easy Memory Trick

Velocity = Yesterday

Capacity = Tomorrow

11. Capacity Calculation

Suppose

Team Members

5

Sprint Length

10 days

Working Hours

8/day

Raw Capacity

5 × 10 × 8

= 400 Hours

Now subtract

Meetings

30 Hours

Leave

24 Hours

Training

16 Hours

Actual Capacity

400 − 70

= 330 Hours

Capacity should always reflect actual availability, not theoretical maximum.

12. Capacity Example

Team

| Member | Availability |
| --- | --- |
| Developer A | 100% |
| Developer B | 100% |
| Developer C | 80% |
| QA | 60% |
| AI Engineer | 100% |

Capacity changes every Sprint.

Velocity may remain similar over time, but capacity varies depending on team availability.

13. Focus Factor

Developers don't spend 100% of their time coding.

Typical work includes:

- Meetings

- Production support

- Documentation

- Code Reviews

- Learning

- Interruptions

Many teams use a Focus Factor.

Example

Raw Capacity

400 Hours

Focus Factor

75%

Effective Capacity

400 × 0.75

= 300 Hours

14. Holidays and Leave

Example

Sprint

10 Days

Developer

Vacation

3 Days

Capacity reduces automatically.

Never assume every team member is available every day.

Capacity Planning should include:

- Public Holidays

- Planned Leave

- Company Events

- Training

- On-call Support

15. Velocity Does NOT Measure Productivity

Many managers misuse Velocity.

Wrong

Higher Velocity means better developers.

Correct

Velocity measures how much work a team completed using its own estimation scale.

Example

Team A

Velocity

60

Team B

Velocity

25

Does Team A perform better?

Impossible to know.

Story Points are team-specific.

16. Velocity is NOT Comparable

Never compare

- Teams

- Departments

- Companies

Every team estimates differently.

Example

Team A

Login

5 Points

Team B

Login

2 Points

Both estimates are valid for their own teams.

17. Burnup of Velocity Over Time

Example

| Sprint | Velocity |
| --- | --- |
| 1 | 20 |
| 2 | 22 |
| 3 | 23 |
| 4 | 24 |
| 5 | 25 |

Notice

Velocity gradually stabilizes.

Stable Velocity improves release forecasting.

18. Healthcare Example

Hospital Management System

Average Velocity

30 Story Points

Upcoming Sprint

Doctor on leave.

Capacity reduced.

Instead of selecting

30 Points

The team selects

24 Points

Sprint succeeds.

19. Pharmacovigilance Example

AI Drug Safety Platform

Historical Velocity

40 Story Points

Upcoming Sprint

Regulatory audit week.

Developers unavailable.

Capacity falls to

28 Story Points.

Product Owner adjusts Sprint scope.

Sprint Goal remains achievable.

20. AI Product Example

Medical AI Assistant

Velocity

35 Story Points

Upcoming Sprint

Large LLM upgrade planned.

Higher uncertainty.

Team intentionally commits to

30 Story Points.

Risk decreases.

21. Common Velocity Anti-Patterns

Anti-pattern 1

Increasing Story Points to appear faster.

This destroys forecasting.

Anti-pattern 2

Comparing team performance using Velocity.

Velocity is not a KPI.

Anti-pattern 3

Counting incomplete stories.

Only Done stories count.

Anti-pattern 4

Treating Velocity as a target.

Teams may inflate estimates.

Velocity is an observation, not a goal.

Anti-pattern 5

Ignoring Capacity.

Historical Velocity cannot replace current availability.

22. Best Practices

✔ Track Velocity consistently.

✔ Use completed Story Points only.

✔ Calculate Average Velocity after several Sprints.

✔ Adjust Sprint scope based on Capacity.

✔ Consider vacations and holidays.

✔ Never compare teams.

✔ Use Velocity for forecasting, not performance evaluation.

✔ Review Velocity trends rather than a single Sprint.

23. Interview Questions

Q1. What is Velocity?

Answer: Velocity is the total number of Story Points completed according to the Definition of Done during a Sprint. It is used to forecast future work.

Q2. How is Velocity calculated?

Answer: By summing the Story Points of all completed User Stories in a Sprint.

Q3. What is Capacity Planning?

Answer: Capacity Planning determines how much work the team can realistically undertake in the upcoming Sprint based on availability, holidays, meetings, and other commitments.

Q4. What is the difference between Velocity and Capacity?

Answer: Velocity is a historical measure of completed work, while Capacity is a forward-looking estimate of the team's available effort for the next Sprint.

Q5. Can Velocity be used to compare Scrum Teams?

Answer: No. Story Points are relative and team-specific, so Velocity should never be used to compare different teams.

24. Real-World Case Study

AI Pharmacovigilance Platform

The Scrum Team has completed five Sprints.

| Sprint | Velocity |
| --- | --- |
| Sprint 1 | 32 |
| Sprint 2 | 36 |
| Sprint 3 | 34 |
| Sprint 4 | 35 |
| Sprint 5 | 33 |

Average Velocity:

(32 + 36 + 34 + 35 + 33) ÷ 5

= 34 Story Points

Upcoming Sprint

Changes:

- One AI Engineer is on leave for 5 days.

- One public holiday occurs during the Sprint.

- A regulatory audit requires the Product Owner's availability.

Capacity is reduced by approximately 20%.

Instead of planning 34 Story Points, the Scrum Team selects 27 Story Points.

Result:

- Sprint Goal achieved.

- No overtime.

- Stable Velocity maintained.

This demonstrates how Velocity and Capacity complement each other during Sprint Planning.

25. Advanced Concepts

Rolling Average Velocity

Instead of averaging all historical Sprints, many teams use the last 3–5 Sprints to reflect recent performance.

Example:

Velocities:

24, 25, 26, 22, 27

Rolling Average (last 3):

(26 + 22 + 27) ÷ 3

= 25 Story Points

This better reflects current team performance.

Velocity Range

Forecasts are often more reliable as a range.

Example:

Last six Sprint Velocities:

20, 22, 24, 21, 23, 25

Forecast:

20–25 Story Points

Planning within a range acknowledges natural variation.

Mini Quiz

- What is Velocity?

- How is Velocity calculated?

- What is Capacity Planning?

- Why shouldn't Velocity be used to compare teams?

- Why should unfinished stories not count toward Velocity?

Practical Assignment

For your AI Pharmacovigilance Platform:

Part 1 – Calculate Velocity

Given:

| Sprint | Completed Story Points |
| --- | --- |
| Sprint 1 | 28 |
| Sprint 2 | 32 |
| Sprint 3 | 30 |
| Sprint 4 | 34 |
| Sprint 5 | 31 |

Calculate:

- Average Velocity

- Rolling Average (last 3 Sprints)

- Velocity Range

Part 2 – Capacity Planning

Assume:

- 6 Team Members

- 10 Working Days

- 8 Hours/Day

- One member on leave for 2 days

- One public holiday

- Focus Factor = 75%

Calculate the team's effective capacity.

Part 3 – Sprint Forecast

Your Product Backlog contains 170 Story Points.

Using your calculated Average Velocity, estimate:

- Number of Sprints required

- Estimated release timeline

Discuss factors that could affect the accuracy of your forecast.

Part 4 – Reflection

Your team's Velocity dropped from 34 to 24 Story Points for one Sprint.

Identify at least five possible reasons (e.g., major production incident, team leave, technical debt, changing requirements) and explain how you would determine whether this is a temporary fluctuation or a trend.

Summary

Velocity and Capacity Planning are complementary practices that help Scrum Teams make realistic Sprint forecasts. Velocity uses historical delivery data to predict future throughput, while Capacity Planning adjusts those forecasts based on the team's actual availability. Used together, they enable predictable delivery without overcommitting the team.

Key Takeaways

- Velocity measures completed Story Points from past Sprints.

- Capacity Planning measures the team's available effort for the upcoming Sprint.

- Only Done work contributes to Velocity.

- Velocity is a forecasting tool, not a productivity metric.

- Story Points and Velocity are team-specific and should never be compared across teams.

- Combining historical Velocity with current Capacity leads to more reliable Sprint Planning and sustainable delivery.

Lesson 40: Scrum Ceremonies – Sprint Planning, Daily Scrum, Sprint Review & Sprint Retrospective

This lesson is extremely important for Business Analyst, Product Owner, Product Manager and Scrum Master interviews.

A Scrum team works in short cycles called Sprints (usually 1–4 weeks). During each sprint, Scrum has specific events (ceremonies) to plan, execute, inspect and improve work.

1. Overview of Scrum Events

A Scrum Sprint follows this cycle:

Product Backlog

↓

Sprint Planning

↓

Development Work

↓

Daily Scrum (Every Day)

↓

Sprint Review

↓

Sprint Retrospective

↓

Next Sprint

2. Sprint Planning

What is Sprint Planning?

Sprint Planning is the meeting where the team decides:

"What will we build in this sprint and how will we build it?"

It happens at the beginning of every sprint.

Participants

- Product Owner

- Scrum Master

- Developers

(Optional: Business Analyst, QA, stakeholders)

Sprint Planning Has Two Main Questions

Question 1:

What can we deliver?

(Product Goal + Backlog Priorities)

Example:

Product Owner says:

"Our priority is to improve PV case processing speed."

Selected stories:

- Upload case documents

- AI extraction

- Case validation

Question 2:

How will we complete it?

Development team discusses:

- Technical approach

- Dependencies

- Tasks

- Risks

Example: AI Pharmacovigilance Sprint Planning

Sprint Goal:

"Enable automated ICSR case intake."

Selected User Stories:

| Story | Points |
| --- | --- |
| Upload PDF report | 3 |
| Extract patient information | 5 |
| Extract adverse event details | 5 |
| Create case record | 3 |

Total:

16 Story Points

Team breaks stories into tasks:

User Story:

"Upload PDF report"

Tasks:

Create upload UI

Create API endpoint

Store document

Validate file type

Test upload

Sprint Planning Output

After meeting, team has:

1. Sprint Goal

Example:

"Allow PV associates to upload and process safety reports."

2. Sprint Backlog

Selected user stories.

3. Plan to deliver

Tasks and approach.

3. Daily Scrum (Daily Stand-up)

What is Daily Scrum?

A short daily meeting (15 minutes).

Purpose:

- Synchronize team

- Identify blockers

- Adjust plan

Three Classic Questions

Each team member answers:

1. What did I complete yesterday?

Example:

"Completed PDF upload API."

2. What will I do today?

Example:

"I will integrate document validation."

3. Any blockers?

Example:

"Waiting for AWS access."

Important:

Daily Scrum is NOT:

❌ Status report to manager

❌ Problem-solving meeting

❌ Long discussion

If a problem needs discussion:

Move it after the meeting.

4. Sprint Review

What is Sprint Review?

At the end of sprint, the team demonstrates completed work to stakeholders.

Purpose:

- Collect feedback

- Validate product direction

- Adjust backlog

Participants:

- Scrum Team

- Product Owner

- Customers

- Business stakeholders

Example:

AI Pharmacovigilance Sprint Review

Team demonstrates:

✅ Upload PDF
✅ AI extracts patient details
✅ Case created automatically

Stakeholder feedback:

"Can we add support for scanned handwritten reports?"

Product Owner adds:

New backlog item:

" OCR support for scanned documents"

Sprint Review is NOT:

❌ Presentation of unfinished work

❌ Performance evaluation

❌ Status meeting

5. Sprint Retrospective

What is Sprint Retrospective?

A team improvement meeting after Sprint Review.

Question:

"How can we work better in the next sprint?"

Participants:

Only Scrum Team:

- Product Owner

- Scrum Master

- Developers

Typical Retrospective Questions

What went well?

Example:

✔ Good collaboration between BA and developers

What did not go well?

Example:

❌ Requirements were unclear

What should we improve?

Example:

Action:

"BA will add acceptance criteria before sprint starts."

Example: AI PV Platform Retrospective

Good:

- AI extraction accuracy improved

- QA completed testing early

Problems:

- Too many requirement changes

- API documentation missing

Action Items:

- Create better user stories

- Add API documentation checklist

6. Sprint Review vs Retrospective Difference

Very common interview question.

| Sprint Review | Sprint Retrospective |
| --- | --- |
| Product focused | Process focused |
| Stakeholders participate | Only Scrum team |
| Review what was built | Improve how we work |
| Feedback on product | Feedback on teamwork |

Example:

Sprint Review:

"AI extraction should include seriousness criteria."

Retrospective:

"We need better communication before development starts."

7. Role of Business Analyst in Scrum Ceremonies

Since you are targeting BA/Product roles, understand this.

Before Sprint Planning

BA:

- Refines requirements

- Writes user stories

- Defines acceptance criteria

- Clarifies business rules

During Sprint Planning

BA:

- Explains user needs

- Answers requirement questions

- Helps prioritize

During Daily Scrum

BA:

- Helps remove requirement blockers

During Sprint Review

BA:

- Collects stakeholder feedback

- Updates requirements

During Retrospective

BA:

- Suggests process improvements

8. Scrum Ceremony Timeline Example

Two-week Sprint:

Day 1:

Sprint Planning

Day 2-13:

Development

Daily Scrum

Day 14:

Sprint Review

Day 14:

Sprint Retrospective

Then next sprint begins.

9. Real Interview Questions

Q1. Difference between Sprint Review and Retrospective?

Answer:

"Sprint Review focuses on the product increment and stakeholder feedback, whereas Sprint Retrospective focuses on improving team processes and ways of working."

Q2. What happens if a story is incomplete at the end of sprint?

Answer:

"The story is not considered done. It returns to the Product Backlog, and the Product Owner decides its priority for future sprints."

Q3. Who decides Sprint Goal?

Answer:

"The Scrum Team collaboratively creates the Sprint Goal, with the Product Owner providing business priorities."

10. Practical Exercise

For your AI Pharmacovigilance Platform, create:

Sprint Goal:

Example:

"Enable PV associates to create and manage safety cases."

Sprint Backlog:

Select 5 items:

- Login

- Case Creation

- PDF Upload

- AI Extraction

- Duplicate Detection

- MedDRA Coding

- Compliance Dashboard

Sprint Retrospective:

Write:

What went well?

What problems occurred?

What improvement action will you take?

Lesson 41: Definition of Done (DoD), Definition of Ready (DoR), Acceptance Criteria & Feature Completion in Agile

This lesson is very important for Business Analyst, Product Owner and Product Manager roles because many projects fail due to unclear understanding of:

- When work can start

- When work is truly complete

- What quality standards must be met

1. Why Do We Need Completion Rules?

Imagine a developer says:

"The login feature is completed."

But:

- UI is ready ✅

- API is incomplete ❌

- Security testing not done ❌

- Error handling missing ❌

- Documentation missing ❌

Can we release it?

No.

Agile needs a common agreement:

"What does complete actually mean?"

This is the purpose of Definition of Done (DoD).

2. Definition of Done (DoD)

What is Definition of Done?

Definition of Done is a checklist that defines the quality standard a product increment must satisfy before it can be considered complete.

It applies to:

- User stories

- Features

- Product increments

Simple Definition:

"A user story is Done only when it is developed, tested, reviewed and ready for release."

3. Example: Login Feature Definition of Done

User Story:

As a user, I want to login securely so that I can access my account.

Definition of Done:

✅ UI completed
✅ Backend API completed
✅ Database integration completed
✅ Unit testing completed
✅ Security testing completed
✅ Acceptance criteria passed
✅ Code review completed
✅ Documentation updated
✅ Product Owner approval received

Only then:

Story = Done

4. Definition of Ready (DoR)

What is Definition of Ready?

Definition of Ready defines whether a user story is prepared enough to enter a sprint.

Before development starts, the team asks:

"Is this story clear enough to work on?"

Example: Story Before Sprint

Bad Story:

❌

"Improve reporting system"

Problems:

- What improvement?

- Who needs it?

- What is expected?

Not Ready.

Good Story:

✅

"As a PV associate, I want to export safety cases into Excel so that I can share reports with regulatory teams."

Ready because:

✔ User identified
✔ Business value clear
✔ Acceptance criteria available
✔ Dependencies identified
✔ Estimate completed

5. Definition of Ready Checklist

A user story is Ready when:

1. User Story Written

Example:

"As a customer, I want..."

2. Business Value Defined

Why is this needed?

Example:

"Reduce manual case processing time."

3. Acceptance Criteria Added

Example:

Given a PDF is uploaded:

When AI extraction runs:

Then patient and drug information should be extracted.

4. Dependencies Identified

Example:

AI extraction requires:

- Document storage

- OCR service

5. Story Estimated

Example:

8 Story Points

6. Team Understands Requirement

Developers and QA agree.

6. Difference Between DoR and DoD

Very common interview question.

| Definition of Ready | Definition of Done |
| --- | --- |
| Before development starts | After development finishes |
| Can we start this? | Can we release this? |
| Story preparation | Quality completion |
| Product Owner responsibility | Whole Scrum Team responsibility |

Simple memory:

READY = Start Line

DONE = Finish Line

7. Acceptance Criteria vs Definition of Done

Another common confusion.

Acceptance Criteria

Specific conditions for one user story.

Example:

Login Story:

Acceptance Criteria:

- User enters valid credentials

- User successfully logs in

- Wrong password shows error

Definition of Done

Applies to all stories.

Example:

Every story must have:

- Testing completed

- Code reviewed

- Documentation updated

Comparison:

| Acceptance Criteria | Definition of Done |
| --- | --- |
| Story-specific | Entire product standard |
| Written by Product Owner/BA | Created by Scrum Team |
| Defines functionality | Defines quality |

8. Real Example: AI Pharmacovigilance Platform

User Story:

As a Pharmacovigilance Associate, I want AI to extract adverse events from reports so that I can process cases faster.

Acceptance Criteria:

Scenario 1: Successful Extraction

Given:

A valid safety report PDF is uploaded

When:

AI extraction is triggered

Then:

System should extract:

- Patient details

- Drug name

- Adverse event

- Seriousness

Scenario 2: Invalid Document

Given:

A corrupted file is uploaded

When:

Extraction starts

Then:

System should show an error message.

Definition of Done:

Before marking complete:

✅ AI model integrated
✅ Extraction tested
✅ Accuracy checked
✅ UI completed
✅ Errors handled
✅ QA approval received
✅ Audit logging implemented

9. Agile Quality Gate

Think of DoD as a quality gate:

User Story

|

↓

Development

|

↓

Testing

|

↓

Code Review

|

↓

Acceptance Criteria Passed

|

↓

Definition of Done

|

↓

Release Ready

10. Role of BA in DoR and DoD

For Business Analyst:

Creating DoR:

BA ensures:

- Requirement clarity

- User story quality

- Business rules defined

- Acceptance criteria written

Supporting DoD:

BA verifies:

- Requirements fulfilled

- Acceptance criteria passed

- Business validation completed

11. Interview Questions

Q1. What is Definition of Done?

Answer:

"Definition of Done is a shared checklist created by the Scrum Team that defines all quality criteria required before a user story can be considered complete."

Q2. Difference between Acceptance Criteria and DoD?

Answer:

"Acceptance criteria define what functionality a specific story should deliver, while Definition of Done defines the overall quality standard applicable to all stories."

Q3. Can a developer mark a story Done if testing is incomplete?

Answer:

No.

Because testing is part of Definition of Done.

12. Practical Exercise

For your AI Pharmacovigilance Platform, create:

User Story:

"As a PV reviewer, I want duplicate cases detected automatically so that duplicate safety reports are avoided."

Create:

Acceptance Criteria:

Definition of Done:

Key Takeaways

After Lesson 41, you should understand:

✅ How Agile decides when work can start
✅ How Agile decides when work is complete
✅ Difference between DoR, DoD and Acceptance Criteria
✅ How BA ensures quality requirements

Lesson 41a – Definition of Ready (DoR) vs Definition of Done (DoD)

Learning Objectives

By the end of this lesson, you will understand:

- What is Definition of Ready (DoR)?

- Why DoR is important

- Scrum Guide's view on DoR

- What is Definition of Done (DoD)?

- Why DoD is mandatory

- Difference between DoR and DoD

- Creating effective DoR & DoD checklists

- Healthcare examples

- Pharmacovigilance examples

- AI Product examples

- Common mistakes

- Best Practices

- Interview Questions

- Mini Quiz

- Practical Assignment

1. Introduction

One of the biggest reasons Scrum teams fail is not poor coding—it is unclear requirements and unfinished work.

Imagine this scenario:

A Product Owner says:

"Build an AI feature."

Developers ask:

- Which AI model?

- What should it predict?

- Which users?

- Which data?

- How will we test it?

Nobody knows.

The Sprint begins anyway.

Result?

- Confusion

- Rework

- Missed Sprint Goal

Scrum solves this problem using two important concepts:

- Definition of Ready (DoR)

- Definition of Done (DoD)

Think of them as two quality gates.

Idea

↓

Definition of Ready

↓

Development

↓

Definition of Done

↓

Working Increment

2. What is Definition of Ready (DoR)?

Definition of Ready is a checklist that determines whether a Product Backlog Item is ready to enter a Sprint.

Simple meaning:

"Can developers start working on this story without confusion?"

If the answer is No, it is not Ready.

3. Scrum Guide and Definition of Ready

An important interview point.

Unlike Definition of Done,

Definition of Ready is NOT officially defined in the Scrum Guide.

Why?

Because every organization is different.

Some companies use it.

Some don't.

Scrum Teams may create their own Ready criteria if it helps improve delivery.

4. Why Do We Need Definition of Ready?

Without DoR:

Developer:

"What exactly should I build?"

Product Owner:

"I'll explain later."

Developer:

"What is the acceptance criteria?"

PO:

"We'll decide during development."

Result:

- Delays

- Scope changes

- Frustration

DoR avoids this.

5. Typical Definition of Ready Checklist

A User Story may be considered "Ready" if:

✔ Business value is understood

✔ Acceptance Criteria are written

✔ Dependencies identified

✔ UI/UX available (if needed)

✔ Technical questions answered

✔ Story is estimated

✔ Small enough for one Sprint

✔ Required APIs are available

✔ Stakeholders agree

✔ No blockers remain

6. Example of a Ready Story

Story

"As a doctor, I want to search patient history."

Acceptance Criteria

- Search by Patient ID

- Search by Name

- Response within 2 seconds

- Results paginated

Estimated?

Yes

Dependencies?

Available

Design?

Completed

Ready?

Yes

7. Example of a Story NOT Ready

Story

"Improve AI."

Questions

Improve what?

Accuracy?

Speed?

Model?

UI?

Business objective?

Unknown.

Ready?

No.

8. What is Definition of Done (DoD)?

Definition of Done is a shared checklist that determines when work is truly complete.

Simple Meaning

"Can we confidently say this work is finished?"

If not,

It is NOT Done.

9. Scrum Guide Definition

The Scrum Guide states:

The Definition of Done is a formal description of the state of the Increment when it meets the quality measures required for the product.

Every Increment must satisfy the Definition of Done.

10. Why DoD is Mandatory

Without DoD

Developer:

"My coding is finished."

Tester:

"I haven't tested it."

DevOps:

"It isn't deployed."

Security:

"No review done."

Product Owner:

"I cannot accept this."

Is it Done?

No.

DoD ensures everyone has the same understanding.

11. Typical Definition of Done Checklist

A Product Backlog Item is Done only if:

✔ Code completed

✔ Code reviewed

✔ Unit tests passed

✔ Integration tests passed

✔ Security review completed

✔ Documentation updated

✔ UI approved

✔ Performance acceptable

✔ Product Owner accepts

✔ Deployed to agreed environment

12. Example

Story

"Upload Medical Report"

Done?

Code written

✔

Testing complete

✔

Security checked

✔

Integrated

✔

Documentation updated

✔

PO accepted

✔

Done?

Yes.

13. Difference Between Ready and Done

| Definition of Ready | Definition of Done |
| --- | --- |
| Before Sprint | End of development |
| Can we start? | Can we finish? |
| Optional in Scrum Guide | Mandatory in Scrum Guide |
| Focus on clarity | Focus on quality |
| Helps planning | Helps delivery |
| Applies to backlog items | Applies to Increment |

Easy way to remember:

Ready = Start

Done = Finish

14. Healthcare Example

Hospital Appointment System

Definition of Ready

- Business requirement approved

- Hospital workflow understood

- UI available

- Doctor confirms requirements

- Story estimated

Development begins.

Definition of Done

- Appointment booking works

- SMS notifications work

- Tests passed

- Security approved

- Documentation complete

Only then is it Done.

15. Pharmacovigilance Example

Story

"As a Safety Officer, I want AI to detect Adverse Events."

Definition of Ready

✔ MedDRA version finalized

✔ Source documents available

✔ AI model selected

✔ Acceptance criteria defined

✔ Dataset available

Development begins.

Definition of Done

✔ AI detects events

✔ Precision >95%

✔ Validation complete

✔ Regulatory documentation complete

✔ Audit logs generated

✔ Product Owner approves

Done.

16. AI Product Example

Story

"AI summarizes clinical reports."

Definition of Ready

- Sample reports available

- LLM selected

- Prompt finalized

- Success metrics defined

Definition of Done

- Summary accuracy >90%

- Hallucination rate acceptable

- Response <5 seconds

- Unit tests passed

- Integrated with product

17. Common Mistakes

Mistake 1

Starting stories without requirements.

Result

Rework.

Mistake 2

Calling coding "Done."

Wrong.

Coding is only one step.

Mistake 3

Every story has different Done criteria.

Wrong.

Definition of Done should be shared across the Scrum Team.

Mistake 4

Making DoR extremely complicated.

Keep it practical.

Mistake 5

Ignoring testing.

Untested software is not Done.

18. Best Practices

✔ Create one shared Definition of Done.

✔ Keep Ready checklist simple.

✔ Review DoD every few months.

✔ Never compromise product quality.

✔ Include security.

✔ Include documentation.

✔ Include automation testing.

✔ Make both checklists visible to the entire team.

19. Interview Questions

Q1. Is Definition of Ready part of the Scrum Guide?

Answer: No. It is an optional practice created by Scrum Teams to improve Sprint Planning and reduce ambiguity.

Q2. Is Definition of Done mandatory?

Answer: Yes. The Scrum Guide requires every Increment to meet the Definition of Done before it is considered complete.

Q3. Who creates Definition of Done?

Answer: The Scrum Team creates and maintains a shared Definition of Done. If organizational standards exist, the Scrum Team incorporates them.

Q4. Can Definition of Done change?

Answer: Yes. It evolves as the team's quality standards and product maturity improve, but it should become more rigorous over time—not weaker.

Q5. Can work be accepted if it doesn't meet the Definition of Done?

Answer: No. Work that does not satisfy the Definition of Done cannot be considered part of the Increment.

20. Agile vs Traditional Approach

| Traditional Development | Scrum |
| --- | --- |
| Testing at the end | Testing throughout the Sprint |
| Documentation later | Documentation included in DoD |
| Quality checked after development | Quality built into every Increment |
| Requirements may remain unclear | DoR improves requirement clarity |

21. Real-World Case Study

AI Pharmacovigilance Platform

A team starts a Sprint to build automatic Serious Adverse Event (SAE) detection.

Without Definition of Ready

- Regulatory rules are incomplete.

- The dataset is missing.

- The confidence threshold isn't defined.

The team spends the first week asking questions instead of developing.

With Definition of Ready

Before Sprint Planning:

- Regulatory definitions are approved.

- The training dataset is available.

- Acceptance criteria specify: Recall ≥ 95% and Precision ≥ 90%.

- Dependencies on the NLP service are confirmed.

Development starts immediately with a shared understanding.

Definition of Done

The feature is complete only when:

- SAE detection works correctly.

- Unit, integration, and validation tests pass.

- Performance targets are met.

- Audit logs are generated.

- Documentation is updated.

- The Product Owner accepts the feature.

The result is a high-quality Increment ready for release when the business decides.

Mini Quiz

- What is the purpose of the Definition of Ready?

- Is Definition of Ready mandatory according to the Scrum Guide?

- Why is the Definition of Done mandatory?

- Can a Product Backlog Item be considered Done if testing is incomplete?

- Which comes first: Definition of Ready or Definition of Done?

Practical Assignment

For your AI Pharmacovigilance Platform:

Part 1 – Create a Definition of Ready

Develop a checklist with at least 10 criteria that every User Story must satisfy before entering a Sprint.

Part 2 – Create a Definition of Done

Develop a checklist with at least 12 quality criteria covering development, testing, security, documentation, regulatory compliance, and Product Owner acceptance.

Part 3 – Evaluate Two User Stories

Take two User Stories from your Product Backlog and determine:

- Are they Ready?

- If not, what information is missing?

- After implementation, do they satisfy your Definition of Done?

Summary

The Definition of Ready ensures that work entering a Sprint is clear, well-understood, and actionable. Although it is not prescribed by the Scrum Guide, it is a widely adopted practice that reduces uncertainty and improves Sprint Planning.

The Definition of Done is an essential Scrum artifact that defines the quality standard every Increment must meet before it is considered complete. Together, DoR and DoD help Scrum Teams deliver predictable, high-quality software while minimizing rework.

Key Takeaways

- Definition of Ready answers: "Can we start?"

- Definition of Done answers: "Can we finish?"

- DoR is optional but highly recommended.

- DoD is mandatory in Scrum.

- Every Increment must satisfy the Definition of Done.

- Strong DoR reduces ambiguity; strong DoD ensures quality.

- In regulated industries such as healthcare and pharmacovigilance, well-defined DoR and DoD are critical for compliance, traceability, and reliable product delivery.

Lesson 42: Agile Metrics & Reporting – Burndown, Burnup, Velocity, CFD, Lead Time & Cycle Time

Agile teams do not manage projects only by opinions. They use metrics to understand:

- Are we progressing?

- Are we delivering value?

- Are there bottlenecks?

- Can we improve our process?

For a Business Analyst / Product Manager, understanding Agile metrics is essential because you will often work with dashboards, sprint reports and stakeholder communication.

1. What are Agile Metrics?

Agile metrics are measurements used to track:

- Team performance

- Delivery progress

- Product health

- Process efficiency

Important Agile metrics:

- Velocity

- Sprint Burndown Chart

- Burnup Chart

- Cumulative Flow Diagram

- Lead Time

- Cycle Time

- Release Progress

2. Velocity

Definition

Velocity measures how many story points a Scrum team completes in a sprint.

Formula:

Velocity =

Completed Story Points per Sprint

Example

Sprint history:

| Sprint | Completed Points |
| --- | --- |
| Sprint 1 | 20 |
| Sprint 2 | 25 |
| Sprint 3 | 30 |
| Sprint 4 | 28 |

Average Velocity:

(20 + 25 + 30 + 28) / 4

= 25.75

Future planning:

Team can expect around:

≈ 26 points per sprint

Product Manager Usage

Velocity helps answer:

"How much can we deliver in the next release?"

Example:

Remaining backlog:

260 points

Team velocity:

26 points/sprint

Estimated:

260 / 26 = 10 sprints

3. Sprint Burndown Chart

Definition

A Burndown Chart shows:

Remaining work versus remaining time in a sprint.

It answers:

"Are we on track to complete the sprint?"

Example:

Sprint duration:

10 days

Work:

50 story points

Ideal:

Day 1 → 50 points

Day 5 → 25 points

Day 10 → 0 points

Actual:

Day 5 → 40 points

Meaning:

Team is behind schedule.

Burndown Chart Interpretation

Healthy Sprint

Work gradually decreases.

50

|

40

|

30

|

20

|

10

|

0

---------

Day 1     Day 10

Problem Situation

No progress until last days.

Possible reasons:

- Stories too large

- Blockers

- Testing delay

4. Burnup Chart

Definition

Burnup Chart shows:

- Completed work

- Total scope

Difference:

Burndown:

Focuses on remaining work.

Burnup:

Focuses on completed work and scope changes.

Example:

Original scope:

100 points

Completed:

60 points

New requirements added:

+30 points

Total scope:

130 points

Burnup clearly shows scope increase.

5. Burndown vs Burnup

| Burndown | Burnup |
| --- | --- |
| Remaining work | Completed work |
| Tracks progress | Tracks achievement |
| Shows scope problems less clearly | Shows scope changes clearly |
| Common in Scrum | Useful for stakeholders |

6. Cumulative Flow Diagram (CFD)

Definition

CFD shows how work moves through different stages.

Example workflow:

Backlog

↓

Development

↓

Testing

↓

Done

Example:

| Stage | Items |
| --- | --- |
| Backlog | 20 |
| Development | 8 |
| Testing | 5 |
| Done | 40 |

Why CFD is Useful?

It identifies bottlenecks.

Example:

Testing increases:

Development     █████

Testing         █████████████

Done            ███

Meaning:

Too many items waiting for QA.

Action:

- Add testers

- Improve automation

- Reduce WIP

7. Lead Time

Definition

Lead Time measures:

Total time from customer request until delivery.

Formula:

Lead Time =

Request Created → Delivered

Example:

Customer requests feature:

1 January

Feature released:

20 January

Lead Time:

19 days

Product Manager cares about:

"How quickly can we deliver customer value?"

8. Cycle Time

Definition

Cycle Time measures:

Time taken after work starts until completion.

Formula:

Cycle Time =

Development Started → Done

Example:

Feature approved:

1 January

Development starts:

5 January

Completed:

15 January

Cycle Time:

10 days

Lead Time vs Cycle Time

Very common interview question.

| Lead Time | Cycle Time |
| --- | --- |
| Customer perspective | Team perspective |
| Request to delivery | Start to completion |
| Includes waiting time | Only active work |

Example:

Customer requests:

1 Jan

Developer starts:

10 Jan

Completed:

20 Jan

Lead Time:

19 days

Cycle Time:

10 days

9. Release Burndown

Used for larger products.

Example:

Product backlog:

500 points

Release goal:

3 months

Tracks:

How much remains before launch.

10. Agile Dashboard Example

For your AI Pharmacovigilance Platform:

Sprint Dashboard

Sprint 5

Velocity:

32 points

Completed:

28 points

Remaining:

4 points

Bugs:

5

Lead Time:

8 days

Cycle Time:

4 days

Sprint Goal:

AI Case Extraction Module

11. Metrics for Product Managers

A Product Manager focuses on:

Delivery Metrics

- Velocity

- Release progress

- Sprint completion

Efficiency Metrics

- Lead time

- Cycle time

- Throughput

Quality Metrics

- Defects

- Production issues

- Rework percentage

Customer Metrics

- User adoption

- Satisfaction score

- Feature usage

12. Common Mistakes

Mistake 1:

Using velocity to compare teams.

Wrong:

"Team A has 50 velocity, Team B has 30, so Team A is better."

Why wrong?

Different teams estimate differently.

Mistake 2:

Optimizing only speed.

Fast delivery with poor quality creates:

- Bugs

- Customer complaints

- Rework

Mistake 3:

Ignoring bottlenecks.

Example:

Developers finish work quickly but QA cannot test.

Solution:

Improve entire flow.

13. Interview Questions

Q1. What is velocity?

Answer:

"Velocity measures the amount of work a Scrum team completes in a sprint using story points. It is used for forecasting future capacity."

Q2. Difference between lead time and cycle time?

Answer:

"Lead time measures the total time from customer request to delivery, while cycle time measures the time from when work begins until completion."

Q3. Why use CFD?

Answer:

"A cumulative flow diagram helps identify bottlenecks by showing how work moves through different stages."

Practical Exercise

For your AI Pharmacovigilance Platform, imagine:

Sprint:

10 days

Backlog:

40 points

Completed:

25 points

Answer:

- What is remaining work?

- What will the burndown show?

- If customer adds 15 new points, which chart shows scope change better?

- A case processing feature requested on 1 July and delivered on 20 July. Calculate Lead Time.

- Development started on 10 July and finished on 20 July. Calculate Cycle Time.

Lesson 42a – Burndown Chart & Burnup Chart (Advanced Scrum Tracking)

Learning Objectives

By the end of this lesson, you will understand:

- What is a Burndown Chart?

- What is a Burnup Chart?

- History of Agile Charts

- Sprint Burndown Chart

- Release Burndown Chart

- Sprint Burnup Chart

- Release Burnup Chart

- Burndown vs Burnup

- How to create Burndown Charts

- How to interpret Burndown Charts

- Common Burndown Patterns

- Scope Change

- Ideal Line vs Actual Line

- Healthcare examples

- Pharmacovigilance examples

- AI Product examples

- Common mistakes

- Best Practices

- Interview Questions

- Mini Quiz

- Practical Assignment

1. Introduction

Imagine you're driving from Delhi to Mumbai.

You constantly check:

- How much distance remains?

- How much distance has been covered?

- Are you ahead of schedule?

- Are you delayed?

Without these measurements, it's difficult to know whether you'll arrive on time.

Software projects face the same challenge.

Managers need answers to questions like:

- Are we on track?

- Will we finish the Sprint?

- Are we falling behind?

- Has the project scope increased?

Scrum answers these questions using Burndown and Burnup Charts.

2. What is a Burndown Chart?

A Burndown Chart is a graphical representation showing how much work remains over time.

It answers one simple question:

"How much work is left?"

As work is completed, the remaining work "burns down" toward zero.

3. Scrum Guide Perspective

The Scrum Guide does not require Burndown or Burnup Charts.

They are optional Agile tracking tools.

Many Scrum Teams use them because they provide excellent visibility into Sprint progress.

4. What is a Burnup Chart?

A Burnup Chart shows how much work has been completed over time.

Unlike Burndown, Burnup also displays total project scope.

This makes Burnup especially useful when scope changes frequently.

5. Burndown vs Burnup

| Burndown | Burnup |
| --- | --- |
| Shows remaining work | Shows completed work |
| Ends at zero | Ends at total scope |
| Scope changes are less obvious | Scope changes are clearly visible |
| Easier to read | Better for changing requirements |

Easy Memory Trick

Burndown → Remaining Work ↓

Burnup → Completed Work ↑

6. Sprint Burndown Chart

A Sprint Burndown tracks progress within a single Sprint.

Example

Sprint

10 Days

Total Work

40 Story Points

Day 1

40 Remaining

Day 2

36 Remaining

Day 3

31 Remaining

...

Day 10

0 Remaining

The goal is to reach zero remaining work by the end of the Sprint.

7. Sprint Burndown Example

| Day | Remaining Story Points |
| --- | --- |
| 1 | 40 |
| 2 | 36 |
| 3 | 32 |
| 4 | 30 |
| 5 | 24 |
| 6 | 20 |
| 7 | 15 |
| 8 | 10 |
| 9 | 5 |
| 10 | 0 |

Notice:

The remaining work continuously decreases.

This indicates healthy Sprint progress.

8. Burndown Visualization

Story Points

40 |●

35 | ●

30 |  ●

25 |    ●

20 |      ●

15 |         ●

10 |            ●

5 |               ●

0 |_______________________________

1 2 3 4 5 6 7 8 9 10

Sprint Days

The line moves downward toward zero.

9. Ideal Line vs Actual Line

Every Burndown Chart usually contains two lines.

Ideal Line

Represents perfectly even progress.

Actual Line

Represents real team progress.

Example

Ideal

40

35

30

25

20

15

10

5

0

Actual

40

39

38

34

27

20

18

9

4

0

Differences help identify risks early.

10. Interpreting Burndown Charts

Actual Above Ideal

Remaining work is higher than expected.

Possible reasons:

- Delays

- Blockers

- Underestimation

Actual Below Ideal

Team is ahead of schedule.

Possible reasons:

- Excellent collaboration

- Easier stories

- Conservative estimates

Actual Matches Ideal

Sprint is progressing as expected.

11. Common Burndown Patterns

Healthy Pattern

Smooth downward trend.

Excellent.

Flat Line

No work completed.

Possible causes:

- Blockers

- Testing delayed

- Stories too large

Sudden Drop

Many stories completed together.

Possible reasons:

- Large stories finished late.

- Team updates tasks infrequently.

Zigzag Pattern

Frequent ups and downs.

May indicate changing scope or inconsistent tracking.

12. Release Burndown Chart

Instead of one Sprint,

Track the entire Product Release.

Example

Product Backlog

240 Story Points

Sprint 1

220 Remaining

Sprint 2

190 Remaining

Sprint 3

160 Remaining

Eventually

0 Remaining

Useful for long-term release planning.

13. Burnup Chart

Burnup tracks:

Completed Story Points

Instead of

Remaining Story Points.

Example

| Sprint | Completed |
| --- | --- |
| 1 | 20 |
| 2 | 45 |
| 3 | 68 |
| 4 | 92 |
| 5 | 120 |

The line continuously moves upward.

14. Burnup Visualization

Story Points

120 |                     ●

100 |                 ●

80 |             ●

60 |         ●

40 |     ●

20 | ●

0 |__________________________

Sprint Progress

15. Why Burnup is Better for Scope Changes

Suppose

Original Scope

120 Story Points

Halfway through,

Customer adds

40 Story Points.

Burndown

Looks confusing.

Burnup

Shows:

Completed Work Line

AND

Scope Line

The increase in scope becomes immediately visible.

16. Scope Change Example

Original Scope

100 Points

New Requirement

+30 Points

Burnup

Scope Line jumps

100 →130

Completed Line continues upward.

Managers instantly understand:

Project isn't slower.

Project became larger.

17. Healthcare Example

Hospital Management System

Sprint Goal

Appointment Booking

Burndown shows

Remaining work reduces steadily.

Mid-Sprint

Government mandates OTP verification.

Scope increases.

Burnup clearly displays the scope increase, helping stakeholders understand why more work remains.

18. Pharmacovigilance Example

AI Drug Safety Platform

Sprint Goal

Automatic ICSR Classification.

During Sprint

New regulatory rule requires:

Reporter qualification extraction.

Burnup Chart

Scope Line increases.

Completed Line continues upward.

The Product Owner explains the impact using the Burnup Chart.

19. AI Product Example

Medical AI Assistant

Original Scope

Voice Support

During Sprint

Doctors request multilingual support.

Scope expands.

Burnup immediately visualizes the increased scope while still showing development progress.

20. Burndown vs Burnup Comparison

| Situation | Better Chart |
| --- | --- |
| Stable Sprint Scope | Burndown |
| Frequent Scope Changes | Burnup |
| Simple Sprint Tracking | Burndown |
| Product Roadmap Tracking | Burnup |
| Executive Reporting | Burnup |

21. Common Mistakes

Mistake 1

Updating charts only at Sprint end.

Charts should be updated daily or whenever work status changes.

Mistake 2

Counting incomplete stories.

Only Done work should affect Story Point progress.

Mistake 3

Using charts to judge individual developers.

Charts measure team progress.

Mistake 4

Ignoring scope changes.

Scope changes should be transparent.

Mistake 5

Focusing only on charts.

Charts support conversations—they do not replace them.

22. Best Practices

✔ Update charts daily.

✔ Compare Actual vs Ideal.

✔ Discuss deviations during Daily Scrum.

✔ Use Burnup for changing scope.

✔ Never manipulate Story Points.

✔ Focus on trends instead of single days.

✔ Combine charts with Sprint Goal discussions.

✔ Review charts during Sprint Review.

23. Burndown and Velocity

Many beginners confuse these concepts.

| Burndown | Velocity |
| --- | --- |
| Daily progress | Sprint outcome |
| Remaining work | Completed Story Points |
| Updated during Sprint | Calculated after Sprint |
| Detects delays | Forecasts future work |

Both complement each other.

24. Interview Questions

Q1. What is a Burndown Chart?

Answer: A Burndown Chart shows the amount of remaining work over time during a Sprint or Release.

Q2. What is a Burnup Chart?

Answer: A Burnup Chart shows completed work over time while also displaying the total project scope.

Q3. Which chart is better when project scope changes frequently?

Answer: Burnup Charts, because they separately display completed work and total scope.

Q4. What does a flat Burndown Chart indicate?

Answer: Little or no work has been completed, possibly due to blockers, oversized stories, or delayed testing.

Q5. Should Burndown Charts be used to evaluate individual performance?

Answer: No. They are team-level progress tracking tools and should never be used to measure individual productivity.

25. Real-World Case Study

AI Pharmacovigilance Platform

Sprint Duration

10 Working Days

Sprint Commitment

40 Story Points

Daily Burndown

| Day | Remaining SP |
| --- | --- |
| 1 | 40 |
| 2 | 38 |
| 3 | 34 |
| 4 | 30 |
| 5 | 24 |
| 6 | 21 |
| 7 | 17 |
| 8 | 10 |
| 9 | 4 |
| 10 | 0 |

During Day 5, regulators introduce a new compliance requirement:

- Capture reporter qualification.

- Validate country information.

The Product Owner adds 6 Story Points to the Product Backlog for a future Sprint instead of disrupting the current Sprint Goal.

The Burndown remains stable, while the Release Burnup Chart reflects the increased total scope.

This allows stakeholders to distinguish between:

- Reduced team performance ❌

- Increased project scope ✅

26. Advanced Burndown Analysis

Experienced Scrum Teams don't just look at the chart—they analyze patterns.

Pattern 1 – Hockey Stick

Most work is completed near the end of the Sprint.

Possible causes:

- Testing delayed until the end.

- Stories too large.

- Late integration.

Pattern 2 – Stair-Step Pattern

Large drops followed by flat periods.

Possible causes:

- Developers close multiple stories at once.

- Work is not integrated continuously.

Pattern 3 – Smooth Decline

Small, regular decreases.

This usually indicates:

- Well-sized User Stories.

- Continuous integration.

- Frequent testing.

- Good Sprint management.

Mini Quiz

- What does a Burndown Chart measure?

- What does a Burnup Chart measure?

- Which chart better handles scope changes?

- What does a flat Burndown trend usually indicate?

- Why should Burndown Charts be updated frequently?

Practical Assignment

For your AI Pharmacovigilance Platform:

Part 1 – Create a Sprint Burndown

Assume:

- Sprint Length: 10 Days

- Total Commitment: 36 Story Points

Create a daily Burndown table showing remaining Story Points.

Part 2 – Analyze the Burndown

Assume:

- No stories completed during Days 1–3.

- Large Story completed on Day 8.

Identify:

- Risks

- Root causes

- Improvement actions

Part 3 – Create a Burnup Chart

Assume:

- Original Scope: 100 Story Points

- New Regulatory Requirement: +20 Story Points after Sprint 3

Create:

- Scope Line

- Completed Work Line

Explain how the Burnup Chart helps stakeholders understand the project status.

Part 4 – Dashboard Design Challenge

Design a Scrum Dashboard containing:

- Sprint Burndown

- Release Burnup

- Velocity Trend

- Sprint Goal Status

- Team Capacity

- Open Impediments

Describe what each visualization tells the Scrum Team and stakeholders.

Summary

Burndown and Burnup Charts are visual management tools that improve transparency throughout a Sprint and across a product release. Burndown focuses on remaining work, while Burnup focuses on completed work and total scope. Together, they help Scrum Teams identify risks early, communicate progress effectively, and make informed decisions when priorities or scope change.

Key Takeaways

- Burndown Charts track remaining work over time.

- Burnup Charts track completed work and total scope.

- Burndown is ideal for monitoring Sprint progress.

- Burnup is especially valuable when requirements or scope change frequently.

- These charts support inspection and adaptation but do not replace team conversations.

- Burndown, Burnup, Velocity, and Capacity together provide a comprehensive view of Scrum delivery performance.

Lesson 42b – Sprint Metrics (Advanced Scrum Analytics & KPIs)

Learning Objectives

By the end of this lesson, you will understand:

- What are Sprint Metrics?

- Why Sprint Metrics matter

- Agile Metrics vs Traditional KPIs

- Velocity

- Sprint Predictability

- Lead Time

- Cycle Time

- Throughput

- Work In Progress (WIP)

- Work Item Age

- Flow Efficiency

- Escaped Defects

- Defect Density

- Rework Percentage

- Customer Satisfaction (CSAT)

- Net Promoter Score (NPS)

- Sprint Goal Success Rate

- Cumulative Flow Diagram (CFD)

- DORA Metrics (Introduction)

- Metric Anti-patterns

- Healthcare examples

- Pharmacovigilance examples

- AI Product examples

- Best Practices

- Interview Questions

- Mini Quiz

- Practical Assignment

1. Introduction

Imagine you're managing a hospital.

Would you judge its performance using only:

- Number of doctors?

Of course not.

You would also measure:

- Patient waiting time

- Recovery rate

- Infection rate

- Patient satisfaction

- Readmission rate

Because one metric never tells the full story.

The same principle applies to Scrum.

Velocity alone cannot tell whether a Scrum Team is healthy.

You need multiple metrics.

2. What are Sprint Metrics?

Sprint Metrics are measurable indicators that help Scrum Teams understand:

- Progress

- Delivery speed

- Product quality

- Customer value

- Process efficiency

- Team predictability

Good metrics help teams improve.

Bad metrics encourage manipulation.

3. Why Do Sprint Metrics Matter?

Without metrics

The team relies on opinions.

With metrics

The team uses evidence.

Metrics answer questions like:

- Are we improving?

- Are customers happier?

- Are we delivering faster?

- Are defects decreasing?

- Are Sprints becoming predictable?

4. Agile Metrics vs Traditional KPIs

| Traditional KPI | Agile Metric |
| --- | --- |
| Hours Worked | Customer Value Delivered |
| Individual Productivity | Team Performance |
| Tasks Completed | Working Software |
| Budget Spent | Sprint Goal Achievement |
| Utilization | Flow Efficiency |

Agile measures outcomes, not just activity.

5. Velocity (Review)

Velocity

= Completed Story Points per Sprint.

Purpose

Forecast future work.

Not

Developer performance.

6. Sprint Predictability

Sprint Predictability measures:

Did the team complete what it committed?

Formula

Completed Story Points

----------------------- ×100

Committed Story Points

Example

Committed

40

Completed

36

Predictability

36 ÷ 40

= 90%

Healthy teams generally aim for consistent predictability rather than perfection.

7. Lead Time

Lead Time answers:

"How long does the customer wait?"

Definition

Time from

Customer Request

to

Delivery.

Example

Customer requests feature

January 1

Delivered

January 20

Lead Time

20 Days

Lower Lead Time means customers receive value faster.

8. Cycle Time

Cycle Time answers:

"How long did development actually take?"

Definition

Time from

Work Started

to

Work Completed.

Example

Started

January 10

Finished

January 20

Cycle Time

10 Days

9. Lead Time vs Cycle Time

Customer Request

│

│

▼

Lead Time Starts

│

│

Work Begins

│

▼

Cycle Time Starts

│

Development

│

Testing

│

Deployment

▼

Delivered

│

Lead Time Ends

Cycle Time Ends

Simple Memory Trick

Lead Time

Customer perspective

Cycle Time

Team perspective

10. Throughput

Throughput measures

Number of work items completed.

Example

Sprint

Completed

18 User Stories.

Throughput

18

It measures quantity,

not size.

11. Work In Progress (WIP)

Definition

Number of work items currently being worked on.

Example

Developer A

2 Stories

Developer B

3 Stories

Developer C

1 Story

Current WIP

6

Lower WIP generally improves focus and flow.

12. Work Item Age

Measures

How long an unfinished task has existed.

Example

Story started

5 Days ago

Still not Done

Work Item Age

5 Days

Large Work Item Age usually indicates a blocker.

13. Flow Efficiency

Definition

Actual work time

÷

Total elapsed time

Example

Working Time

6 Hours

Waiting Time

18 Hours

Elapsed Time

24 Hours

Flow Efficiency

6 ÷ 24

= 25%

Higher Flow Efficiency means less waiting.

14. Escaped Defects

Escaped Defects are bugs found after release.

Example

Hospital App

Patient data exported incorrectly.

Bug discovered by customers.

Escaped Defect.

Lower is better.

15. Defect Density

Formula

Number of Defects

-----------------

Software Size

Often measured per:

- Story

- Feature

- Module

- 1,000 Lines of Code (where applicable)

Lower Defect Density generally indicates higher quality.

16. Rework Percentage

Measures

How much effort is spent fixing existing work instead of creating new value.

Example

Sprint Effort

100 Hours

Bug Fixes

20 Hours

Rework

20%

Lower Rework allows more time for innovation.

17. Sprint Goal Success Rate

Formula

Successful Sprints

------------------

Total Sprints

Example

20 Sprints

18 Goals achieved

Success Rate

90%

This metric is often more meaningful than simply counting completed Story Points.

18. Customer Satisfaction (CSAT)

Measures customer happiness.

Example Survey

Rate your satisfaction

1–5

Average

4.6

Excellent.

19. Net Promoter Score (NPS)

Question

"How likely are you to recommend this product?"

Score

0–10

Promoters

9–10

Passives

7–8

Detractors

0–6

Formula

NPS = % Promoters − % Detractors

20. Cumulative Flow Diagram (CFD)

A CFD shows

Work Items in each workflow stage.

Example

Done

──────────────

Testing

──────────────

Development

──────────────

To Do

──────────────

Time →

Benefits

- Detect bottlenecks

- Visualize WIP

- Analyze workflow stability

- Improve delivery flow

21. DORA Metrics (Introduction)

Widely used for DevOps and Agile teams.

The four key DORA Metrics are:

| Metric | Purpose |
| --- | --- |
| Deployment Frequency | How often software is deployed |
| Lead Time for Changes | Speed of delivering changes |
| Change Failure Rate | Percentage of deployments causing failures |
| Mean Time to Recovery (MTTR) | Recovery speed after incidents |

Many modern Product Managers understand these metrics when working with engineering teams.

22. Healthcare Example

Hospital Appointment System

Metrics

Sprint Predictability

92%

Lead Time

12 Days

Escaped Defects

1

CSAT

4.8/5

Management concludes:

Delivery is reliable.

Quality is high.

23. Pharmacovigilance Example

AI Drug Safety Platform

Sprint Metrics

Velocity

38

Cycle Time

4 Days

Lead Time

8 Days

Escaped Defects

0

Flow Efficiency

82%

Regulatory compliance improved.

24. AI Product Example

Medical AI Assistant

Metrics

Customer Satisfaction

4.7

Prompt Accuracy

96%

Cycle Time

3 Days

Deployment Frequency

Daily

Product team uses these metrics to guide improvements rather than relying on intuition.

25. Metric Anti-Patterns

Anti-pattern 1

Using Velocity to evaluate developers.

Wrong.

Velocity is a team metric.

Anti-pattern 2

Optimizing one metric only.

Example

Higher Velocity

but

Poor Quality.

Anti-pattern 3

Gaming metrics.

Inflating Story Points.

Closing incomplete tasks.

Ignoring bugs.

Anti-pattern 4

Measuring too many metrics.

Teams lose focus.

Measure what drives decisions.

Anti-pattern 5

Ignoring customer outcomes.

Fast delivery means little if customers receive no value.

26. Best Practices

✔ Use metrics to improve, not punish.

✔ Measure trends over time.

✔ Combine quantitative and qualitative feedback.

✔ Track customer outcomes.

✔ Review metrics every Sprint Review and Retrospective.

✔ Keep dashboards simple.

✔ Focus on actionable insights.

✔ Never optimize one metric at the expense of others.

27. Agile Dashboard Example

A mature Scrum Dashboard might include:

| Metric | Current Value |
| --- | --- |
| Velocity | 34 SP |
| Sprint Predictability | 92% |
| Cycle Time | 3.8 Days |
| Lead Time | 8.4 Days |
| Throughput | 15 Stories |
| WIP | 7 Items |
| Escaped Defects | 1 |
| CSAT | 4.7/5 |
| Sprint Goal Success | 95% |

This gives stakeholders a balanced view of delivery, quality, and customer satisfaction.

28. Interview Questions

Q1. What is Sprint Predictability?

Answer: Sprint Predictability measures how closely the team delivered against its Sprint commitment.

Q2. What is the difference between Lead Time and Cycle Time?

Answer: Lead Time measures the total time from customer request to delivery, while Cycle Time measures only the time from when work begins until it is completed.

Q3. What are Escaped Defects?

Answer: Defects discovered by users or customers after a product has been released.

Q4. What is Throughput?

Answer: Throughput is the number of work items completed during a specific period.

Q5. Why shouldn't Velocity be used as a KPI?

Answer: Because it is a team-specific planning metric and using it as a performance target often leads to inflated estimates and poor behaviors.

29. Real-World Case Study

AI Pharmacovigilance Platform

The Scrum Team tracks the following metrics over six Sprints.

| Metric | Value |
| --- | --- |
| Average Velocity | 36 SP |
| Sprint Predictability | 91% |
| Lead Time | 9 Days |
| Cycle Time | 4 Days |
| Throughput | 14 Stories/Sprint |
| Escaped Defects | 0 |
| CSAT | 4.8/5 |
| Sprint Goal Success | 100% |

Insights

- Stable Velocity supports accurate release forecasting.

- High Sprint Predictability indicates realistic Sprint Planning.

- Short Cycle Time enables faster feature delivery.

- Zero Escaped Defects demonstrates effective testing.

- High CSAT confirms that delivered features provide customer value.

During the Sprint Retrospective, the team identifies one opportunity for improvement:

Although delivery metrics are strong, Work In Progress occasionally becomes too high during the first week of the Sprint.

Action:

Introduce a WIP limit of two active User Stories per developer.

Expected Result:

- Improved Flow Efficiency.

- Lower Cycle Time.

- Faster feedback.

- Reduced context switching.

30. Building a Product Manager KPI Dashboard

As a Product Manager, you should avoid relying on a single metric.

A balanced dashboard might include four categories:

Delivery

- Velocity

- Sprint Predictability

- Throughput

Flow

- Lead Time

- Cycle Time

- WIP

- Flow Efficiency

Quality

- Escaped Defects

- Defect Density

- Rework Percentage

Customer Value

- CSAT

- NPS

- Sprint Goal Success

- Feature Adoption (if available)

This balanced approach helps ensure that improvements in one area do not come at the expense of another.

Mini Quiz

- What is the difference between Lead Time and Cycle Time?

- What are Escaped Defects?

- Why is Sprint Predictability important?

- What does a Cumulative Flow Diagram help identify?

- Why should Product Managers avoid focusing on only one metric?

Practical Assignment

For your AI Pharmacovigilance Platform:

Part 1 – Build a Scrum Dashboard

Create a dashboard containing:

- Velocity

- Sprint Predictability

- Cycle Time

- Lead Time

- Throughput

- WIP

- Escaped Defects

- CSAT

- Sprint Goal Success

Explain how each metric would influence Product Management decisions.

Part 2 – Analyze Sprint Performance

Assume the following data:

| Metric | Value |
| --- | --- |
| Velocity | 30 SP |
| Sprint Predictability | 75% |
| Cycle Time | 8 Days |
| Lead Time | 15 Days |
| Escaped Defects | 6 |
| CSAT | 3.6/5 |

Identify:

- Three strengths.

- Five improvement opportunities.

- Actions you would discuss during the Sprint Retrospective.

Part 3 – Design Executive KPIs

As a Product Manager, recommend 8–10 metrics you would present monthly to senior leadership. Justify why each metric matters and explain how it supports strategic decision-making.

Part 4 – Reflection

Write a one-page analysis explaining:

"Why metrics should guide conversations rather than become performance targets."

Include examples of how misusing Velocity, Story Points, or Throughput can lead to unintended behaviors.

Summary

Sprint Metrics provide a comprehensive view of a Scrum Team's performance across delivery, flow, quality, and customer value. Rather than relying on a single indicator such as Velocity, high-performing teams monitor a balanced set of metrics—including Lead Time, Cycle Time, Throughput, Sprint Predictability, Escaped Defects, and Customer Satisfaction—to support continuous improvement. The purpose of these metrics is not to judge individuals but to help teams inspect, adapt, and consistently deliver valuable products.

Key Takeaways

- Metrics should enable learning, not drive fear or competition.

- Velocity supports forecasting but should never be used as a productivity KPI.

- Lead Time reflects the customer's experience, while Cycle Time measures delivery efficiency.

- Throughput, WIP, and Flow Efficiency help optimize workflow.

- Escaped Defects, Defect Density, and Rework Percentage indicate product quality.

- CSAT and NPS measure whether the product is creating value for customers.

- A balanced Product Management dashboard combines delivery, flow, quality, and customer outcome metrics.

- The best Scrum Teams use metrics to ask better questions, make better decisions, and continuously improve—not to compare people or inflate performance.