Module 4

Lesson 72 – T-Shirt Sizing (Advanced Agile Estimation Masterclass)

Learning Objectives

By the end of this lesson, you will understand:

- What is T-Shirt Sizing?

- History of T-Shirt Sizing

- Why Agile Teams use T-Shirt Sizing

- T-Shirt Sizes Explained

- T-Shirt Sizing vs Story Points

- T-Shirt Sizing vs Planning Poker

- Relative Estimation

- Mapping T-Shirt Sizes to Story Points

- Team Calibration

- Portfolio Estimation

- Product Roadmap Estimation

- Scaling Agile with T-Shirt Sizing

- Common Mistakes

- Best Practices

- Healthcare Examples

- Pharmacovigilance Examples

- AI Product Examples

- Interview Questions

- Mini Quiz

- Practical Assignment

1. Introduction

Imagine you are asked:

"How much effort is required to build an AI-powered Drug Safety Platform?"

You cannot immediately estimate:

- 384 Story Points

- 672 hours

- 18 weeks

Because there are hundreds of unknowns.

Instead, experienced Product Managers begin with a rough relative estimate.

Just like clothing sizes:

- XS

- S

- M

- L

- XL

Agile teams estimate work the same way.

This technique is called T-Shirt Sizing.

2. What is T-Shirt Sizing?

T-Shirt Sizing is a relative estimation technique where work items are classified into predefined size categories instead of assigning exact numbers.

Instead of saying:

"This feature is 21 Story Points."

The team says:

"This feature is Large."

3. Simple Definition

T-Shirt Sizing estimates the relative size, complexity, effort, and uncertainty of work using clothing sizes.

It is intentionally approximate.

4. Why Use T-Shirt Sizing?

Early in a project:

Requirements are incomplete.

Technical details are unclear.

Dependencies are unknown.

Trying to estimate exact Story Points becomes unreliable.

T-Shirt Sizing allows teams to estimate quickly while acknowledging uncertainty.

5. History

T-Shirt Sizing emerged from Agile planning practices as teams needed a fast way to estimate large backlogs and roadmaps before detailed Sprint Planning.

It is widely used in:

- Scrum

- SAFe

- LeSS

- Spotify Model

- Product Discovery

- Portfolio Management

6. Standard T-Shirt Sizes

Most organizations use:

| Size | Meaning |
| --- | --- |
| XS | Very Small |
| S | Small |
| M | Medium |
| L | Large |
| XL | Very Large |

Some organizations also include:

- XXL

- XXXL

Large items are usually split before development.

7. What Does Size Represent?

A T-Shirt Size reflects a combination of:

- Effort

- Complexity

- Risk

- Uncertainty

- Dependencies

It does not represent time.

8. Example

| Feature | Size |
| --- | --- |
| Change logo | XS |
| Password reset | S |
| Appointment booking | M |
| AI report generation | L |
| Complete Hospital ERP | XL |

Notice:

The estimates are relative rather than precise.

9. Relative Estimation

T-Shirt Sizing compares work items with each other.

Example

If Password Reset = Small

Then

AI Medical Diagnosis

must be much larger.

This comparison is easier than estimating exact hours.

10. T-Shirt Sizes vs Story Points

Many teams later convert sizes into Story Points.

Example Mapping

| T-Shirt | Story Points |
| --- | --- |
| XS | 1 |
| S | 2–3 |
| M | 5–8 |
| L | 13–21 |
| XL | 34–55 |

Important: There is no universal mapping.

Each Scrum Team defines its own calibration.

11. Team Calibration

Calibration ensures everyone interprets sizes consistently.

Example

Reference Stories

| Story | Size |
| --- | --- |
| Login | XS |
| Registration | S |
| Dashboard | M |
| Analytics | L |
| AI Engine | XL |

Future estimates are compared against these reference stories.

12. T-Shirt Sizing vs Story Points

| T-Shirt Sizing | Story Points |
| --- | --- |
| High-level estimation | Sprint estimation |
| Fast | More detailed |
| Used early | Used before Sprint |
| Roadmap planning | Sprint Planning |
| Portfolio planning | Team execution |

13. T-Shirt Sizing vs Planning Poker

| T-Shirt Sizing | Planning Poker |
| --- | --- |
| Very fast | More discussion |
| Approximate | More accurate |
| Good for hundreds of items | Good for Sprint backlog |
| Discovery phase | Delivery phase |

Many teams use:

T-Shirt Sizing

↓

Planning Poker

↓

Story Points

14. Portfolio Estimation

Executives rarely estimate:

500 User Stories.

Instead,

they estimate:

Features

Epics

Initiatives

using T-Shirt Sizes.

This enables roadmap planning months before implementation.

15. Product Roadmap Example

| Initiative | Size |
| --- | --- |
| AI Search | XL |
| Mobile App | L |
| Dark Mode | S |
| Reports | M |
| Notifications | S |

This provides a quick view of delivery effort.

16. Scaling Agile

Frameworks like SAFe commonly use T-Shirt Sizing for:

- Portfolio planning

- Program Increment (PI) planning

- Epic sizing

- Investment decisions

Detailed Story Point estimation happens later at the team level.

17. Converting Large Items

If an item is:

XL

It should usually be:

Split.

Example

Epic

Hospital Management

↓

Features

Appointments

Billing

EMR

Pharmacy

↓

User Stories

↓

Tasks

Large estimates often signal the need for decomposition.

18. Healthcare Example

Hospital Product

Requested Feature

Online Appointment Booking

Discussion

- Moderate workflow

- Payment integration

- Calendar integration

Estimated

Medium

Another Feature

Complete Electronic Medical Record System

Estimated

XL

Needs decomposition.

19. Pharmacovigilance Example

AI Drug Safety Platform

Features

| Feature | Size |
| --- | --- |
| PDF Upload | S |
| OCR | M |
| MedDRA Coding | L |
| Duplicate Detection | XL |
| Regulatory Dashboard | M |

Large items are later broken into multiple User Stories.

20. AI Product Example

Medical AI Assistant

Roadmap

| Feature | Size |
| --- | --- |
| Login | XS |
| Prompt History | S |
| AI Summarization | M |
| Voice Assistant | L |
| Multi-Agent AI Workflow | XL |

The Product Manager uses these estimates to communicate roadmap expectations to stakeholders.

21. Advantages

✔ Extremely fast

✔ Easy to understand

✔ Encourages discussion

✔ Suitable for executives

✔ Excellent for roadmaps

✔ Handles uncertainty well

✔ Reduces false precision

22. Limitations

✖ Less precise than Story Points.

✖ Different teams may interpret sizes differently.

✖ Cannot accurately forecast Sprint capacity without further estimation.

✖ Requires calibration.

23. Common Mistakes

Mistake 1

Treating T-Shirt Sizes as time estimates.

Wrong.

They represent relative size.

Mistake 2

Creating too many size categories.

Keep the scale simple.

Mistake 3

Skipping calibration.

Teams lose consistency.

Mistake 4

Never splitting XL items.

Large items increase delivery risk.

Mistake 5

Converting directly to hours.

T-Shirt Sizing should remain relative.

24. Best Practices

✔ Estimate collaboratively.

✔ Compare with reference stories.

✔ Review calibration regularly.

✔ Split XL initiatives.

✔ Convert to Story Points before Sprint Planning.

✔ Use for Product Discovery and Roadmap planning.

25. Interview Questions

Q1. What is T-Shirt Sizing?

Answer: T-Shirt Sizing is a relative estimation technique that classifies work into categories such as XS, S, M, L, and XL based on effort, complexity, risk, and uncertainty.

Q2. Why is T-Shirt Sizing useful?

Answer: It enables fast, high-level estimation during Product Discovery, Roadmap Planning, and Portfolio Management when detailed information is not yet available.

Q3. How does T-Shirt Sizing differ from Story Points?

Answer: T-Shirt Sizing provides approximate, high-level estimates, while Story Points provide more detailed estimates for Sprint Planning.

Q4. Should T-Shirt Sizes be converted directly into hours?

Answer: No. T-Shirt Sizes are relative estimates and should not be interpreted as time.

Q5. What should teams do with XL items?

Answer: XL items should typically be decomposed into smaller Features, User Stories, or Tasks before implementation.

26. Real-World Case Study

AI Pharmacovigilance Platform

A Product Team is preparing the roadmap for the next six months.

The Product Backlog includes:

| Initiative | Size |
| --- | --- |
| OCR Pipeline | M |
| Duplicate Case Detection | XL |
| AI Causality Assessment | XL |
| Regulatory Dashboard | L |
| Case Search | M |
| Notification Service | S |
| Audit Log Improvements | S |

Product Manager's Approach

Instead of estimating hundreds of User Stories, the team:

- Applies T-Shirt Sizing to initiatives.

- Identifies XL items requiring decomposition.

- Splits "AI Causality Assessment" into:

  - Data Collection

  - Model Training

  - Validation

  - Explainability

  - User Interface

Each Feature is later estimated using Story Points during Sprint Planning.

This approach enables executive roadmap discussions without requiring detailed engineering estimates months in advance.

Mini Quiz

- What does T-Shirt Sizing measure?

- Why is T-Shirt Sizing preferred during Product Discovery?

- Name five standard T-Shirt Size categories.

- How does T-Shirt Sizing differ from Planning Poker?

- Why should XL items be decomposed before Sprint Planning?

Practical Assignment

Part 1 – Size a Product Roadmap

Estimate the following Features using T-Shirt Sizes:

- User Login

- Two-Factor Authentication

- AI OCR Engine

- Duplicate Case Detection

- Global Language Support

- Real-Time Analytics Dashboard

Explain your reasoning.

Part 2 – Create Reference Stories

Define one reference story for each size:

- XS

- S

- M

- L

- XL

Use these as calibration examples for your Scrum Team.

Part 3 – Convert to Story Points

Using your team's calibration, map each T-Shirt Size to Story Points.

Explain why your mapping may differ from another team's mapping.

Part 4 – Roadmap Planning

Assume your Product Backlog contains:

- 5 XS Features

- 10 S Features

- 8 M Features

- 6 L Features

- 3 XL Features

Identify which items should be decomposed before Sprint Planning and propose a high-level release sequencing strategy.

Summary

T-Shirt Sizing is a lightweight, collaborative estimation technique used to assess the relative size of Product Backlog Items. It is especially valuable during Product Discovery, Roadmap Planning, and Portfolio Management, where detailed requirements are not yet available. Rather than pursuing false precision, Agile teams use T-Shirt Sizes to compare work, communicate complexity, and identify large initiatives that require further decomposition before Sprint execution.

Key Takeaways

- T-Shirt Sizing is a relative estimation technique, not a time estimate.

- It is best suited for early planning, roadmapping, and portfolio-level estimation.

- Sizes represent a combination of effort, complexity, uncertainty, risk, and dependencies.

- Teams should establish reference stories to maintain consistent calibration.

- Large (XL) items are strong candidates for decomposition into Features and User Stories.

- T-Shirt Sizing complements, rather than replaces, Story Points and Planning Poker.

Lesson 73 – Affinity Estimation (Fast Collaborative Estimation for Large Backlogs)

Learning Objectives

By the end of this lesson, you will understand:

- What is Affinity Estimation?

- History and Origins

- Why Agile Teams Use Affinity Estimation

- Principles of Relative Estimation

- Affinity Estimation Process

- Silent Sorting Technique

- Bucket System

- Calibration Stories

- Affinity Estimation vs Planning Poker

- Affinity Estimation vs T-Shirt Sizing

- Affinity Estimation vs Story Points

- Large Backlog Estimation

- Remote Affinity Estimation

- Product Owner's Role

- Scrum Master's Role

- Developers' Role

- Healthcare Examples

- Pharmacovigilance Examples

- AI Product Examples

- Common Mistakes

- Best Practices

- Interview Questions

- Mini Quiz

- Practical Assignment

1. Introduction

Imagine your Product Backlog contains:

- 320 User Stories

- 48 Features

- 12 Epics

Your Product Owner asks:

"Can we estimate everything before tomorrow's roadmap meeting?"

Using Planning Poker?

Impossible.

Even if each story takes only 5 minutes,

320 stories would require more than 26 hours.

Agile teams solve this problem using Affinity Estimation.

2. What is Affinity Estimation?

Affinity Estimation is a collaborative, relative estimation technique in which backlog items are grouped according to their relative size rather than estimated individually.

Instead of discussing every story one by one, the team compares stories with each other and places them into groups (or "buckets") of similar effort.

3. Simple Definition

Affinity Estimation is a rapid estimation method where similar Product Backlog Items are grouped together based on relative effort, complexity, and uncertainty.

4. History

Affinity Estimation evolved from Lean and Agile practices as organizations needed a faster way to estimate hundreds of backlog items.

It is widely used in:

- Scrum

- SAFe

- LeSS

- Nexus

- Enterprise Agile transformations

It is particularly useful during:

- Release Planning

- PI Planning

- Portfolio Planning

- Initial Product Backlog creation

5. Why Use Affinity Estimation?

Planning Poker works well for:

- 10–30 stories.

But not for:

- 300 stories.

Affinity Estimation dramatically reduces estimation time while maintaining reasonable accuracy.

6. Basic Principle

Instead of asking:

"How many Story Points?"

The team asks:

"Is this story larger or smaller than that one?"

Humans compare more accurately than they estimate absolute values.

This is the foundation of relative estimation.

7. Typical Workflow

Collect Product Backlog Items

│

▼

Choose Reference Story

│

▼

Silent Grouping

│

▼

Discuss Differences

│

▼

Adjust Groups

│

▼

Assign Story Points

│

▼

Validate Estimates

8. Silent Sorting

One unique aspect of Affinity Estimation is silent sorting.

Each team member independently places stories into relative groups without discussion.

Why?

Because it:

- Reduces bias.

- Prevents dominant personalities from influencing decisions.

- Encourages independent thinking.

Discussion begins only after the initial grouping.

9. Using Calibration Stories

The team selects one or more reference stories whose sizes are already well understood.

Example:

| Story | Story Points |
| --- | --- |
| Login | 3 |
| Registration | 5 |
| Search | 8 |

All other stories are compared against these references.

10. Bucket System

A common approach is to create buckets representing Story Point values.

Example:

| Bucket | Story Points |
| --- | --- |
| Bucket 1 | 1 |
| Bucket 2 | 2 |
| Bucket 3 | 3 |
| Bucket 4 | 5 |
| Bucket 5 | 8 |
| Bucket 6 | 13 |
| Bucket 7 | 21 |

Stories are placed into the most appropriate bucket.

11. Example

Suppose the team has these User Stories:

- User Login

- Password Reset

- AI Diagnosis

- Dashboard

- Notification Service

After comparison:

| Story | Bucket |
| --- | --- |
| Login | 2 |
| Password Reset | 3 |
| Dashboard | 5 |
| Notification Service | 8 |
| AI Diagnosis | 21 |

The team estimates five stories in minutes rather than debating each one individually.

12. Affinity Estimation vs Planning Poker

| Affinity Estimation | Planning Poker |
| --- | --- |
| Fast | Slower |
| Suitable for hundreds of stories | Suitable for Sprint Planning |
| Relative grouping | Individual discussion |
| Less discussion initially | Discussion for every story |
| Portfolio scale | Sprint scale |

13. Affinity Estimation vs T-Shirt Sizing

| Affinity Estimation | T-Shirt Sizing |
| --- | --- |
| Produces Story Point groups | Produces size categories |
| More detailed | Higher level |
| Better for backlog estimation | Better for roadmaps |
| Used before Sprint Planning | Used during Product Discovery |

14. Affinity Estimation vs Story Points

Affinity Estimation is not a replacement for Story Points.

It is a technique used to assign Story Points efficiently.

Think of it this way:

- Story Points = the measurement.

- Affinity Estimation = one method of arriving at that measurement.

15. Product Owner's Role

The Product Owner:

- Explains business requirements.

- Clarifies User Stories.

- Answers domain questions.

- Does not decide the estimates.

Estimation belongs to the Developers.

16. Developers' Role

Developers:

- Compare stories.

- Discuss technical complexity.

- Identify dependencies.

- Reach consensus on grouping.

They own the final estimate.

17. Scrum Master's Role

The Scrum Master:

- Facilitates the session.

- Keeps discussions focused.

- Encourages participation.

- Prevents anchoring and bias.

- Ensures time-boxes are respected.

18. Remote Affinity Estimation

Distributed teams often use online collaboration tools.

Typical workflow:

- Create digital cards.

- Drag cards into buckets.

- Vote independently.

- Review disagreements.

- Finalize Story Points.

This approach works well for globally distributed Agile teams.

19. Healthcare Example

Hospital Management System

The backlog contains:

- Patient Registration

- Appointment Booking

- Billing

- Lab Reports

- Pharmacy Integration

- Doctor Scheduling

- Insurance Claims

Rather than estimating each story individually, the team groups similar items and then assigns Story Points to each group.

The estimation session finishes in under an hour instead of several days.

20. Pharmacovigilance Example

AI Drug Safety Platform

Backlog Items:

- PDF Upload

- OCR Extraction

- MedDRA Coding

- Duplicate Detection

- Narrative Generation

- E2B Export

- Audit Trail

The team first groups:

Small:

- PDF Upload

- Audit Trail

Medium:

- OCR

- E2B Export

Large:

- MedDRA Coding

- Duplicate Detection

Very Large:

- AI Narrative Generation

Story Points are then assigned to each group.

21. AI Product Example

Medical AI Assistant

Features:

- Login

- Prompt History

- Voice Input

- AI Translation

- Multi-Agent Workflow

- Retrieval-Augmented Generation (RAG)

The team groups similar work based on complexity and technical uncertainty before assigning Story Points.

This accelerates estimation while preserving consistency.

22. Advantages

✔ Very fast.

✔ Excellent for large Product Backlogs.

✔ Encourages collaboration.

✔ Reduces estimation fatigue.

✔ Minimizes anchoring bias.

✔ Scales well across multiple Agile teams.

✔ Supports Release Planning and Portfolio Planning.

23. Limitations

✖ Less detailed than Planning Poker.

✖ Requires experienced team members.

✖ May need follow-up discussions for complex stories.

✖ Depends on good calibration stories.

24. Common Mistakes

Mistake 1

Estimating without reference stories.

Calibration becomes inconsistent.

Mistake 2

Skipping silent sorting.

This increases groupthink and anchoring bias.

Mistake 3

Allowing the Product Owner to assign estimates.

Only Developers estimate effort.

Mistake 4

Using Affinity Estimation for only five stories.

Planning Poker is often more appropriate for very small backlogs.

Mistake 5

Treating grouped estimates as permanent.

Estimates should be revisited when requirements change.

25. Best Practices

✔ Use clear calibration stories.

✔ Start with silent sorting.

✔ Time-box discussions.

✔ Revisit outliers.

✔ Keep estimation relative.

✔ Re-estimate after significant requirement changes.

✔ Combine Affinity Estimation with Backlog Refinement.

26. Interview Questions

Q1. What is Affinity Estimation?

Answer: Affinity Estimation is a collaborative Agile estimation technique where Product Backlog Items are grouped by relative size and then assigned Story Point values.

Q2. When should Affinity Estimation be used?

Answer: It is best used for estimating large Product Backlogs, Release Planning, Portfolio Planning, and Program Increment Planning where estimating each story individually would be too time-consuming.

Q3. How is Affinity Estimation different from Planning Poker?

Answer: Affinity Estimation groups stories quickly based on relative size, while Planning Poker estimates stories individually through discussion and consensus.

Q4. Why is silent sorting important?

Answer: Silent sorting reduces anchoring bias, encourages independent thinking, and prevents dominant personalities from influencing early estimates.

Q5. Who owns the final estimate?

Answer: The Developers own the final estimate because they are responsible for implementing the work.

27. Real-World Case Study

Global AI Pharmacovigilance Platform

A multinational pharmaceutical company plans the next quarterly release.

The Product Backlog contains 450 User Stories spread across five Scrum Teams.

Using Planning Poker for every story would require multiple days of workshops.

The Team's Approach

- Selects three calibration stories (3, 8, and 13 Story Points).

- Conducts silent Affinity Estimation for all backlog items.

- Groups stories into buckets.

- Discusses only stories where significant disagreement exists.

- Finalizes estimates and identifies stories larger than 21 Story Points for further decomposition.

Outcome

- Estimation time reduced from approximately three days to four hours.

- Consistent estimates across teams.

- Faster Release Planning.

- Improved confidence in forecasting.

Mini Quiz

- What is the primary purpose of Affinity Estimation?

- Why is silent sorting used?

- How does Affinity Estimation differ from Planning Poker?

- What are calibration stories?

- Who should assign Story Point estimates in Scrum?

Practical Assignment

Part 1 – Create Calibration Stories

Select five Product Backlog Items from a healthcare or AI product and assign them as reference stories with agreed Story Point values.

Part 2 – Group a Backlog

Given the following backlog, group the items into relative buckets before assigning Story Points:

- User Login

- Password Reset

- Appointment Booking

- AI OCR Engine

- Duplicate Case Detection

- Audit Trail

- E2B Export

- Regulatory Dashboard

Explain your reasoning.

Part 3 – Facilitate an Affinity Estimation Workshop

Design a 60-minute workshop agenda including:

- Preparation

- Silent Sorting

- Discussion

- Consensus

- Final Story Point Assignment

Include the responsibilities of the Product Owner, Developers, and Scrum Master.

Part 4 – Reflection

Write a one-page comparison answering:

"When should a Scrum Team choose Affinity Estimation instead of Planning Poker?"

Use examples from Healthcare, Pharmacovigilance, or AI product development to justify your answer.

Summary

Affinity Estimation is a fast, collaborative Agile estimation technique designed for large Product Backlogs. By grouping work items according to their relative size, teams can estimate hundreds of stories in a fraction of the time required by traditional methods. When combined with calibration stories, silent sorting, and focused discussions, Affinity Estimation supports consistent Story Point estimation, efficient Release Planning, and better forecasting across multiple Scrum Teams.

Key Takeaways

- Affinity Estimation is a relative estimation technique for large backlogs.

- It uses grouping and comparison instead of estimating each item individually.

- Silent sorting reduces bias and improves collaboration.

- Calibration stories establish a consistent reference for estimation.

- Developers own the estimates; the Product Owner clarifies requirements, and the Scrum Master facilitates the process.

- Affinity Estimation is especially valuable for Release Planning, Portfolio Planning, and enterprise-scale Agile environments.

Lesson 74 – Release Planning (Planning Product Releases with Agile Forecasting)

Learning Objectives

By the end of this lesson, you will understand:

- What is Release Planning?

- History of Release Planning

- Why Release Planning is Important

- Agile Release Planning vs Traditional Release Planning

- Release Planning Process

- Inputs to Release Planning

- Outputs of Release Planning

- Product Roadmap vs Release Plan

- MVP and Release Planning

- Velocity-Based Release Planning

- Capacity-Based Release Planning

- Managing Dependencies

- Managing Risks

- Release Planning in Scrum

- Release Planning in SAFe

- Release Burndown Chart

- Release Burnup Chart

- Release Readiness Checklist

- Product Owner's Role

- Scrum Master's Role

- Developers' Role

- Healthcare Examples

- Pharmacovigilance Examples

- AI Product Examples

- Best Practices

- Common Mistakes

- Interview Questions

- Mini Quiz

- Practical Assignment

1. Introduction

Imagine your CEO asks:

"When can customers start using our AI Pharmacovigilance Platform?"

As a Product Manager, answering:

"Whenever the developers finish."

is unacceptable.

Instead, you need a realistic plan.

That plan is called a Release Plan.

2. What is Release Planning?

Release Planning is the process of deciding:

- What features will be delivered

- When they will be delivered

- Which release they belong to

- What resources are required

- What risks may delay delivery

Unlike Sprint Planning, Release Planning spans multiple Sprints.

3. Simple Definition

Release Planning is the process of determining what product functionality will be delivered in a future release based on business priorities, team capacity, and expected delivery timelines.

4. History

Traditional software projects planned one large release over many months or years.

Agile changed this approach by encouraging:

- Smaller releases

- Frequent customer feedback

- Incremental delivery

- Continuous improvement

Modern Agile teams release:

- Weekly

- Bi-weekly

- Monthly

- Quarterly

depending on product needs.

5. Why Release Planning Matters

Without Release Planning:

- Stakeholders don't know when features will arrive.

- Marketing cannot prepare campaigns.

- Sales cannot commit to customers.

- Compliance teams cannot schedule validation.

- Customers lose confidence.

Release Planning aligns everyone around a shared delivery goal.

6. Release Planning vs Sprint Planning

| Release Planning | Sprint Planning |
| --- | --- |
| Long-term | Short-term |
| Multiple Sprints | One Sprint |
| Features & Epics | Sprint Backlog Items |
| Business focus | Delivery focus |
| Forecast | Commitment for the Sprint |

7. Product Roadmap vs Release Plan

| Product Roadmap | Release Plan |
| --- | --- |
| Strategic direction | Tactical delivery |
| Months to years | Weeks to months |
| High-level initiatives | Specific deliverables |
| Business vision | Planned release content |

A roadmap answers "Where are we going?"

A release plan answers "What will we deliver next?"

8. Inputs to Release Planning

A Product Manager typically uses:

- Product Vision

- Product Roadmap

- Product Backlog

- Business priorities

- Customer feedback

- Team velocity

- Team capacity

- Technical dependencies

- Regulatory requirements

- Risk assessments

9. Outputs of Release Planning

A Release Plan usually includes:

- Release Goal

- Planned Features

- Planned Sprint sequence

- Expected Release Date

- Major milestones

- Dependencies

- Risks

- Success metrics

10. Release Planning Process

Product Vision

│

▼

Product Roadmap

│

▼

Prioritized Product Backlog

│

▼

Estimate Features

│

▼

Calculate Capacity & Velocity

│

▼

Create Release Plan

│

▼

Validate Risks

│

▼

Execute Across Multiple Sprints

│

▼

Release Product

11. MVP and Release Planning

Not every feature belongs in Release 1.

Instead,

identify the Minimum Viable Product (MVP).

Example

AI Medical Assistant

Possible Features

- Login

- Patient Search

- AI Diagnosis

- Voice Assistant

- Multi-language

- Analytics

Release 1

- Login

- Patient Search

- AI Diagnosis

Later Releases

- Voice Assistant

- Analytics

- Multi-language

Deliver value early.

12. Velocity-Based Release Planning

Suppose

Average Velocity = 40 Story Points per Sprint

Remaining Backlog = 240 Story Points

Estimated Sprints

240 ÷ 40 = 6 Sprints

If each Sprint is two weeks:

Estimated Release

≈ 12 weeks

Remember: this is a forecast, not a guarantee.

13. Capacity-Based Release Planning

Capacity considers real-world availability.

Example

Team:

- 6 Developers

- 10 working days

- 1 public holiday

- 2 people on leave

Available capacity is lower than a full Sprint.

Ignoring capacity leads to unrealistic release plans.

14. Managing Dependencies

Some work cannot begin until other work is complete.

Example

You cannot:

Develop AI Report Generation

before:

OCR Data Extraction is available.

Dependency mapping prevents blocked work.

15. Risk Management

Every release has risks.

Examples

- Vendor delays

- API failures

- Regulatory changes

- Team turnover

- Infrastructure issues

- Performance problems

Release Planning should identify and monitor these risks.

16. Release Planning in Scrum

The Scrum Guide does not define Release Planning as an official Scrum Event.

However,

many Scrum Teams perform Release Planning as part of Product Management.

Typical activities:

- Review Product Backlog.

- Estimate Features.

- Forecast delivery.

- Align stakeholders.

17. Release Planning in SAFe

In SAFe,

Release Planning is closely linked to:

- Program Increment (PI) Planning

- ART synchronization

- Portfolio management

Multiple Agile teams coordinate delivery across shared objectives.

18. Release Burndown Chart

Tracks:

Remaining work

↓

toward Release.

Example

Story Points Remaining

250

220

190

160

130

100

70

40

20

0

The downward trend indicates progress.

19. Release Burnup Chart

Tracks:

Completed work

↑

toward Total Scope.

Useful when scope changes during development because it shows:

- Work completed

- Total scope

on separate lines.

20. Release Readiness Checklist

Before releasing:

✔ Features completed

✔ Acceptance Criteria satisfied

✔ Regression testing complete

✔ Performance testing complete

✔ Security validation complete

✔ Documentation updated

✔ Training completed

✔ Deployment plan approved

✔ Rollback strategy prepared

✔ Stakeholder approval obtained

21. Product Owner's Role

The Product Owner:

- Defines Release Goals.

- Prioritizes Features.

- Balances scope and value.

- Makes trade-off decisions.

- Communicates with stakeholders.

- Adjusts the Release Plan as new information emerges.

22. Developers' Role

Developers:

- Estimate work.

- Identify technical risks.

- Highlight dependencies.

- Provide delivery forecasts.

- Build and validate the product increment.

23. Scrum Master's Role

The Scrum Master:

- Facilitates planning.

- Removes impediments.

- Encourages realistic forecasting.

- Promotes transparency.

- Supports continuous improvement.

24. Healthcare Example

Hospital Appointment System

Release Goal

Enable online appointments.

Release 1

- Patient Registration

- Doctor Search

- Appointment Booking

Release 2

- Online Payments

- SMS Notifications

Release 3

- Telemedicine

- AI Appointment Suggestions

Each release delivers measurable customer value.

25. Pharmacovigilance Example

AI Drug Safety Platform

Release 1

- Case Intake

- PDF Upload

- OCR

- MedDRA Coding

Release 2

- Duplicate Detection

- Narrative Generation

- AI Signal Detection

Release 3

- Global Regulatory Reporting

- Dashboard Analytics

- Predictive Safety Insights

This phased approach reduces risk while delivering value continuously.

26. AI Product Example

Medical AI Assistant

Release 1

- Login

- Chat Interface

- GPT Integration

Release 2

- Voice Input

- Medical Summaries

- Drug Interaction Checker

Release 3

- Multi-Agent AI

- Clinical Decision Support

- Personalized Recommendations

Stakeholders receive meaningful functionality in each release instead of waiting for a massive launch.

27. Common Mistakes

Mistake 1

Treating forecasts as guarantees.

Forecasts should be updated as new information becomes available.

Mistake 2

Ignoring velocity history.

Past performance is valuable for realistic forecasting.

Mistake 3

Ignoring dependencies.

Blocked work delays the release.

Mistake 4

Planning every detail months in advance.

Agile embraces change.

Plans should evolve.

Mistake 5

Releasing too many features at once.

Smaller, incremental releases reduce risk.

28. Best Practices

✔ Define a clear Release Goal.

✔ Prioritize customer value.

✔ Use historical velocity.

✔ Account for team capacity.

✔ Identify dependencies early.

✔ Review risks regularly.

✔ Keep releases small and frequent.

✔ Update the Release Plan continuously.

29. Interview Questions

Q1. What is Release Planning?

Answer: Release Planning is the process of determining what product functionality will be delivered in future releases based on business priorities, team capacity, velocity, and technical constraints.

Q2. Is Release Planning an official Scrum Event?

Answer: No. The Scrum Guide does not define Release Planning as an official event, but many Scrum organizations use it as a Product Management practice.

Q3. What is the difference between a Product Roadmap and a Release Plan?

Answer: A Product Roadmap defines the strategic direction over months or years, while a Release Plan specifies which features will be delivered in upcoming releases over a shorter timeframe.

Q4. Why is historical velocity important?

Answer: Historical velocity provides a data-driven basis for forecasting how much work a Scrum Team can realistically complete in future Sprints.

Q5. Why should releases be incremental?

Answer: Incremental releases reduce delivery risk, enable faster customer feedback, and allow teams to adapt to changing business needs.

30. Real-World Case Study

AI Pharmacovigilance Platform

A pharmaceutical company wants to launch an AI-powered adverse event management platform within six months.

Product Backlog

- User Authentication

- OCR Processing

- MedDRA Coding

- Duplicate Detection

- AI Narrative Generation

- Regulatory Reporting

- Analytics Dashboard

- Mobile Access

Historical Velocity

Average:

45 Story Points per Sprint

Sprint Length:

2 weeks

Release Planning

Release 1 (3 Sprints)

- Authentication

- OCR

- MedDRA Coding

Release 2 (2 Sprints)

- Duplicate Detection

- Narrative Generation

Release 3 (2 Sprints)

- Regulatory Reporting

- Dashboard

- Mobile Access

Risks

- OCR accuracy

- Regulatory updates

- AI model performance

Outcome

The phased release approach allows customers to begin using the platform after the first release while later releases add advanced capabilities based on user feedback and evolving requirements.

Mini Quiz

- What is the primary objective of Release Planning?

- How does Release Planning differ from Sprint Planning?

- Why is historical velocity useful in Release Planning?

- Name three common inputs to a Release Plan.

- Why should Agile teams prefer smaller releases over large, infrequent releases?

Practical Assignment

Part 1 – Create a Release Plan

Assume you are developing an AI Pharmacovigilance Platform.

Prepare a Release Plan containing:

- Release Goal

- MVP Features

- Future Features

- Estimated number of Sprints

- Major risks

- Success metrics

Part 2 – Estimate a Release

Given:

- Product Backlog = 320 Story Points

- Average Velocity = 40 Story Points/Sprint

- Sprint Length = 2 weeks

Calculate:

- Number of Sprints required.

- Estimated release duration.

- Factors that could change this forecast.

Part 3 – Build a Release Readiness Checklist

Design a checklist covering:

- Functional testing

- Security

- Performance

- Compliance

- Documentation

- Deployment

- Rollback

- User training

Explain why each item is important before releasing a product.

Part 4 – Reflection

Write a one-page response to:

"How should a Product Manager balance customer expectations, team capacity, and changing business priorities during Release Planning?"

Support your answer with examples from Healthcare, Pharmacovigilance, or AI product development.

Summary

Release Planning is a strategic Product Management activity that bridges long-term product vision and short-term Sprint execution. By combining business priorities, backlog refinement, historical velocity, team capacity, and risk analysis, Product Managers create realistic release plans that maximize customer value while maintaining flexibility. Effective Release Planning is iterative, transparent, and continuously updated as new information emerges.

Key Takeaways

- Release Planning determines what will be delivered and when across multiple Sprints.

- It differs from Sprint Planning, which focuses on a single Sprint.

- Historical velocity and current team capacity are essential inputs for realistic forecasting.

- Successful Release Plans prioritize MVP delivery, manage dependencies, and continuously assess risks.

- Agile teams favor small, incremental releases to reduce risk and accelerate customer feedback.

- Although not an official Scrum Event, Release Planning is a core Product Management practice used by Agile organizations worldwide.

Lesson 75 – Agile Forecasting (Velocity, Throughput, Monte Carlo & Predictive Delivery)

Learning Objectives

By the end of this lesson, you will understand:

- What is Agile Forecasting?

- Why Forecasting Matters

- Forecast vs Commitment

- History of Agile Forecasting

- Types of Forecasting

- Velocity-Based Forecasting

- Throughput Forecasting

- Cycle Time Forecasting

- Lead Time Forecasting

- Monte Carlo Forecasting

- Confidence Levels

- Best-Case vs Worst-Case Forecasting

- Release Date Forecasting

- Scope Forecasting

- Forecasting with Changing Scope

- Forecasting Anti-Patterns

- Product Owner's Role

- Scrum Master's Role

- Developers' Role

- Healthcare Examples

- Pharmacovigilance Examples

- AI Product Examples

- Best Practices

- Common Mistakes

- Interview Questions

- Mini Quiz

- Practical Assignment

1. Introduction

Imagine your CEO asks:

"Can we launch our AI product by 30th September?"

A poor Product Manager replies:

"Yes."

An experienced Product Manager replies:

"Based on our historical delivery data, we have an 85% probability of completing the MVP by that date."

That difference is Agile Forecasting.

2. What is Agile Forecasting?

Agile Forecasting predicts future delivery using historical team performance rather than guesswork.

Instead of asking:

"When will this definitely finish?"

Agile asks:

"Given our past performance, what is the most likely delivery outcome?"

3. Simple Definition

Agile Forecasting is the practice of predicting future delivery using empirical data such as velocity, throughput, cycle time, and historical trends.

4. Forecast vs Commitment

This is one of the most misunderstood concepts in Agile.

| Forecast | Commitment |
| --- | --- |
| Prediction | Promise |
| Can change | Expected to be honored |
| Based on probability | Based on Sprint Goal |
| Updated regularly | Fixed for the Sprint |

A Product Manager should avoid treating forecasts as guarantees.

5. History

Traditional projects relied on:

- Fixed schedules

- Detailed upfront planning

- Gantt charts

Agile shifted toward:

- Empirical planning

- Continuous forecasting

- Incremental delivery

- Data-driven predictions

6. Why Forecasting Matters

Forecasting helps answer questions such as:

- When will Release 2 be ready?

- Can we meet the regulatory deadline?

- How many features fit into this quarter?

- Should we reduce scope?

- Do we need additional engineers?

7. Types of Agile Forecasting

Common forecasting methods include:

- Velocity Forecasting

- Throughput Forecasting

- Cycle Time Forecasting

- Lead Time Forecasting

- Monte Carlo Forecasting

8. Velocity-Based Forecasting

The most common Scrum forecasting technique.

Formula

Remaining Story Points

----------------------

Average Velocity

Example

Remaining Work

240 Story Points

Average Velocity

40 Story Points/Sprint

Forecast

240 ÷ 40

=

6 Sprints

If each Sprint lasts two weeks,

Estimated Release

≈ 12 weeks

9. Velocity Trend Analysis

Velocity should not be viewed in isolation.

Example:

| Sprint | Velocity |
| --- | --- |
| Sprint 1 | 34 |
| Sprint 2 | 36 |
| Sprint 3 | 39 |
| Sprint 4 | 41 |
| Sprint 5 | 40 |
| Sprint 6 | 42 |

Average

≈ 39

This provides a more reliable basis for forecasting than using a single Sprint.

10. Throughput Forecasting

Instead of Story Points,

Throughput measures:

Completed Work Items

Example

| Sprint | Stories Completed |
| --- | --- |
| 1 | 11 |
| 2 | 10 |
| 3 | 12 |
| 4 | 9 |
| 5 | 11 |

Average Throughput

≈ 11 stories per Sprint

Useful for Kanban and teams that do not estimate Story Points.

11. Cycle Time Forecasting

Cycle Time

Measures:

Start of development → Completion

Example

| Story | Cycle Time |
| --- | --- |
| Login | 2 days |
| Dashboard | 5 days |
| OCR | 8 days |

Average Cycle Time helps forecast future work.

12. Lead Time Forecasting

Lead Time measures:

Customer Request → Delivery

Example

Customer requests AI Search.

Delivered

28 days later.

Lead Time

28 days.

Organizations often optimize Lead Time to improve customer responsiveness.

13. Monte Carlo Forecasting

One of the most advanced Agile forecasting techniques.

Instead of calculating one delivery date,

Monte Carlo simulation generates thousands of possible outcomes based on historical performance.

Example:

- 1,000 simulated releases

- Different velocity patterns

- Different throughput values

- Probability distribution

Result:

- 50% chance by Sept 15

- 85% chance by Sept 25

- 95% chance by Oct 2

This gives stakeholders a realistic range rather than a single date.

14. Confidence Levels

Forecasts should include confidence.

Example

| Confidence | Meaning |
| --- | --- |
| 50% | Aggressive |
| 70% | Reasonable |
| 85% | High confidence |
| 95% | Very conservative |

Many organizations communicate release plans using 80–90% confidence.

15. Best-Case vs Worst-Case Forecasting

Example

Best Case

5 Sprints

Most Likely

6 Sprints

Worst Case

8 Sprints

This prepares stakeholders for uncertainty.

16. Scope Forecasting

Sometimes the date is fixed.

Question becomes:

"How much can we deliver?"

Example

Remaining Time

4 Sprints

Velocity

40

Forecast

≈160 Story Points

The Product Owner decides which work fits into those 160 Story Points.

17. Forecasting with Changing Scope

Agile assumes:

Scope changes.

Forecasts must therefore be updated whenever:

- New Features are added.

- Stories are removed.

- Priorities change.

- Team size changes.

Forecasting is continuous.

18. Product Owner's Role

The Product Owner:

- Prioritizes scope.

- Communicates forecasts.

- Makes trade-offs.

- Reduces scope when necessary.

- Aligns stakeholders with realistic expectations.

19. Developers' Role

Developers:

- Estimate work.

- Improve estimation quality.

- Maintain sustainable velocity.

- Highlight technical risks.

20. Scrum Master's Role

The Scrum Master:

- Encourages empirical planning.

- Coaches realistic expectations.

- Prevents misuse of velocity.

- Facilitates transparency.

21. Healthcare Example

Hospital Appointment System

Average Velocity

45 Story Points

Remaining Backlog

180 Story Points

Forecast

4 Sprints

Hospital management schedules staff training based on this forecast.

22. Pharmacovigilance Example

AI Drug Safety Platform

Remaining Work

- OCR Improvements

- Duplicate Detection

- Regulatory Reports

Velocity

42 Story Points

Forecast

≈5 Sprints

Monte Carlo analysis suggests:

- 80% probability of delivery before regulatory submission.

- 95% probability within one additional Sprint.

The Product Owner shares the probability range instead of a fixed promise.

23. AI Product Example

Medical AI Assistant

Historical Throughput

12 Features per month

Upcoming Roadmap

48 Features

Forecast

≈4 months

However,

adding multilingual support increases scope.

Forecast is revised to approximately five months.

This demonstrates why Agile forecasting is continuously updated.

24. Common Mistakes

Mistake 1

Treating forecasts as guarantees.

Mistake 2

Using one Sprint's velocity.

Use historical averages.

Mistake 3

Ignoring holidays and team changes.

Mistake 4

Using velocity to compare teams.

Velocity is team-specific.

Mistake 5

Never updating forecasts.

Forecasts must evolve with new information.

25. Best Practices

✔ Use historical data.

✔ Update forecasts frequently.

✔ Include confidence levels.

✔ Present ranges instead of exact dates.

✔ Consider capacity changes.

✔ Review scope regularly.

✔ Communicate uncertainty clearly.

26. Interview Questions

Q1. What is Agile Forecasting?

Answer: Agile Forecasting uses historical delivery data—such as velocity, throughput, and cycle time—to predict future delivery outcomes.

Q2. What is the difference between a forecast and a commitment?

Answer: A forecast is a probability-based prediction, while a commitment is an agreed objective, such as the Sprint Goal.

Q3. What is Throughput?

Answer: Throughput measures the number of completed work items over a given period, commonly used in Kanban.

Q4. What is Monte Carlo Forecasting?

Answer: Monte Carlo Forecasting uses repeated simulations based on historical performance to estimate the probability of different delivery dates or outcomes.

Q5. Why shouldn't Product Managers promise exact delivery dates?

Answer: Because Agile projects involve changing scope, varying team capacity, and uncertainty. Probabilistic forecasts are more realistic and transparent.

27. Real-World Case Study

Global AI Pharmacovigilance Platform

A pharmaceutical company plans to launch an AI-powered adverse event processing platform before a major regulatory conference.

Current Status

Remaining Backlog:

- 420 Story Points

Historical Velocity:

- Sprint 1: 38

- Sprint 2: 42

- Sprint 3: 40

- Sprint 4: 41

- Sprint 5: 39

Average Velocity:

40 Story Points

Initial Forecast

420 ÷ 40

≈ 10.5 Sprints

Mid-Project Changes

- New regulatory reporting requirements add 60 Story Points.

- Two developers leave the team.

- One new developer joins.

The Product Owner updates the forecast rather than keeping the original release date.

Monte Carlo Simulation

Historical velocity data is used to generate multiple delivery scenarios.

Results:

- 50% confidence: 10 Sprints

- 80% confidence: 11 Sprints

- 95% confidence: 12 Sprints

Decision

Stakeholders choose the 80% confidence forecast and remove two low-priority features from the release scope to increase the likelihood of meeting the target date.

28. Forecasting Comparison

| Method | Best For | Measures | Typical Use |
| --- | --- | --- | --- |
| Velocity Forecasting | Scrum | Story Points | Sprint & Release Planning |
| Throughput Forecasting | Kanban | Completed Items | Flow-based teams |
| Cycle Time Forecasting | Continuous Delivery | Time from start to finish | Process improvement |
| Lead Time Forecasting | Customer Experience | Request to delivery | Service optimization |
| Monte Carlo Forecasting | Enterprise Agile | Probability of outcomes | Executive planning & release forecasting |

Mini Quiz

- What is the difference between a forecast and a commitment?

- How is Velocity Forecasting calculated?

- When is Throughput Forecasting more useful than Velocity Forecasting?

- What information does Monte Carlo Forecasting provide that simple velocity calculations do not?

- Why should forecasts be updated throughout a project?

Practical Assignment

Part 1 – Velocity Forecast

Given:

- Remaining Backlog: 360 Story Points

- Average Velocity: 45 Story Points/Sprint

- Sprint Length: 2 weeks

Calculate:

- Number of Sprints required.

- Estimated release duration.

- One risk that could change the forecast.

Part 2 – Throughput Forecast

A Kanban team completed:

- Week 1: 14 items

- Week 2: 12 items

- Week 3: 15 items

- Week 4: 13 items

Calculate the average weekly throughput and estimate how many weeks are needed to complete a backlog of 130 items.

Part 3 – Monte Carlo Scenario

Assume historical Sprint velocities ranged between 35 and 50 Story Points over the past 12 Sprints.

Explain:

- Why a single release date may be misleading.

- How Monte Carlo simulation provides more useful information for stakeholders.

- Which confidence level (50%, 80%, or 95%) you would recommend for a regulatory product release and why.

Part 4 – Reflection

Write a one-page response to:

"Why should Product Managers communicate probabilities instead of promises when forecasting Agile releases?"

Use examples from Healthcare, Pharmacovigilance, or AI product development.

Summary

Agile Forecasting enables Product Managers to make informed, data-driven predictions about future delivery rather than relying on intuition or fixed schedules. By leveraging historical metrics such as velocity, throughput, cycle time, and lead time—and, when appropriate, probabilistic techniques like Monte Carlo simulation—teams can communicate realistic expectations, manage risk, and adapt plans as circumstances evolve. Forecasting is a continuous practice that supports better decision-making without undermining Agile's flexibility.

Key Takeaways

- Forecasts are predictions, not promises.

- Use historical data instead of intuition whenever possible.

- Velocity Forecasting is common in Scrum; Throughput Forecasting is common in Kanban.

- Cycle Time and Lead Time measure different aspects of delivery performance.

- Monte Carlo Forecasting provides probability-based delivery ranges rather than a single date.

- Effective Product Managers communicate confidence levels and update forecasts as scope, capacity, or priorities change.