MODULE 6 – Agile Metrics

Lesson 76: Why Agile Metrics Matter (Foundation)

Role Perspective:
As a future Business Analyst / Product Analyst / Product Manager / AI Product Manager, understanding metrics is critical because Agile is not only about "delivering faster"; it is about delivering the right value and continuously improving.

1. Concept: What are Agile Metrics?

Simple Definition

Agile Metrics are measurements used by Agile teams to understand progress, performance, quality, flow, and improvement.

They help answer questions like:

- Are we delivering value?

- Are we improving?

- Are we predictable?

- Are we building quality products?

- Are customers happy?

Example:

A Pharmacovigilance team is developing an:

AI Adverse Event Detection Platform

Management asks:

"Are we progressing well?"

A weak answer:

"We completed 50 user stories."

A better Agile answer:

- Average cycle time reduced from 10 days to 5 days

- Case processing accuracy increased from 85% to 95%

- Release predictability improved from 60% to 90%

- User satisfaction increased

These are metrics.

2. Why Agile Metrics Exist

The Problem

Without metrics, teams rely on opinions.

Example:

Product Owner:

"The team is slow."

Developer:

"We are working very hard."

Manager:

"Why is release delayed?"

Everyone has a different opinion.

Metrics create a common reality.

Metrics help answer:

1. Where are we?

Example:

How much work is completed?

2. Where are we going?

Example:

Can we release the product by December?

3. What is blocking us?

Example:

Why are user stories waiting 15 days?

4. How can we improve?

Example:

Why are defects increasing every sprint?

3. Real-Life Analogy

Imagine you are driving a car.

Without metrics:

You don't know:

- Speed

- Fuel level

- Engine temperature

You may reach the destination, or you may fail.

Dashboard gives information:

Speed       80 km/hr

Fuel        50%

Temperature Normal

Distance    100 km

Agile metrics are the dashboard of a product team.

4. Technical Explanation

Agile metrics generally fall into four categories:

Agile Metrics

|

------------------------------------------------

|                  |                |           |

Delivery          Flow            Quality      Value

Metrics           Metrics         Metrics      Metrics

Category 1: Delivery Metrics

Measure:

"Are we completing planned work?"

Examples:

- Velocity

- Sprint Completion

- Sprint Predictability

- Burndown Chart

Example:

Sprint Goal:

Complete AI case extraction module.

Planned:

20 story points

Completed:

18 story points

Sprint completion:

90%

Category 2: Flow Metrics

Measure:

"How smoothly does work move through the system?"

Examples:

- Cycle Time

- Lead Time

- Throughput

- WIP

Example:

AI model improvement request:

Day 1:
Created

Day 5:
Developer starts

Day 10:
Testing

Day 12:
Released

Flow metrics measure this journey.

Category 3: Quality Metrics

Measure:

"Are we building a reliable product?"

Examples:

- Escaped Defects

- Bug Rate

- Test Coverage

- Production Issues

Healthcare example:

AI Pharmacovigilance system:

A defect causes:

Wrong MedDRA coding suggestion.

Quality metric detects:

- Number of errors

- Severity

- Root cause

Category 4: Value Metrics

Measure:

"Are users getting benefits?"

Examples:

- User satisfaction

- Adoption rate

- Revenue

- Time saved

- Business outcomes

Example:

Before AI:

PV associate reviews:

100 cases/day

After AI:

300 cases/day

Value improvement:

3x productivity.

5. Metrics vs KPIs

Many people confuse these.

Metric

Any measurement.

Example:

Number of user stories completed.

KPI (Key Performance Indicator)

A metric directly linked to business goals.

Example:

Goal:

Reduce drug safety case processing time.

KPI:

Average processing time reduced by 40%.

Comparison:

| Metric | KPI |
| --- | --- |
| Measures something | Measures important business outcome |
| Many metrics exist | Few important KPIs |
| Team-focused | Business-focused |

6. Good Agile Metrics vs Bad Agile Metrics

Good Metrics

Help improvement.

Examples:

✅ Cycle time
✅ Customer satisfaction
✅ Defect rate
✅ Release frequency

Bad Metrics

Create unhealthy behavior.

Examples:

❌ Number of hours worked
❌ Number of lines of code
❌ Number of meetings attended
❌ Number of tickets closed

Example:

If developers are measured by:

"Number of tickets completed"

They may close easy tickets instead of solving important problems.

7. Agile Metrics in Scrum

A Scrum team commonly uses:

Product Backlog

|

↓

Sprint Planning

|

↓

Sprint Execution

|

↓

Sprint Review

|

↓

Metrics Analysis

|

↓

Retrospective Improvement

Metrics support continuous improvement.

8. Healthcare Example

Project:

AI Pharmacovigilance Platform

Business Goal:

Reduce manual case processing.

Metrics:

Delivery:

Velocity:
30 story points/sprint

Flow:

Cycle Time:
7 days/story

Quality:

AI extraction accuracy:
96%

Value:

Case processing time:

Before:
30 minutes/case

After:
10 minutes/case

9. AI Product Example

AI Medical Assistant

Important metrics:

Model Performance

- Accuracy

- Precision

- Recall

- Hallucination rate

Product Metrics

- Daily active users

- User retention

- Task completion rate

Agile Metrics

- Release frequency

- Cycle time

- Defect rate

10. Common Mistakes

Mistake 1:

Using metrics to punish teams.

Wrong:

"Your velocity dropped, explain."

Better:

"Why did velocity change? What can improve?"

Mistake 2:

Optimizing one metric.

Example:

Increase velocity.

Result:

Teams create smaller stories.

Velocity increases but value decreases.

Mistake 3:

Tracking too many metrics.

A dashboard with 100 metrics creates confusion.

11. Best Practices

Good Agile metrics should be:

Simple

Everyone understands them.

Transparent

Visible to the team.

Actionable

They should lead to improvement.

Balanced

Include:

- Speed

- Quality

- Value

12. Jira Example

Jira provides Agile reports:

Dashboard

--------------------------------

Sprint Burndown

Remaining Work ↓

Velocity Chart

Sprint 1: 35 points

Sprint 2: 42 points

Sprint 3: 40 points

Cumulative Flow Diagram

Cycle Time Report

--------------------------------

13. Interview Questions

Q1. Why are Agile metrics important?

Answer:

Agile metrics provide visibility into team performance, product delivery, quality, and improvement opportunities. They help teams make data-driven decisions.

Q2. Should velocity be used to compare teams?

Answer:

No. Velocity is a team-specific planning metric. Comparing velocity between teams creates unhealthy competition.

Q3. What is the difference between metric and KPI?

Answer:

A metric measures any activity, while a KPI measures progress toward an important business objective.

14. Mini Quiz

Answer these:

Q1.

Agile metrics mainly help teams:

A) Punish poor performers
B) Improve decision-making
C) Avoid planning

Q2.

Which is a Flow Metric?

A) Cycle Time
B) Revenue
C) Customer Rating

Q3.

Velocity should be:

A) Compared between teams
B) Used for team forecasting
C) Used to judge developers

Q4.

Which is a Value Metric?

A) Number of meetings
B) Customer satisfaction
C) Lines of code

15. Practical Assignment

For your portfolio project:

AI Pharmacovigilance Platform

Create a metrics dashboard.

Define:

Delivery Metrics:

Flow Metrics:

Quality Metrics:

Value Metrics:

16. Lesson Summary

Today we learned:

- What Agile metrics are

- Why they exist

- Four categories of metrics

- Metrics vs KPIs

- Good vs bad metrics

- How metrics help Product Managers and Business Analysts

Key Takeaways

Remember:

- Metrics are a product team's health dashboard.

- Metrics should improve decisions, not punish people.

- Velocity measures capacity, not value.

- Business outcomes matter more than activity.

- Good Agile teams measure delivery + flow + quality + value.

Lesson 77: Velocity (Advanced Understanding)

Role Perspective:
As a Business Analyst / Product Analyst / Product Manager, velocity helps you understand how much work a team can realistically deliver, forecast releases, and identify improvement opportunities.

A common interview mistake is saying:

"Velocity measures developer productivity."

This is incorrect.

Velocity measures team delivery capacity, not individual performance.

1. Concept: What is Velocity?

Simple Definition

Velocity is the amount of work a Scrum team completes during a Sprint, usually measured in Story Points.

Formula:

Velocity = Total Story Points Completed in a Sprint

Example:

Sprint duration:

2 weeks

Team committed:

40 Story Points

Completed:

35 Story Points

Velocity:

35 Story Points

2. Why Velocity Exists

The Problem

A Product Owner asks:

"When can we release our AI Pharmacovigilance Platform?"

The team says:

"We don't know."

Velocity helps create a forecast.

Example:

Product Backlog:

300 Story Points

Team velocity:

30 points/sprint

Forecast:

300 ÷ 30 = 10 Sprints

If one Sprint = 2 weeks:

10 × 2 = 20 weeks

Approximate release:

5 months

3. Real-Life Analogy

Imagine you run a restaurant.

Every day you prepare meals.

Day 1:

100 meals

Day 2:

120 meals

Day 3:

110 meals

Your average capacity:

≈110 meals/day

You can predict:

"How many meals can we prepare next week?"

Velocity works similarly.

4. Technical Explanation

Velocity uses:

Story Points

Not:

❌ Hours
❌ Lines of code
❌ Number of tasks

Example:

Sprint 1:

| User Story | Points |
| --- | --- |
| Login | 3 |
| Patient Profile | 5 |
| Case Upload | 8 |
| Dashboard | 13 |

Completed:

3 + 5 + 8 + 13

= 29 Story Points

Velocity:

29

5. How Velocity is Calculated

Example: AI Pharmacovigilance Platform

Sprint 1

Completed:

- User Authentication → 5

- PDF Upload → 8

- Case Database → 13

Velocity:

5 + 8 + 13 = 26

Sprint 2

Completed:

- MedDRA Search → 8

- Case Validation → 5

- Reporting Module → 13

Velocity:

8 + 5 + 13 = 26

Sprint 3

Completed:

- Signal Detection → 13

- Dashboard → 8

Velocity:

21

Average Velocity:

(26 + 26 + 21) ÷ 3

= 24.3

≈ 24 Story Points/Sprint

6. Velocity Chart

A Jira Velocity Chart looks like:

Story Points

50 |

40 |

30 |        █

20 | █      █       █

10 |

---------------------

S1    S2      S3

Committed

Completed

It shows:

- Planned work

- Completed work

- Team consistency

7. Velocity and Product Management

Product Managers use velocity for:

Release Forecasting

Question:

"When will Feature X be available?"

Example:

Backlog:

Feature:

AI Signal Detection

Remaining:

120 points

Team velocity:

30 points

Forecast:

120 / 30

= 4 Sprints

8. Velocity in Healthcare Example

Project:

AI Pharmacovigilance Case Processing Platform

Product Backlog:

| Feature | Points |
| --- | --- |
| ICSR Upload | 8 |
| AI Extraction | 13 |
| MedDRA Coding | 13 |
| Duplicate Detection | 8 |
| Signal Detection | 21 |

Total:

63 points

Team velocity:

20 points/sprint

Forecast:

63 ÷ 20

≈ 4 Sprints

9. Velocity in AI Product Development

AI products are uncertain.

Example:

Building:

Medical AI Chatbot

Some stories:

- Create UI → predictable

- Integrate LLM → uncertain

- Improve accuracy → highly uncertain

Velocity helps absorb uncertainty.

Example:

Sprint 1:

20 points

Sprint 2:

25 points

Sprint 3:

28 points

Team learns and improves forecasting.

10. Velocity vs Capacity

Important distinction.

Capacity

How much time/resources are available.

Example:

Developer availability:

80 hours

Velocity

How much work was actually completed.

Example:

Completed:

30 points

Relationship:

Capacity

↓

Team Work Ability

↓

Velocity

↓

Forecast

11. Velocity vs Productivity

This is a common interview trap.

Wrong:

"Velocity shows how productive developers are."

Correct:

"Velocity shows how much value a Scrum team can deliver based on completed work."

Why?

A team can increase velocity by:

- Breaking stories smaller

- Changing estimation

- Taking easier work

But business value may not increase.

12. Common Velocity Mistakes

Mistake 1:

Comparing team velocities

Wrong:

Team A velocity = 50

Team B velocity = 30

Team A is better.

Why wrong?

Different teams estimate differently.

Mistake 2:

Forcing higher velocity

Example:

Manager:

"Last sprint you delivered 30 points. Now deliver 50."

Result:

- Poor quality

- Artificial estimates

- Burnout

Mistake 3:

Changing Story Point values

Example:

Login was 5 points.

After completion:

"Make it 3 points."

This destroys historical data.

13. Best Practices

Good velocity usage:

✅ Use average of multiple sprints
✅ Use for forecasting
✅ Look for trends
✅ Discuss changes in retrospectives

Do not:

❌ Measure individuals
❌ Compare teams
❌ Set targets

14. Jira Example

In Jira:

Project → Reports → Velocity Chart

Example:

Sprint       Commitment     Completed

Sprint 1        40              35

Sprint 2        40              38

Sprint 3        45              42

Average velocity:

(35+38+42)/3

=38.3 points

15. Interview Questions

Q1. What is velocity?

Answer:

Velocity is the amount of story points a Scrum team completes in a sprint. It helps teams forecast future delivery.

Q2. Can velocity be compared between teams?

Answer:

No. Velocity is relative to each team's estimation approach and should only be used within the same team.

Q3. What happens if velocity suddenly drops?

Good answer:

The team should investigate causes such as dependencies, technical issues, scope changes, team availability, or increased complexity.

Q4. Should Product Owners maximize velocity?

Answer:

No. Product Owners should maximize business value. Velocity is only a planning tool.

16. Mini Quiz

Answer:

Q1.

Velocity measures:

A) Developer productivity
B) Completed Story Points
C) Number of bugs

Q2.

A team completes:

Sprint 1 = 30 points
Sprint 2 = 40 points
Sprint 3 = 50 points

Average velocity?

Q3.

A backlog has:

200 points

Velocity:

25 points/sprint

How many sprints required?

Q4.

Can Team A velocity 60 be compared with Team B velocity 40?

Yes/No and why?

17. Practical Assignment

Create a velocity calculation for your:

AI Pharmacovigilance Platform

Assume Sprint duration:

2 weeks

Create:

Sprint 1:

- 3 user stories

- Story points

- Completed points

Sprint 2:

- 3 user stories

- Story points

- Completed points

Calculate:

- Sprint velocity

- Average velocity

- Release forecast

18. Lesson Summary

Today we learned:

- What velocity means

- Why velocity exists

- How to calculate velocity

- How Product Managers use velocity

- Velocity vs capacity

- Velocity vs productivity

- Common mistakes

Key Takeaways

Remember:

- Velocity = completed story points.

- Velocity is for forecasting, not judging people.

- Velocity belongs to a team, not individuals.

- Stable velocity helps release planning.

- Business value matters more than increasing velocity.

Lesson 78: Cycle Time (Deep Dive)

Role Perspective: Business Analyst • Product Analyst • Product Manager • AI Product Manager

Learning Objectives

By the end of this lesson, you will be able to:

- Understand what Cycle Time is.

- Differentiate Cycle Time from Lead Time (a very common interview topic).

- Identify bottlenecks using Cycle Time.

- Use Cycle Time to improve delivery.

- Interpret Cycle Time reports in Jira.

- Apply Cycle Time to Healthcare, Pharmacovigilance, and AI products.

1. Concept

What is Cycle Time?

Simple Definition

Cycle Time is the time it takes to complete work after the team starts working on it.

It answers the question:

"Once we start working on something, how long does it take until it is finished?"

2. Why Does Cycle Time Exist?

Imagine you're a Product Manager.

A stakeholder asks:

"Once the development team starts working on the AI Duplicate Detection feature, how long will it take to finish?"

Velocity won't answer that because Velocity measures how much work is completed in a Sprint.

Cycle Time answers how long a single work item takes.

Without Cycle Time:

- Delivery becomes unpredictable.

- Stakeholders lose confidence.

- Bottlenecks remain hidden.

3. Real-Life Analogy

Imagine ordering a pizza.

Timeline:

6:00 PM   Order placed

6:20 PM   Chef starts making pizza

6:45 PM   Pizza ready

7:00 PM   Delivered

Cycle Time begins when the chef starts cooking.

6:20 PM → 6:45 PM

Cycle Time = 25 minutes

Notice that waiting before cooking is not part of Cycle Time.

4. Technical Explanation

Typical Agile workflow:

Backlog

│

▼

To Do

│

▼

In Progress

│

▼

Code Review

│

▼

Testing

│

▼

Done

Cycle Time begins when the work item enters:

In Progress

Cycle Time ends when it reaches:

Done

Formula:

Cycle Time = Done Date − Start Date

5. Example

User Story:

As a PV Associate,
I want AI to extract patient age from an ICSR,
so that manual data entry is reduced.

Timeline:

| Day | Status |
| --- | --- |
| Monday | In Progress |
| Tuesday | Development |
| Wednesday | Code Review |
| Thursday | Testing |
| Friday | Done |

Cycle Time:

Monday → Friday

= 5 Days

6. Another Example

Hospital Management System

Feature:

Appointment Booking

Timeline:

Started:

10 July

Completed:

15 July

Cycle Time:

6 Days

7. Healthcare Example

Project:

AI Pharmacovigilance Platform

Feature:

Automatic MedDRA Coding

Timeline:

Developer starts:

1 August

Completed:

8 August

Cycle Time:

7 Days

Now imagine:

AI Case Intake

Started:
2 August

Completed:
18 August

Cycle Time:

16 Days

Question:

Why did one feature take more than twice as long?

Possible reasons:

- Complex AI logic

- Waiting for SME review

- API dependency

- Poor requirements

- Testing delays

Cycle Time helps uncover these issues.

---

# 8. AI Product Example

AI Medical Chatbot

Stories:

| Story | Cycle Time |

|---------|------------|

| Login | 2 Days |

| Chat UI | 3 Days |

| Prompt Engineering | 8 Days |

| LLM Integration | 12 Days |

| AI Evaluation | 15 Days |

Observation:

AI-related work often has longer Cycle Time because of:

- Experimentation

- Model tuning

- Validation

- Hallucination testing

- Safety reviews

---

# 9. Why Product Managers Care

Suppose customers request:

> "Export AI reports to Excel."

You need to estimate delivery.

Historical Cycle Time:

Small features:

Average:

4 days

You can confidently communicate:

> "Development usually takes about 4–5 working days after implementation begins."

That's much more reliable than guessing.

---

# 10. Why Business Analysts Care

Business Analysts can reduce Cycle Time by:

- Writing clear requirements

- Removing ambiguity

- Clarifying acceptance criteria

- Answering developer questions quickly

- Reducing rework

Poor requirements often increase Cycle Time significantly.

---

# 11. Cycle Time vs Velocity

| Velocity | Cycle Time |

|-----------|------------|

| Measures amount of work | Measures time for one work item |

| Story Points | Days/Hours |

| Sprint-level | Story-level |

| Used for forecasting releases | Used for improving workflow |

| Scrum-focused | Scrum and Kanban |

Example:

Velocity:

30 Story Points

Cycle Time:

5 Days per story

Both metrics are useful, but they answer different questions.

---

# 12. Cycle Time vs Lead Time (Preview)

This is one of the most common interview questions.

Imagine:

```text

1 July

Customer requests feature

↓

5 July

Development starts

↓

10 July

Feature completed

Cycle Time:

5 July → 10 July

= 5 Days

Lead Time:

1 July → 10 July

= 10 Days

Simple memory trick:

Lead Time includes waiting. Cycle Time does not.

We'll explore Lead Time in detail in the next lesson.

13. What Increases Cycle Time?

Common causes:

Unclear Requirements

Developers repeatedly ask questions.

Too Many Approvals

Waiting for:

- Manager

- Security

- Legal

- Compliance

External Dependencies

Example:

Waiting for another team to deliver an API.

Large User Stories

Example:

"Build complete AI module"

Instead of:

- Upload PDF

- Extract patient

- Detect duplicate

- Generate report

Large stories naturally take longer.

Excessive Work in Progress (WIP)

Developers start many stories but finish few.

Result:

Cycle Time increases.

14. How to Reduce Cycle Time

Good Agile teams:

✅ Split large stories.

✅ Limit WIP.

✅ Clarify requirements early.

✅ Automate testing.

✅ Remove approval bottlenecks.

✅ Improve CI/CD.

✅ Encourage collaboration.

15. Jira Example

In Jira, Cycle Time data is often visualized through Control Charts or marketplace apps.

Example:

Story                    Cycle Time

Login                       2 Days

Dashboard                   5 Days

AI Extraction               8 Days

Signal Detection           10 Days

Report Generation           4 Days

Average:

5.8 Days

Managers may ask:

"Why is Signal Detection taking almost twice as long as other features?"

16. Diagram

Customer Request

│

▼

Backlog

│

▼

In Progress  ◄── Cycle Time Starts

│

▼

Development

│

▼

Code Review

│

▼

Testing

│

▼

Done      ◄── Cycle Time Ends

17. Common Mistakes

Mistake 1

Measuring only average Cycle Time.

Why it's risky:

Average may hide extremes.

Example:

Stories:

2

2

2

2

20

Average:

5.6 days

Reality:

One story is severely delayed.

Always examine the distribution, not just the average.

Mistake 2

Comparing different story types.

Comparing:

- Bug fix

- AI model development

is unfair because their complexity differs.

Mistake 3

Using Cycle Time to pressure developers.

Cycle Time should reveal process problems, not assign blame.

18. Best Practices

✔ Track trends over time.

✔ Categorize by work type.

✔ Monitor unusually long stories.

✔ Discuss long Cycle Times during Retrospectives.

✔ Improve the system, not individual performance.

19. Interview Questions

Q1. What is Cycle Time?

Answer:

Cycle Time measures the time taken to complete a work item after development begins until it is finished.

Q2. Why is Cycle Time important?

Answer:

It improves predictability, identifies bottlenecks, and helps teams deliver work more efficiently.

Q3. Can a low Velocity still have a good Cycle Time?

Answer:

Yes. A team may complete fewer but larger stories quickly, or be intentionally working on high-complexity items. Velocity and Cycle Time measure different aspects of delivery.

Q4. How can a BA reduce Cycle Time?

Answer:

By providing clear requirements, defining acceptance criteria, resolving stakeholder questions quickly, and reducing ambiguity before development starts.

20. Mini Quiz

Q1.

Cycle Time starts when:

A. Customer requests a feature

B. Development starts

C. Feature is released

Q2.

Cycle Time measures:

A. Story Points

B. Time taken to complete work after it starts

C. Revenue

Q3.

Which increases Cycle Time?

A. Clear requirements

B. Small user stories

C. Too many dependencies

Q4.

True or False:

Cycle Time includes the waiting period before development starts.

21. Practical Assignment

For your AI Pharmacovigilance Platform, choose five user stories.

For each story, create:

| User Story | Start Date | Done Date | Cycle Time |
| --- | --- | --- | --- |

Then answer:

- Which story has the longest Cycle Time?

- Why?

- How would you reduce its Cycle Time?

22. Lesson Summary

Today we learned:

- What Cycle Time is.

- Why it matters.

- How to calculate it.

- How Product Managers and Business Analysts use it.

- How to identify bottlenecks.

- How to improve delivery using Cycle Time.

- The key difference between Velocity and Cycle Time.

- A preview of Cycle Time vs Lead Time.

Key Takeaways

- Cycle Time starts when work begins, not when it's requested.

- Shorter, stable Cycle Time generally means a smoother delivery process.

- Cycle Time helps identify bottlenecks and improve workflow.

- Business Analysts influence Cycle Time through clear requirements.

- Velocity measures "how much"; Cycle Time measures "how long."

Lesson 79: Lead Time (Deep Dive)

Role Perspective: Business Analyst • Product Analyst • Product Manager • AI Product Manager

This is one of the most frequently asked Agile interview topics.

Almost every Scrum Master, Business Analyst, Product Owner, and Product Manager interview includes a question about Lead Time vs Cycle Time.

Learning Objectives

By the end of this lesson, you will be able to:

- Understand Lead Time.

- Differentiate Lead Time from Cycle Time.

- Identify delays before development starts.

- Improve customer satisfaction using Lead Time.

- Interpret Lead Time in Jira and Kanban.

- Apply Lead Time in Healthcare and AI product development.

1. Concept

What is Lead Time?

Simple Definition

Lead Time is the total time from when a customer or stakeholder requests work until that work is delivered.

It answers the question:

"How long does the customer wait?"

2. Why Does Lead Time Exist?

Imagine you request a new feature:

"Add AI-powered Duplicate Detection."

As a customer, you don't care when developers started coding.

You care about:

"When did I ask for it, and when did I receive it?"

Lead Time measures the customer's waiting experience.

3. Real-Life Analogy

Suppose you order a laptop online.

Timeline:

1 July

You place the order

↓

3 July

Warehouse starts packing

↓

5 July

Courier picks it up

↓

7 July

Delivered

Lead Time:

1 July → 7 July

= 6 Days

Notice that the warehouse didn't start work until 3 July, but you still waited from 1 July.

4. Technical Explanation

Typical Agile workflow:

Feature Requested

│

▼

Product Backlog

│

▼

Selected

│

▼

In Progress

│

▼

Development

│

▼

Testing

│

▼

Done

Lead Time starts here:

Feature Requested

Lead Time ends here:

Done

Formula:

Lead Time = Done Date − Request Date

5. Lead Time vs Cycle Time

Let's use one example.

Timeline:

1 Aug

Customer requests feature

↓

5 Aug

Development starts

↓

10 Aug

Feature completed

Lead Time:

1 Aug → 10 Aug

= 9 Days

Cycle Time:

5 Aug → 10 Aug

= 5 Days

Visual comparison:

Request ---------------------------- Done

|----------------------------------|

Lead Time

Start -------- Done

|-------------|

Cycle Time

Memory Trick

Lead = Customer waits

Cycle = Team works

6. Example

Project:

Hospital Management System

Feature:

Online Appointment Booking

Timeline:

| Event | Date |
| --- | --- |
| Requested | 1 Sept |
| Approved | 5 Sept |
| Development Started | 7 Sept |
| Completed | 15 Sept |

Lead Time:

1 Sept → 15 Sept

14 Days

Cycle Time:

7 Sept → 15 Sept

8 Days

Difference:

6 days were spent waiting before development began.

7. Healthcare Example

Project:

AI Pharmacovigilance Platform

Feature:

Automatic WHO Drug Coding

Timeline:

| Event | Date |
| --- | --- |
| Business requests feature | 1 Oct |
| Prioritized in Sprint | 10 Oct |
| Development Starts | 12 Oct |
| Released | 20 Oct |

Lead Time:

1 Oct → 20 Oct

19 Days

Cycle Time:

12 Oct → 20 Oct

8 Days

Observation:

The team worked efficiently.

Most delay happened before development.

8. AI Product Example

Project:

AI Medical Chatbot

Feature:

Voice Input

Timeline:

Customer Request

↓

Product Discovery

↓

Market Research

↓

Prioritization

↓

Sprint Planning

↓

Development

↓

Testing

↓

Release

AI products often have longer Lead Times because:

- Ethical review

- Security approval

- Model validation

- Regulatory compliance

- Data preparation

Even if coding takes only one week, the customer may wait much longer.

9. Why Product Managers Care

A Product Manager is responsible for delivering customer value quickly.

High Lead Time may indicate:

- Slow prioritization

- Too many approvals

- Overloaded backlog

- Poor roadmap planning

Reducing Lead Time improves customer satisfaction.

10. Why Business Analysts Care

Business Analysts influence Lead Time by:

- Clarifying requirements early.

- Running stakeholder workshops promptly.

- Avoiding repeated requirement changes.

- Preparing user stories before Sprint Planning.

Well-prepared work spends less time waiting.

11. Why Scrum Masters Care

Scrum Masters focus on removing delays.

Common causes:

- Waiting for Product Owner decisions.

- Waiting for infrastructure.

- Waiting for another team.

- Waiting for approvals.

Reducing waiting time reduces Lead Time.

12. Lead Time in Kanban

Kanban teams heavily use Lead Time because they deliver continuously.

Example:

Request

↓

Backlog

↓

Ready

↓

Development

↓

Testing

↓

Released

Kanban aims to:

- Reduce waiting.

- Reduce bottlenecks.

- Deliver continuously.

Lead Time is one of Kanban's most important metrics.

13. Lead Time in Jira

Jira dashboards or marketplace apps can display Lead Time reports.

Example:

| Story | Lead Time |
| --- | --- |
| Login | 5 Days |
| Dashboard | 7 Days |
| AI Extraction | 14 Days |
| Duplicate Detection | 20 Days |

Question:

Why does Duplicate Detection have such a long Lead Time?

Possible reasons:

- Low priority.

- Waiting for AI model.

- Waiting for compliance approval.

- Dependency on another team.

14. Common Causes of High Lead Time

Large Backlog

Too many items waiting.

Poor Prioritization

Important work waits behind less valuable work.

Approval Delays

Legal.

Security.

Compliance.

Architecture.

Team Capacity

No developers available.

Dependencies

Waiting for APIs.

Waiting for infrastructure.

Waiting for vendors.

15. How to Reduce Lead Time

Good Agile teams:

✔ Prioritize frequently.

✔ Keep backlog manageable.

✔ Reduce approval layers.

✔ Break work into smaller stories.

✔ Remove dependencies.

✔ Improve Sprint Planning.

✔ Automate testing and deployment.

16. Lead Time vs Cycle Time Table

| Aspect | Lead Time | Cycle Time |
| --- | --- | --- |
| Starts | Customer request | Development starts |
| Ends | Work completed | Work completed |
| Measures | Customer waiting time | Team working time |
| Focus | Customer experience | Team efficiency |
| Includes waiting? | Yes | No |
| Used by | Product Managers, Kanban teams | Scrum teams, Delivery teams |

17. Diagram

Customer Request

│

▼

Product Backlog

│

▼

Selected

│

▼

In Progress

│

▼

Development

│

▼

Testing

│

▼

Done

Lead Time:

Request ─────────────────────────► Done

Cycle Time:

In Progress ─────────────────────► Done

18. Common Mistakes

Mistake 1

Thinking Lead Time and Cycle Time are the same.

They are related but measure different things.

Mistake 2

Reducing Cycle Time while ignoring waiting.

Example:

Development takes only 3 days.

But work waits 30 days in backlog.

Customers still experience a long wait.

Mistake 3

Tracking only averages.

A few very long Lead Times can indicate serious process problems.

19. Best Practices

✔ Monitor Lead Time trends.

✔ Review delays during Retrospectives.

✔ Limit Work in Progress (WIP).

✔ Prioritize customer value.

✔ Remove unnecessary approvals.

20. Interview Questions

Q1. What is Lead Time?

Answer:

Lead Time is the total time from when work is requested until it is delivered.

Q2. What is the difference between Lead Time and Cycle Time?

Answer:

Lead Time measures the customer's waiting time from request to delivery.

Cycle Time measures the team's working time from development start to completion.

Q3. Why is Lead Time important?

Answer:

It reflects customer experience and helps identify delays before development begins.

Q4. Which metric is more customer-focused?

Answer:

Lead Time, because it measures how long the customer waits for value.

21. Mini Quiz

Q1.

Lead Time starts when:

A. Development starts

B. Customer requests work

C. Testing starts

Q2.

Lead Time measures:

A. Story Points

B. Customer waiting time

C. Developer productivity

Q3.

Which metric includes backlog waiting time?

A. Lead Time

B. Cycle Time

C. Velocity

Q4.

True or False:

Reducing approval delays can reduce Lead Time.

22. Practical Assignment

For your AI Pharmacovigilance Platform, choose three features.

For each feature, record:

| Feature | Request Date | Start Date | Done Date | Lead Time | Cycle Time |
| --- | --- | --- | --- | --- | --- |

Then answer:

- Which feature has the longest Lead Time?

- Was the delay before development or during development?

- What process improvement would reduce the delay?

23. Lesson Summary

Today we learned:

- What Lead Time is.

- Why it matters to customers.

- The difference between Lead Time and Cycle Time.

- How Product Managers, Business Analysts, and Scrum Masters use Lead Time.

- Common causes of high Lead Time.

- Practical ways to reduce Lead Time.

Key Takeaways

- Lead Time starts when the customer requests work.

- Cycle Time starts when the team begins work.

- Lead Time reflects customer experience; Cycle Time reflects delivery efficiency.

- Reducing waiting is just as important as improving development speed.

- Lead Time is especially important in Kanban and continuous delivery environments.

Lesson 80: Flow Efficiency (Deep Dive)

Role Perspective: Business Analyst • Product Analyst • Product Manager • AI Product Manager • Scrum Master

Flow Efficiency is one of the most powerful—but least understood—Agile metrics.

Elite organizations like Amazon, Microsoft, and Spotify focus not just on working faster, but on reducing waiting time. This is where Flow Efficiency becomes valuable.

Learning Objectives

By the end of this lesson, you will be able to:

- Understand what Flow Efficiency is.

- Calculate Flow Efficiency.

- Identify waste in Agile processes.

- Improve delivery speed without increasing workload.

- Apply Flow Efficiency to Healthcare, Pharmacovigilance, and AI products.

- Interpret Flow Efficiency alongside Lead Time and Cycle Time.

1. Concept

What is Flow Efficiency?

Simple Definition

Flow Efficiency measures how much of the total time a work item is actually being worked on versus waiting.

It answers:

"How much of the elapsed time was productive work?"

2. Why Does Flow Efficiency Exist?

Imagine a user story takes 10 days to finish.

You might think:

"It took 10 days of work."

But when you investigate:

- Developers worked only 3 days.

- The story spent 7 days waiting:

  - Waiting for approvals.

  - Waiting for testing.

  - Waiting for another team.

  - Waiting for deployment.

Flow Efficiency reveals this hidden waste.

3. Real-Life Analogy

Suppose you visit a hospital for a blood test.

Timeline:

9:00 AM   Arrive

9:20 AM   Registration

9:50 AM   Waiting

10:10 AM  Blood Sample (5 minutes)

10:15 AM  Waiting

11:00 AM  Doctor Review (10 minutes)

11:10 AM  Leave

Total Time:

2 hours 10 minutes (130 minutes)

Actual medical work:

- Blood sample = 5 minutes

- Doctor review = 10 minutes

Total active work:

15 minutes

Most of your visit was spent waiting.

This is exactly what Flow Efficiency measures.

4. Technical Explanation

Formula:

Flow Efficiency = (Active Working Time ÷ Total Elapsed Time) × 100%

Example:

User Story:

Total elapsed time:

10 days

Actual work:

4 days

Calculation:

(4 ÷ 10) × 100

= 40%

Flow Efficiency:

40%

Meaning:

The work item spent 60% of its time waiting.

5. Visual Timeline

Day 1     Day 2     Day 3     Day 4     Day 5

│          │          │          │          │

Working  Waiting  Working  Waiting  Waiting

██████    ░░░░░░   ██████   ░░░░░░   ░░░░░░

Legend:

- █ = Active work

- ░ = Waiting

Even though the story took 5 days, only 2 days involved actual work.

6. Example

Feature:

AI PDF Upload

Timeline:

| Activity | Time |
| --- | --- |
| Development | 2 Days |
| Waiting for Code Review | 1 Day |
| Testing | 1 Day |
| Waiting for Deployment | 2 Days |

Total elapsed time:

6 Days

Active work:

3 Days

Calculation:

3 ÷ 6 × 100

= 50%

Flow Efficiency:

50%

7. Healthcare Example

Project:

AI Pharmacovigilance Platform

Feature:

Automatic MedDRA Coding

Timeline:

| Activity | Duration |
| --- | --- |
| Development | 4 Days |
| SME Review | 3 Days |
| Compliance Approval | 2 Days |
| Testing | 2 Days |
| Deployment Queue | 4 Days |

Total elapsed time:

15 Days

Active work:

Development + Testing

= 6 Days

Calculation:

6 ÷ 15 × 100

= 40%

Observation:

The developers weren't slow.

The process had too much waiting.

8. AI Product Example

Project:

Medical AI Chatbot

Feature:

Voice Assistant

Timeline:

| Activity | Duration |
| --- | --- |
| Development | 5 Days |
| Model Training | 2 Days |
| Security Review | 4 Days |
| AI Safety Review | 3 Days |
| Deployment | 1 Day |

Active work:

- Development

- Model Training

- Deployment

= 8 Days

Total:

15 Days

Flow Efficiency:

8 ÷ 15

≈53%

Improvement opportunity:

Reduce review delays.

9. Why Product Managers Care

Imagine customers complain:

"Features take too long."

Flow Efficiency helps answer:

- Is development slow?

- Or is work waiting in queues?

A Product Manager can improve delivery by removing waiting, not just asking teams to code faster.

10. Why Business Analysts Care

Business Analysts can improve Flow Efficiency by:

- Clarifying requirements early.

- Reducing rework.

- Scheduling stakeholder reviews promptly.

- Avoiding repeated requirement changes.

- Preparing acceptance criteria before Sprint Planning.

11. Why Scrum Masters Care

Scrum Masters use Flow Efficiency to identify:

- Approval bottlenecks.

- Long code reviews.

- Testing delays.

- Infrastructure issues.

- Dependency problems.

Instead of asking:

"Why aren't developers faster?"

They ask:

"Why is work waiting?"

12. Relationship with Other Metrics

| Metric | Focus |
| --- | --- |
| Velocity | How much work is completed |
| Cycle Time | How long active work takes |
| Lead Time | Total customer waiting time |
| Flow Efficiency | Percentage of time spent actively working |

13. Common Causes of Low Flow Efficiency

Too Many Approvals

Waiting for:

- Compliance

- Security

- Architecture

Large User Stories

Large stories often pause multiple times.

Team Dependencies

Waiting for another team.

Slow Code Reviews

Developers finish coding.

Then wait several days for review.

Manual Testing

Testing queues become bottlenecks.

Deployment Delays

Feature completed.

But deployment happens once every two weeks.

14. How to Improve Flow Efficiency

Break Stories Smaller

Smaller stories move faster.

Limit Work in Progress (WIP)

Finish work before starting new work.

Automate Testing

Reduces waiting.

Continuous Deployment

Deploy frequently.

Cross-functional Teams

Reduce dependency on other teams.

Faster Reviews

Review code daily instead of weekly.

15. Jira Example

Many Jira marketplace apps display Flow Efficiency.

Example:

| Story | Total Time | Active Time | Flow Efficiency |
| --- | --- | --- | --- |
| Login | 5 Days | 4 Days | 80% |
| Dashboard | 10 Days | 5 Days | 50% |
| AI Extraction | 15 Days | 6 Days | 40% |

Question:

Which story needs investigation?

Answer:

AI Extraction.

Most time was spent waiting.

16. Diagram

Feature Requested

│

▼

Waiting

░░░░░░░

│

▼

Development

█████████

│

▼

Waiting

░░░░░░░░░

│

▼

Testing

███████

│

▼

Waiting

░░░░░░

│

▼

Released

Active work:

██████

Waiting:

░░░░░░░░░

Flow Efficiency compares these two.

17. Common Mistakes

Mistake 1

Assuming low Flow Efficiency means developers are slow.

Reality:

The process may be inefficient.

Mistake 2

Trying to increase working hours.

Better approach:

Reduce waiting.

Mistake 3

Ignoring dependency queues.

Many delays happen outside the development team.

18. Best Practices

✔ Track waiting reasons.

✔ Reduce handoffs.

✔ Review bottlenecks every Sprint Retrospective.

✔ Improve automation.

✔ Measure trends, not one-off numbers.

19. Interview Questions

Q1. What is Flow Efficiency?

Answer:

Flow Efficiency measures the percentage of total elapsed time during which work is actively being performed on a work item.

Q2. How is Flow Efficiency calculated?

Answer:

Flow Efficiency = (Active Working Time ÷ Total Elapsed Time) × 100%.

Q3. What causes low Flow Efficiency?

Answer:

Waiting for approvals, dependencies, code reviews, testing, or deployment.

Q4. How can a Product Manager improve Flow Efficiency?

Answer:

By reducing waiting time, prioritizing effectively, removing bottlenecks, and supporting process improvements rather than simply increasing team workload.

20. Mini Quiz

Q1.

Flow Efficiency measures:

A. Story Points

B. Percentage of active work time

C. Revenue

Q2.

A feature takes:

10 days total

Developers actively work for 4 days.

Flow Efficiency is:

A. 25%

B. 40%

C. 60%

Q3.

Which action is most likely to improve Flow Efficiency?

A. Increase developer overtime

B. Reduce approval delays

C. Increase Story Points

Q4.

True or False:

A team can improve Flow Efficiency by reducing unnecessary waiting even if coding speed stays the same.

21. Practical Assignment

Using your AI Pharmacovigilance Platform, choose one feature (e.g., Duplicate Detection).

Create a timeline:

| Stage | Duration |
| --- | --- |
| Waiting in Backlog |  |
| Development |  |
| Code Review |  |
| Testing |  |
| Waiting for Deployment |  |
| Released |  |

Then calculate:

- Total elapsed time.

- Active working time.

- Flow Efficiency.

- Identify the biggest bottleneck.

- Suggest two improvements.

22. Lesson Summary

Today we learned:

- What Flow Efficiency is.

- How to calculate it.

- Why waiting is often a bigger problem than coding speed.

- How Product Managers, Business Analysts, and Scrum Masters use Flow Efficiency.

- Practical ways to improve delivery without increasing workload.

Key Takeaways

- Flow Efficiency measures how much time is spent working versus waiting.

- High waiting time is usually a process problem, not a people problem.

- Reducing bottlenecks often improves delivery more than increasing coding speed.

- Flow Efficiency complements Lead Time and Cycle Time.

- Continuous improvement focuses on the entire workflow, not just development.

Lesson 81: Escaped Defects (Deep Dive)

Role Perspective: Business Analyst • Product Analyst • Product Manager • Scrum Master • QA • AI Product Manager

If Velocity tells you how fast you're delivering, Escaped Defects tell you whether you're delivering quality.

A team can have excellent Velocity and terrible quality. High-performing Agile teams optimize both speed and quality.

Learning Objectives

By the end of this lesson, you will understand:

- What Escaped Defects are.

- Why they matter.

- How to measure them.

- How to reduce them.

- The role of BAs, Product Managers, Scrum Masters, Developers, and QA.

- Real Healthcare and AI examples.

- Interview scenarios and Jira usage.

1. Concept

What is an Escaped Defect?

Simple Definition

An Escaped Defect is a bug that was not found during development or testing and reaches the customer or production environment.

In simple words:

A defect that "escaped" your quality process.

2. Why Does This Metric Exist?

Imagine your team says:

"We delivered every Sprint on time."

Great!

But one week later:

Customers complain:

- Login doesn't work.

- AI gives incorrect answers.

- Reports are missing data.

The team delivered quickly, but poor quality.

Escaped Defects help answer:

"How many problems reached our users?"

3. Real-Life Analogy

Imagine a pharmaceutical company manufactures tablets.

Quality checks happen before shipping.

If damaged tablets reach pharmacies:

The quality process failed.

The damaged tablets are like Escaped Defects.

4. Technical Explanation

Typical software flow:

Requirements

│

▼

Development

│

▼

Code Review

│

▼

Testing

│

▼

Release

│

▼

Customer

If a bug is found:

- During Development ✅

- During Testing ✅

It is not an escaped defect.

If the customer finds it after release ❌

It is an Escaped Defect.

5. Example

Feature:

AI PDF Upload

Bug:

Large PDF files fail to upload.

Timeline:

Development

↓

Testing

↓

Release

↓

Customer uploads 50MB PDF

↓

System crashes

This bug escaped testing.

Therefore:

Escaped Defect = Yes

6. Formula

There are different ways organizations measure Escaped Defects.

Method 1: Count

Example:

Production bugs this Sprint:

| Bug | Severity |
| --- | --- |
| Login Failure | High |
| Report Missing | Medium |
| AI Extraction Error | High |

Escaped Defects:

3

Method 2: Percentage

Formula:

Escaped Defect Rate =

(Production Defects ÷ Total Defects) × 100%

Example:

Total defects found:

100

Production defects:

8

Calculation:

8 ÷ 100 × 100

= 8%

Escaped Defect Rate:

8%

7. Healthcare Example

Project:

AI Pharmacovigilance Platform

Feature:

Automatic MedDRA Coding

Bug:

The AI incorrectly codes:

"Nausea"

as

"Vomiting"

The testing team missed it.

PV Associates discover the issue after release.

Impact:

- Incorrect safety database.

- Incorrect regulatory submissions.

- Potential compliance risk.

This is a High-Severity Escaped Defect.

8. AI Product Example

Project:

Medical AI Chatbot

Question:

"Can I take Drug A and Drug B together?"

The AI incorrectly answers:

"Yes"

The correct answer should have warned about a serious interaction.

The bug was not detected before release.

Consequences:

- Patient safety risk.

- Loss of user trust.

- Possible legal issues.

This is a Critical Escaped Defect.

9. Types of Escaped Defects

Functional

Feature doesn't work.

Example:

Login button fails.

Performance

System is too slow.

Example:

Dashboard loads in 60 seconds.

Security

Sensitive data exposed.

Example:

Patient records visible without authorization.

Usability

Confusing interface.

Example:

Users cannot find the Submit button.

Data

Incorrect calculations.

Example:

Wrong dosage displayed.

AI

Incorrect AI predictions.

Example:

Hallucinated medical advice.

10. Severity vs Priority

These are often confused.

Severity

How serious is the impact?

Examples:

- System crash

- Data loss

- Wrong diagnosis

Priority

How quickly should we fix it?

Examples:

- High

- Medium

- Low

Example:

Typo on homepage.

Severity:

Low

Priority:

High (because every customer sees it)

11. Root Cause Analysis

Instead of asking:

"Who made the mistake?"

Ask:

"Why did this defect escape?"

Possible reasons:

- Poor requirements.

- Missing acceptance criteria.

- Incomplete testing.

- Lack of automation.

- Last-minute changes.

- Communication gaps.

- AI model limitations.

12. Defect Lifecycle

Reported

│

▼

Triaged

│

▼

Assigned

│

▼

Fixed

│

▼

Retested

│

▼

Closed

If reported after release:

It becomes an Escaped Defect.

13. Role Responsibilities

Business Analyst

Reduce defects by:

- Writing clear requirements.

- Defining acceptance criteria.

- Clarifying business rules.

- Validating stakeholder expectations.

Product Manager

Focus on:

- Customer impact.

- Prioritizing defect fixes.

- Balancing new features vs quality.

Scrum Master

Ensure:

- Root Cause Analysis during Retrospectives.

- Process improvements.

- Better collaboration.

Developers

Responsibilities:

- Unit testing.

- Code reviews.

- Following coding standards.

QA Engineers

Responsibilities:

- Test planning.

- Regression testing.

- Exploratory testing.

- Automation.

14. Jira Example

Typical Jira bug workflow:

To Do

│

▼

In Progress

│

▼

Code Review

│

▼

Testing

│

▼

Done

Production bug:

Bug Reported

↓

Critical

↓

Assigned

↓

Hotfix

↓

Production Release

↓

Closed

Common Jira fields:

| Field | Example |
| --- | --- |
| Issue Type | Bug |
| Severity | High |
| Priority | Highest |
| Environment | Production |
| Root Cause | Missing validation |
| Resolution | Fixed |

15. Escaped Defects Dashboard

Example:

Sprint 12

New Bugs:

18

Fixed:

16

Escaped Defects:

2

Critical:

1

High:

1

Medium:

0

Trend:

Sprint 9   ████

Sprint 10  ███

Sprint 11  ██

Sprint 12  █

A downward trend indicates improving quality.

16. Common Causes

- Incomplete requirements.

- Ambiguous acceptance criteria.

- Insufficient testing.

- Manual testing only.

- Tight deadlines.

- Lack of regression testing.

- Weak code reviews.

- Poor communication.

17. How to Reduce Escaped Defects

Better User Stories

Clear requirements reduce misunderstandings.

Strong Acceptance Criteria

Developers know exactly what "done" means.

Automated Testing

Run regression tests every release.

Code Reviews

Catch issues early.

Shift Left Testing

Start testing earlier.

Frequent Releases

Smaller releases reduce risk.

Root Cause Analysis

Improve the process after each escaped defect.

18. Healthcare Best Practices

For healthcare software:

- Clinical validation.

- Regulatory review.

- Audit trails.

- Data verification.

- Medical SME testing.

- Risk-based testing.

Quality is not optional.

19. AI Product Considerations

AI products require additional validation:

- Hallucination testing.

- Bias testing.

- Safety testing.

- Prompt testing.

- Model evaluation.

- Human review for critical decisions.

Some AI errors are not traditional software bugs, but they still affect users and should be monitored.

20. Interview Questions

Q1. What is an Escaped Defect?

Answer:

A defect discovered by users after the software has been released to production.

Q2. Why is it important?

Answer:

It measures the effectiveness of the development and testing process and highlights quality issues that reached customers.

Q3. How can a Business Analyst reduce Escaped Defects?

Answer:

By gathering complete requirements, writing clear user stories, defining strong acceptance criteria, and validating business rules with stakeholders.

Q4. What should a Scrum Team do after a critical escaped defect?

Answer:

Fix the issue, perform Root Cause Analysis, discuss it in the Retrospective, and implement process improvements to prevent recurrence.

21. Mini Quiz

Q1.

An Escaped Defect is:

A. A bug found during testing

B. A bug found after release

C. A user story

Q2.

Who is primarily responsible for preventing Escaped Defects?

A. Only QA

B. Only Developers

C. The entire Scrum Team

Q3.

Which practice helps reduce Escaped Defects?

A. Clear acceptance criteria

B. Skipping testing

C. Increasing Sprint length

Q4.

True or False:

A high Velocity automatically means high product quality.

22. Practical Assignment

For your AI Pharmacovigilance Platform, imagine the following production issues:

- AI assigns the wrong MedDRA code.

- Duplicate Detection misses duplicate cases.

- PDF upload fails for files larger than 25 MB.

For each issue, create:

| Defect | Severity | Priority | Possible Root Cause | Prevention |
| --- | --- | --- | --- | --- |

Then answer:

- Which issue is the highest business risk?

- Which team members should be involved in fixing it?

- What process change would prevent similar defects in the future?

23. Lesson Summary

Today we learned:

- What Escaped Defects are.

- How they differ from defects found during testing.

- Why they are a key quality metric.

- How to measure and reduce them.

- The responsibilities of different Agile roles.

- Healthcare and AI-specific quality considerations.

Key Takeaways

- Escaped Defects are bugs discovered after release.

- Quality is a shared responsibility across the Scrum Team.

- Root Cause Analysis should focus on improving the process, not assigning blame.

- Clear requirements and acceptance criteria significantly reduce escaped defects.

Lesson 82: Sprint Predictability (Deep Dive)

Role Perspective: Business Analyst • Product Analyst • Product Manager • Scrum Master • Product Owner • Engineering Manager

Sprint Predictability answers one of the most important business questions:

"Can this team reliably deliver what they plan?"

Managers don't expect perfection—they value consistency and reliable forecasting.

Learning Objectives

By the end of this lesson, you will understand:

- What Sprint Predictability is.

- Why it's more important than high Velocity.

- How to calculate it.

- Why teams miss Sprint Goals.

- How Product Managers use Predictability.

- How Scrum Masters improve it.

- How Jira measures Sprint Predictability.

1. Concept

What is Sprint Predictability?

Simple Definition

Sprint Predictability measures how consistently a Scrum Team delivers the work it committed to during Sprint Planning.

It answers:

"Did we deliver what we said we would?"

2. Why Does Sprint Predictability Exist?

Imagine you are a Product Manager.

You tell the CEO:

"The AI Duplicate Detection feature will be ready this Sprint."

Sprint ends.

Feature is only 50% complete.

Now:

- Customers wait.

- Release plans change.

- Stakeholders lose confidence.

The issue isn't just that work is unfinished—it's that the forecast was unreliable.

Sprint Predictability helps improve trust.

3. Real-Life Analogy

Imagine a courier company.

Every day they promise:

"We will deliver 100 packages."

Scenario A:

| Day | Promised | Delivered |
| --- | --- | --- |
| Monday | 100 | 99 |
| Tuesday | 100 | 101 |
| Wednesday | 100 | 98 |

Very predictable.

Scenario B:

| Day | Promised | Delivered |
| --- | --- | --- |
| Monday | 100 | 45 |
| Tuesday | 100 | 140 |
| Wednesday | 100 | 70 |

Average deliveries may still be close to 100, but customers cannot rely on them.

Consistency matters.

4. Technical Explanation

Formula:

Sprint Predictability (%) =

(Completed Story Points ÷ Committed Story Points) × 100

Example:

Sprint Planning:

Committed:

40 Story Points

Sprint End:

Completed:

36 Story Points

Calculation:

36 ÷ 40 × 100

= 90%

Sprint Predictability:

90%

5. Another Example

Sprint Commitment:

50 Story Points

Completed:

50 Story Points

Predictability:

50 ÷ 50 ×100

=100%

Excellent predictability.

Now another Sprint:

Committed:

60

Completed:

30

Predictability:

30 ÷60 ×100

=50%

This indicates unreliable planning or execution.

6. Visual Example

Sprint Planning

│

▼

Committed

40 Points

│

▼

Sprint Work

│

▼

Completed

36 Points

│

▼

Predictability

90%

7. Why Predictability Matters More Than Velocity

Consider two teams.

Team Alpha

Velocity:

60

Predictability:

45%

Team Beta

Velocity:

35

Predictability:

95%

Which team would a Product Manager prefer?

Usually Team Beta.

Why?

Because reliable forecasting enables:

- Better release planning.

- Better stakeholder communication.

- Better customer commitments.

A fast but unpredictable team creates planning problems.

8. Healthcare Example

Project:

AI Pharmacovigilance Platform

Sprint Goal:

- AI PDF Upload

- MedDRA Search

- Duplicate Detection

Committed:

45 Story Points

Completed:

43 Story Points

Predictability:

96%

Excellent.

Stakeholders can confidently plan training and regulatory activities.

Another Sprint:

Committed:

45

Completed:

20

Predictability:

44%

Questions to investigate:

- Were requirements unclear?

- Did priorities change?

- Were developers unavailable?

- Were stories underestimated?

- Were there external dependencies?

9. AI Product Example

Project:

Medical AI Chatbot

Sprint Goal:

Improve hallucination detection.

Committed:

30 Story Points

During the Sprint:

The AI vendor releases a breaking API update.

Team spends half the Sprint fixing integrations.

Completed:

15 Story Points

Predictability:

50%

Discussion:

Low predictability is understandable, but the Retrospective should identify how to reduce similar disruptions in the future.

10. What Affects Sprint Predictability?

Unrealistic Sprint Planning

Taking too much work.

Poor Estimation

Story Points don't reflect actual complexity.

Scope Changes

New work added mid-Sprint.

Team Absence

Unexpected leave.

Dependencies

Waiting for another team.

Technical Debt

Unexpected refactoring.

Production Support

Developers pulled away for urgent incidents.

11. Sprint Predictability vs Velocity

| Velocity | Predictability |
| --- | --- |
| Measures completed work | Measures forecasting accuracy |
| Story Points | Percentage |
| Planning tool | Reliability tool |
| Team capacity | Delivery consistency |

Example:

Sprint A:

Velocity:

40

Predictability:

100%

Sprint B:

Velocity:

60

Predictability:

50%

Higher Velocity doesn't necessarily mean better performance.

12. Sprint Goal vs Sprint Predictability

Suppose the Sprint Goal is:

"Enable AI to extract patient demographics."

Stories:

- PDF Upload

- Patient Name Extraction

- Age Detection

- Gender Detection

If only PDF Upload is completed:

Story completion may look acceptable.

Sprint Goal is not achieved.

Modern Scrum emphasizes Sprint Goal achievement, not just Story Point completion.

13. How Scrum Masters Improve Predictability

- Better Sprint Planning.

- Remove blockers quickly.

- Protect the Sprint from unnecessary scope changes.

- Improve estimation skills.

- Facilitate Retrospectives.

- Encourage smaller user stories.

14. How Product Owners Improve Predictability

- Prioritize effectively.

- Clarify requirements.

- Avoid changing priorities during the Sprint.

- Prepare backlog items before Sprint Planning.

15. How Business Analysts Improve Predictability

Business Analysts contribute by:

- Writing complete user stories.

- Defining clear acceptance criteria.

- Resolving stakeholder questions early.

- Reducing requirement ambiguity.

Better requirements reduce surprises.

16. Jira Example

Jira Sprint Report:

Sprint 21

Committed:

42 Story Points

Completed:

39 Story Points

Added Mid-Sprint:

5 Story Points

Removed:

3 Story Points

Predictability:

93%

A Scrum Master may notice frequent mid-Sprint additions and discuss this during the Retrospective.

17. Common Mistakes

Mistake 1

Trying to achieve 100% every Sprint.

Reality:

Unexpected events happen.

A consistent range (for example, around 85–100%) is often healthier than forcing perfection.

Mistake 2

Adding work during the Sprint.

Frequent additions reduce predictability.

Mistake 3

Overcommitting.

Teams sometimes commit to impress stakeholders.

Result:

Missed Sprint Goals.

Mistake 4

Measuring individuals.

Sprint Predictability belongs to the team, not to a single developer.

18. Best Practices

✔ Use historical Velocity during Sprint Planning.

✔ Keep stories small.

✔ Avoid changing Sprint scope.

✔ Prepare backlog items before Sprint Planning.

✔ Analyze missed commitments during Retrospectives.

✔ Focus on delivering the Sprint Goal.

19. Interview Questions

Q1. What is Sprint Predictability?

Answer:

Sprint Predictability measures how consistently a Scrum Team delivers the work it committed to during Sprint Planning.

Q2. Why is Sprint Predictability important?

Answer:

It builds trust with stakeholders, improves forecasting, and supports more reliable release planning.

Q3. Can a team have high Velocity but poor Predictability?

Answer:

Yes. A team may complete a lot of work overall but frequently miss what it originally committed to.

Q4. How can Sprint Predictability be improved?

Answer:

By improving estimation, keeping user stories small, reducing scope changes, preparing the backlog well, and removing impediments quickly.

20. Mini Quiz

Q1.

Sprint Predictability measures:

A. Code quality

B. Forecast accuracy

C. Customer satisfaction

Q2.

Committed:

40 Story Points

Completed:

32 Story Points

Predictability?

A. 60%

B. 70%

C. 80%

Q3.

Which practice improves Sprint Predictability?

A. Adding work every day

B. Stable Sprint scope

C. Measuring developers individually

Q4.

True or False:

High Velocity automatically means high Sprint Predictability.

21. Practical Assignment

For your AI Pharmacovigilance Platform, design three Sprints.

Create a table:

| Sprint | Committed Points | Completed Points | Predictability |
| --- | --- | --- | --- |
| Sprint 1 |  |  |  |
| Sprint 2 |  |  |  |
| Sprint 3 |  |  |  |

Then answer:

- Which Sprint had the highest Predictability?

- Why did another Sprint perform worse?

- What changes would improve future Sprint Predictability?

22. Lesson Summary

Today we learned:

- What Sprint Predictability is.

- How to calculate it.

- Why consistency is more valuable than occasional high output.

- The relationship between Velocity, Sprint Goals, and Predictability.

- How each Agile role contributes to improving predictability.

Key Takeaways

- Sprint Predictability measures how reliably a team delivers its Sprint commitment.

- Reliable teams are easier to plan around than simply fast teams.

- Stable Sprint scope and good backlog preparation improve predictability.

- Focus on achieving the Sprint Goal, not just maximizing Story Points.

- Use Sprint Predictability to improve planning—not to blame the team.

Lesson 83: Burndown Chart (Masterclass)

Role Perspective: Business Analyst • Product Owner • Scrum Master • Product Manager • Engineering Manager

The Burndown Chart is one of the most recognized Agile charts.

However, many people know how to look at it but not how to interpret it. In interviews, you're often shown a Burndown Chart and asked:

"What do you think is happening in this Sprint?"

This lesson will teach you to answer that confidently.

Learning Objectives

By the end of this lesson, you will be able to:

- Understand what a Burndown Chart is.

- Read and interpret different Burndown patterns.

- Explain the difference between the Ideal Line and the Actual Line.

- Identify common delivery problems.

- Use Burndown Charts in Scrum and Jira.

- Know when a Burndown Chart is useful—and when it is misleading.

1. Concept

What is a Burndown Chart?

Simple Definition

A Burndown Chart is a graph that shows how much work remains in the Sprint over time.

It answers:

"Are we on track to finish our Sprint work?"

Notice that it shows remaining work, not completed work.

2. Why Does a Burndown Chart Exist?

Imagine you're halfway through a two-week Sprint.

The Scrum Master asks:

"Are we likely to finish all planned work?"

Without a Burndown Chart:

- Everyone guesses.

- Opinions differ.

With a Burndown Chart:

- You can see the trend.

- You can identify risks early.

- You can take corrective action before the Sprint ends.

3. Real-Life Analogy

Imagine climbing down a mountain.

You start at:

1000 meters

Every hour you descend.

Eventually you reach:

0 meters

Your remaining distance decreases over time.

A Burndown Chart works the same way.

Instead of remaining distance, it tracks remaining work.

4. Technical Explanation

The chart has two axes.

X-Axis

Time

Usually:

Sprint Days

Example:

Day 1

Day 2

Day 3

...

Day 10

Y-Axis

Remaining Work

Usually measured in:

- Story Points

- Hours

- Tasks

Most Scrum teams use Story Points.

5. Example

Sprint:

10 Days

Committed:

50 Story Points

Initial chart:

Remaining Work

50 ●

45 |

40 |

35 |

30 |

25 |

20 |

15 |

10 |

5 |

0 +---------------------------->

D1 D2 D3 D4 D5 D6 D7 D8 D9 D10

The goal:

Reach 0 on the final day.

6. Ideal Burndown Line

An ideal Sprint looks like this:

Remaining Work

50 ●

45 |\

40 | \

35 |  \

30 |   \

25 |    \

20 |     \

15 |      \

10 |       \

5 |        \

0 +---------\---------------->

D1      D5           D10

A straight downward line.

Reality is rarely this perfect.

7. Actual Burndown Line

Real projects look like:

Remaining Work

50 ●

45 |

40 |_____

35 |     \

30 |      \

25 |       \__

20 |          \

15 |           \

10 |            \

5 |             \

0 +--------------------------->

Notice:

No work appears completed for several days.

Then many stories finish together.

This is common when:

- Testing happens late.

- Teams complete stories only after integration.

- Work is started but not finished.

8. Example: AI Pharmacovigilance Platform

Sprint Goal:

Build:

- Login

- PDF Upload

- MedDRA Coding

Sprint Commitment:

40 Story Points

Daily Remaining Work:

| Day | Remaining |
| --- | --- |
| 1 | 40 |
| 2 | 38 |
| 3 | 35 |
| 4 | 30 |
| 5 | 28 |
| 6 | 20 |
| 7 | 18 |
| 8 | 12 |
| 9 | 5 |
| 10 | 0 |

The Burndown shows a healthy trend.

9. Healthcare Example

Project:

Hospital Management System

Sprint:

Appointment Booking

Burndown:

50

45

45

45

45

20

15

10

5

0

Question:

Why was there no progress for four days?

Possible reasons:

- Stories too large.

- Testing delayed.

- Code review backlog.

- Work completed but not accepted.

10. AI Product Example

Project:

Medical AI Chatbot

Sprint Goal:

Improve hallucination detection.

Burndown:

40

40

40

39

38

37

15

10

5

0

Interpretation:

Early work involved:

- Research.

- Prompt experiments.

- Model evaluation.

Most Story Points were completed only after validation.

This pattern can be normal in AI projects, but the team should examine whether stories can be split into smaller increments.

11. Common Burndown Patterns

Pattern 1: Healthy

50

45

40

35

30

25

20

15

10

5

0

Meaning:

Consistent delivery.

Pattern 2: Flat Line

50

50

50

50

50

50

50

30

10

0

Meaning:

Nothing is reaching "Done."

Possible causes:

- Large stories.

- Delayed testing.

- Work in progress too high.

Pattern 3: Steep Drop at End

50

50

48

47

46

45

20

10

5

0

Meaning:

Stories completed only at the end.

Possible causes:

- Batch testing.

- Late integration.

- Late acceptance.

Pattern 4: Burndown Goes Up

40

38

42

39

36

30

20

10

0

Remaining work increased!

Possible reasons:

- New stories added.

- Re-estimation.

- Scope change.

This is not always bad, but the team should understand why it happened.

Pattern 5: Never Reaches Zero

40

38

36

35

34

30

28

25

20

15

Sprint ends.

Work remains.

Possible causes:

- Overcommitment.

- Poor estimation.

- Blockers.

- Dependencies.

12. Burndown vs Velocity

| Burndown | Velocity |
| --- | --- |
| Tracks remaining work during a Sprint | Measures completed Story Points after a Sprint |
| Daily progress | Sprint summary |
| Visual trend | Numerical measure |
| Detects problems early | Helps forecast future Sprints |

13. Burndown vs Burnup

Burndown:

Shows:

Remaining Work

Starts high.

Ends at zero.

Burnup:

Shows:

Completed Work

Starts at zero.

Moves upward.

We'll study Burnup in the next lesson.

14. Jira Burndown Chart

Jira automatically creates a Burndown Report.

Typical view:

Sprint Burndown

Ideal Line

──────────────

Actual Line

─────╲____╲____

The report also shows:

- Scope changes.

- Added issues.

- Removed issues.

- Remaining Story Points.

As a BA or Product Manager, use this report to discuss trends—not to blame the team.

15. Common Mistakes

Mistake 1

Using the Burndown Chart to judge individual developers.

The Burndown reflects team progress, not personal performance.

Mistake 2

Expecting a perfectly straight line.

Real Sprints involve:

- Reviews.

- Testing.

- Discovery.

- Dependencies.

Small variations are normal.

Mistake 3

Ignoring scope changes.

If work is added mid-Sprint, the Burndown changes.

Interpret the chart in context.

Mistake 4

Starting many stories but finishing none.

Burndown only decreases when stories reach Done.

Work that is 90% complete still counts as unfinished.

16. Best Practices

✔ Finish stories before starting new ones.

✔ Keep user stories small.

✔ Update Jira daily.

✔ Discuss Burndown during the Daily Scrum.

✔ Use Burndown to identify risks early.

✔ Focus on the Sprint Goal, not just the chart.

17. Interview Questions

Q1. What is a Burndown Chart?

Answer:

A Burndown Chart is a graph showing the amount of remaining work in a Sprint over time, helping teams track progress toward the Sprint Goal.

Q2. What does a flat Burndown indicate?

Answer:

It often indicates that work is not reaching "Done," possibly due to large stories, delayed testing, or excessive Work in Progress.

Q3. Why might a Burndown line increase?

Answer:

Because additional work was added to the Sprint or estimates were revised upward.

Q4. Does a Burndown Chart measure productivity?

Answer:

No. It measures Sprint progress, not individual productivity.

18. Mini Quiz

Q1.

A Burndown Chart shows:

A. Completed work

B. Remaining work

C. Team size

Q2.

A flat Burndown usually means:

A. Everything is complete

B. Work is not reaching "Done"

C. Velocity is increasing

Q3.

If the Burndown line rises, it may indicate:

A. Scope was added

B. Developers worked faster

C. Testing finished

Q4.

True or False:

A perfectly straight Burndown line is expected in every Sprint.

19. Practical Assignment

For your AI Pharmacovigilance Platform, assume:

- Sprint length: 10 days

- Sprint commitment: 50 Story Points

Create a table:

| Day | Remaining Story Points |
| --- | --- |
| 1 | 50 |
| 2 |  |
| 3 |  |
| ... |  |
| 10 | 0 |

Then answer:

- Is your Burndown healthy, flat, or irregular?

- If it becomes flat on Days 4–6, what could be the cause?

- What actions would you take as a Scrum Master or Product Manager?

20. Lesson Summary

Today we learned:

- What a Burndown Chart is.

- How to read it.

- Common Burndown patterns.

- How to interpret deviations.

- The relationship between Burndown, Velocity, and Burnup.

- How Jira generates Burndown Reports.

Key Takeaways

- A Burndown Chart tracks remaining work, not completed work.

- It is an early warning system for Sprint progress.

- Flat or rising lines often indicate bottlenecks or scope changes.

- Use Burndown to guide conversations and improvements—not to judge people.

- Always interpret the chart alongside Sprint context and the Sprint Goal.

Lesson 84: Burnup Chart (Masterclass)

Role Perspective: Business Analyst • Product Owner • Product Manager • Scrum Master • Engineering Manager

Many experienced Product Managers prefer Burnup Charts over Burndown Charts because they clearly show both progress and scope changes.

If your CEO asks:

"Why isn't the release finished yet?"

A Burndown Chart may not tell the full story.

A Burnup Chart often can.

Learning Objectives

By the end of this lesson, you will be able to:

- Understand what a Burnup Chart is.

- Read and interpret Burnup Charts.

- Explain the difference between Burnup and Burndown.

- Detect scope changes.

- Use Burnup Charts for release planning.

- Interpret Jira Burnup reports.

- Answer Burnup interview questions confidently.

1. Concept

What is a Burnup Chart?

Simple Definition

A Burnup Chart is a graph that shows:

- How much work has been completed (Completed Work Line)

- How much total work exists (Total Scope Line)

It answers two important questions:

- How much work have we completed?

- Has the project scope changed?

2. Why Does a Burnup Chart Exist?

Imagine your Product Manager says:

"We completed 80 Story Points this month."

Great.

But another team added 50 new Story Points.

The project still feels far from completion.

A Burndown Chart only shows remaining work.

It doesn't clearly explain why remaining work increased.

A Burnup Chart shows:

- Progress

- Scope growth

Both on the same graph.

3. Real-Life Analogy

Imagine filling a water tank.

Tank capacity:

100 liters

Every hour:

You add water.

But sometimes:

The tank size increases because the customer wants a larger tank.

Now:

- Water level increases.

- Tank capacity also increases.

Burnup Chart shows both.

4. Technical Explanation

A Burnup Chart contains two lines.

Line 1

Completed Work

Starts at:

0

Moves upward.

Line 2

Total Scope

Usually stays constant.

Unless new work is added.

Example:

Sprint begins.

Total scope:

100 Story Points

Completed:

0

Chart:

Scope

100 ───────────────────────────

Completed

0

As work finishes:

Completed line rises.

5. Visual Example

Story Points

100 |------------------------------- Scope

90 |

80 |

70 |

60 |

50 |                     /

40 |                  /

30 |               /

20 |            /

10 |         /

0 +------------------------------------>

D1 D2 D3 D4 D5 D6 D7 D8 D9 D10

The project is complete when:

Completed line touches Scope line.

6. Scope Change Example

Initial scope:

100 Story Points

Day 5:

Customer requests:

AI Duplicate Detection

Adds:

20 Story Points

New scope:

120

Chart:

Story Points

120 |---------------------------- Scope

100 |-------------|

80 |

60 |               /

40 |            /

20 |         /

0 +----------------------------------->

Notice:

The scope line moved upward.

This immediately explains why completion takes longer.

7. AI Pharmacovigilance Example

Initial backlog:

| Feature | Story Points |
| --- | --- |
| Login | 8 |
| PDF Upload | 13 |
| AI Extraction | 21 |
| MedDRA Coding | 21 |
| Dashboard | 17 |

Total:

80 Story Points

Mid-project:

Regulatory team requests:

Audit Trail

Adds:

15 Story Points

New scope:

95 Story Points

The Burnup Chart clearly shows:

- Work completed

- Scope increased

Without it, stakeholders may incorrectly assume the team slowed down.

8. Healthcare Example

Hospital Management System

Initial scope:

150 Story Points

Halfway through the release:

Government introduces a new compliance rule.

Additional work:

30 Story Points

Burnup Chart:

- Completed work continues upward.

- Scope line jumps from 150 to 180.

The Product Manager can explain:

"The team is progressing steadily. The release moved because the project scope increased."

9. AI Product Example

Project:

Medical AI Chatbot

Initial scope:

120 Story Points

After user testing:

Customers request:

- Voice Input

- Multiple Languages

- Medical Report Summaries

Scope increases:

120 → 170 Story Points

Burnup Chart makes this transparent.

10. Burnup vs Burndown

| Burnup | Burndown |
| --- | --- |
| Shows completed work | Shows remaining work |
| Clearly shows scope changes | Scope changes are harder to interpret |
| Easier for release planning | Better for Sprint tracking |
| Often preferred by Product Managers | Commonly used by Scrum Teams |

11. Why Product Managers Love Burnup Charts

Imagine the CEO asks:

"Why is the release delayed?"

Burnup Chart answers:

Option A:

Team completed only 30%.

OR

Option B:

Team completed 80%.

But scope increased by 40%.

Very different situations.

Burnup provides context.

12. Reading a Burnup Chart

Healthy Pattern

Scope

────────────────────

Completed

/

/

/

/

/

Meaning:

Consistent progress.

Scope Increase

Scope

───────────────

─────────

Completed

/

/

/

/

Meaning:

Requirements changed.

Flat Completed Line

Completed

______

______

Meaning:

No stories reached "Done."

Possible causes:

- Large stories.

- Testing delays.

- High WIP.

Slow Progress

Completed line rises slowly.

Possible reasons:

- Dependencies.

- Understaffing.

- Technical debt.

- Production support.

13. Release Forecast Example

Backlog:

200 Story Points

Average Velocity:

25

Expected release:

200 ÷25

=8 Sprints

Now:

Customer adds:

50 Story Points

New backlog:

250

Forecast:

250 ÷25

=10 Sprints

Burnup Chart visually supports this change.

14. Jira Burnup Report

Jira offers Burnup reports (especially in Advanced Roadmaps and some marketplace apps).

Typical chart:

Scope Line

────────────────────

Completed Line

/

/

/

/

You can quickly identify:

- Total scope.

- Completed work.

- Scope additions.

- Release readiness.

15. Common Mistakes

Mistake 1

Confusing Burnup with Burndown.

Remember:

Burnup goes up.

Burndown goes down.

Mistake 2

Ignoring scope changes.

If scope doubles, the team may still be performing well.

Mistake 3

Using Burnup to evaluate individuals.

Burnup reflects team progress, not individual performance.

Mistake 4

Assuming more completed Story Points always mean more customer value.

Not necessarily.

A small high-value feature may be more impactful than many low-value features.

16. Best Practices

✔ Review Burnup weekly.

✔ Explain scope changes to stakeholders.

✔ Separate planned work from added work.

✔ Use Burnup during Release Planning.

✔ Pair Burnup with Velocity for forecasting.

17. Interview Questions

Q1. What is a Burnup Chart?

Answer:

A Burnup Chart shows completed work and total project scope over time, helping teams visualize progress and scope changes.

Q2. Why do Product Managers often prefer Burnup Charts?

Answer:

Because Burnup Charts clearly distinguish between slow delivery and increased project scope, making stakeholder communication easier.

Q3. What does an upward jump in the scope line indicate?

Answer:

Additional work was added to the project or release.

Q4. When would you use Burnup instead of Burndown?

Answer:

Burnup is especially useful for release planning and long-running projects where scope changes are expected.

18. Mini Quiz

Q1.

A Burnup Chart primarily shows:

A. Remaining work

B. Completed work and total scope

C. Team size

Q2.

If the Scope Line suddenly rises, it usually means:

A. Team productivity increased

B. Additional work was added

C. Velocity increased

Q3.

Which chart better explains scope changes?

A. Burndown

B. Burnup

C. Velocity Chart

Q4.

True or False:

A Burnup Chart reaches completion when the Completed Work line meets the Total Scope line.

19. Practical Assignment

For your AI Pharmacovigilance Platform, assume:

Initial Release Scope:

100 Story Points

Midway through the release:

- Audit Trail = 10 Story Points

- WHO Drug Coding Enhancement = 15 Story Points

Create a table:

| Week | Completed Story Points | Total Scope |
| --- | --- | --- |
| 1 | 10 | 100 |
| 2 | 25 | 100 |
| 3 | 40 | 125 |
| 4 | 60 | 125 |
| 5 | 85 | 125 |
| 6 | 125 | 125 |

Then answer:

- Why did the release take longer?

- Was the team's delivery speed poor, or did the scope change?

- How would you explain this to stakeholders?

20. Lesson Summary

Today we learned:

- What a Burnup Chart is.

- How to interpret Completed Work and Total Scope lines.

- Why Burnup is useful for release planning.

- The differences between Burnup and Burndown.

- How Burnup helps explain scope changes.

- How Product Managers use Burnup to communicate with stakeholders.

Key Takeaways

- Burnup Charts show completed work and total scope.

- They make scope changes visible and easier to explain.

- They are especially valuable for release planning and stakeholder communication.

- A project can appear delayed because of increased scope—not because the team slowed down.

- Always interpret Burnup together with Velocity and business priorities.

Lesson 85: Cumulative Flow Diagram (CFD) (Masterclass)

Role Perspective: Business Analyst • Product Manager • Scrum Master • Engineering Manager • Agile Coach

If the Burndown Chart tells you "Are we finishing work?", the Cumulative Flow Diagram tells you "How is work flowing through the system?"

Companies like Amazon, Microsoft, Spotify, Atlassian, and many large healthcare organizations use CFDs to identify bottlenecks before they become major problems.

Learning Objectives

By the end of this lesson, you will be able to:

- Understand what a Cumulative Flow Diagram (CFD) is.

- Read every part of a CFD.

- Identify bottlenecks.

- Detect excessive Work in Progress (WIP).

- Understand the relationship between CFD, Lead Time, Cycle Time, and Throughput.

- Use CFDs in Jira and Azure DevOps.

- Answer CFD interview questions confidently.

1. Concept

What is a Cumulative Flow Diagram?

Simple Definition

A Cumulative Flow Diagram (CFD) is a chart that shows how work moves through different stages of your workflow over time.

Unlike a Burndown Chart, which focuses on remaining work, a CFD shows:

- How much work is waiting.

- How much work is in progress.

- How much work is completed.

- Whether work is flowing smoothly.

2. Why Does CFD Exist?

Imagine your Product Manager says:

"We completed only 15 stories this Sprint."

The next question is:

"Why?"

Possible reasons:

- Too much work waiting.

- Testing is overloaded.

- Code reviews are delayed.

- Developers started too many tasks.

A CFD helps answer these questions visually.

3. Real-Life Analogy

Imagine a hospital emergency department.

Patients move through stages:

Registration

↓

Doctor Assessment

↓

Lab Tests

↓

Treatment

↓

Discharge

If many patients are waiting for lab tests, the queue grows.

This indicates a bottleneck in the lab—not that doctors are working slowly.

A CFD works exactly the same way for software delivery.

4. Technical Explanation

A CFD tracks the number of work items in each workflow state.

Example workflow:

To Do

↓

In Progress

↓

Code Review

↓

Testing

↓

Done

Each stage is represented by a colored band (or layer) on the chart.

The height of each band shows how many items are in that stage.

5. Anatomy of a CFD

Number of Work Items

40 |████████████████████████ Done

35 |██████████████████ Testing

30 |██████████████ Code Review

25 |██████████ In Progress

20 |██████ To Do

+------------------------------------>

Week1 Week2 Week3 Week4 Week5

Each colored layer represents one workflow stage.

The total height represents all work items in the system.

6. Understanding the Bands

Narrow Band

Testing

██

Good.

Work is moving quickly.

Wide Band

Testing

██████████████████

Warning.

Too much work is waiting in testing.

Possible causes:

- Too few testers.

- Manual testing delays.

- Complex regression testing.

7. Healthcare Example

Project:

Hospital Management System

Workflow:

Requirements

↓

Development

↓

Testing

↓

Deployment

CFD:

Testing

████████████████████

Interpretation:

Testing queue is growing.

The team should investigate:

- Do we need more automated tests?

- Are requirements causing rework?

- Is QA overloaded?

8. AI Product Example

Project:

Medical AI Chatbot

Workflow:

Design

↓

Prompt Engineering

↓

Model Evaluation

↓

Human Review

↓

Done

CFD shows:

Human Review

██████████████████

Interpretation:

The Human Review stage is the bottleneck.

Possible improvements:

- Increase reviewers.

- Improve AI confidence thresholds.

- Automate low-risk approvals.

9. Pharmacovigilance Example

Project:

AI Pharmacovigilance Platform

Workflow:

Requirement

↓

Development

↓

Medical Validation

↓

Compliance Review

↓

Production

CFD:

Compliance Review

█████████████████████

Interpretation:

Compliance approvals are slowing delivery.

This may be expected in regulated environments, but the team could:

- Schedule reviews earlier.

- Define standard approval checklists.

- Reduce unnecessary review cycles.

10. What Can a CFD Tell You?

Bottlenecks

Large bands indicate work accumulating.

Stable Flow

Bands remain roughly the same width over time.

Good sign.

Increasing WIP

"In Progress" band keeps growing.

Team is starting work faster than it finishes.

Low Throughput

"Done" band grows slowly.

Few items are reaching completion.

Long Lead Time

Wide bands usually indicate longer waiting times.

11. CFD and Work in Progress (WIP)

Suppose:

In Progress

██████████████████████

Developers have started 25 stories.

Only 2 stories are completed.

This is excessive WIP.

Better practice:

Finish existing stories before starting new ones.

12. CFD and Lead Time

If the distance between:

To Do

and

Done

becomes wider over time,

Lead Time is increasing.

Customers wait longer.

13. CFD and Cycle Time

If:

In Progress

↓

Done

takes longer,

Cycle Time increases.

The CFD helps reveal where the delay occurs.

14. CFD and Throughput

Throughput measures:

Completed items per unit of time.

On a CFD:

A steadily growing "Done" band indicates healthy throughput.

A flat "Done" band suggests work is not being completed.

15. Good CFD Example

Done

██████████████████████

Testing

████

Development

████

To Do

████

Characteristics:

- Similar band widths.

- No major queues.

- Smooth flow.

16. Poor CFD Example

Done

██████

Testing

██████████████████████

Development

██████████████████

To Do

██

Interpretation:

Testing and Development are overloaded.

The team should focus on finishing work instead of starting more.

17. Jira Example

Jira and Azure DevOps can generate CFDs automatically.

Typical workflow:

Backlog

↓

Selected

↓

Development

↓

Testing

↓

Done

The CFD updates as issues move between columns.

During Sprint Reviews or Retrospectives, the Scrum Team can discuss:

- Which stage is growing?

- Why is work waiting?

- How can we improve flow?

18. Common Mistakes

Mistake 1

Looking only at the "Done" band.

You should examine every stage.

Mistake 2

Ignoring growing queues.

Large queues often mean hidden delays.

Mistake 3

Treating a CFD as a productivity chart.

A CFD measures flow, not individual performance.

Mistake 4

Trying to maximize WIP.

Starting more work rarely improves delivery.

Finishing work does.

19. Best Practices

✔ Limit Work in Progress.

✔ Monitor bottlenecks regularly.

✔ Keep workflow stages clearly defined.

✔ Automate repetitive steps where possible.

✔ Review CFDs during Retrospectives.

✔ Combine CFDs with Lead Time and Throughput metrics.

20. Interview Questions

Q1. What is a Cumulative Flow Diagram?

Answer:

A CFD is a visualization showing the number of work items in each workflow stage over time, helping teams understand flow and identify bottlenecks.

Q2. What does a widening band indicate?

Answer:

Work is accumulating in that stage, indicating a potential bottleneck.

Q3. Why is a CFD useful?

Answer:

It helps teams monitor flow, identify delays, manage WIP, and improve overall delivery efficiency.

Q4. How does a CFD differ from a Burndown Chart?

Answer:

A Burndown Chart shows remaining work over time, while a CFD shows how work is distributed across workflow stages and highlights bottlenecks.

21. Mini Quiz

Q1.

A CFD primarily helps identify:

A. Team salaries

B. Workflow bottlenecks

C. Customer satisfaction

Q2.

A widening "Testing" band most likely indicates:

A. Faster testing

B. Testing bottleneck

C. Reduced scope

Q3.

What usually happens when WIP becomes too high?

A. Flow improves automatically

B. More work waits in the system

C. Lead Time decreases

Q4.

True or False:

A CFD is primarily used to measure individual developer performance.

22. Practical Assignment

For your AI Pharmacovigilance Platform, use this workflow:

Backlog

↓

Development

↓

Medical Validation

↓

Compliance Review

↓

Done

Imagine the following number of items after one week:

| Stage | Items |
| --- | --- |
| Backlog | 15 |
| Development | 8 |
| Medical Validation | 4 |
| Compliance Review | 12 |
| Done | 10 |

Answer:

- Which stage is the bottleneck?

- What impact will it have on Lead Time?

- How would you improve the workflow?

- Which Agile role should take the lead in addressing this issue?

23. Lesson Summary

Today we learned:

- What a Cumulative Flow Diagram is.

- How to interpret workflow stages.

- How to identify bottlenecks.

- The relationship between CFDs, WIP, Lead Time, Cycle Time, and Throughput.

- How Jira and Azure DevOps use CFDs.

- Why CFDs are especially valuable for continuous improvement.

Key Takeaways

- A CFD visualizes how work flows through each stage of the process.

- Wide bands usually indicate bottlenecks or excessive waiting.

- Stable band widths suggest a healthy and balanced workflow.

- Limit Work in Progress to improve flow and reduce delays.

- Use CFDs to improve the process—not to evaluate individuals.

Lesson 86: Throughput (Masterclass)

Role Perspective: Business Analyst • Product Manager • Scrum Master • Agile Coach • Engineering Manager

Throughput answers one simple but powerful question:

"How many work items does the team complete in a given period?"

Unlike Velocity, Throughput doesn't care about Story Points. It focuses on finished work, making it especially useful in Kanban, Lean, DevOps, and AI product teams.

Learning Objectives

By the end of this lesson, you will be able to:

- Understand what Throughput is.

- Calculate Throughput.

- Differentiate Throughput from Velocity.

- Use Throughput for forecasting.

- Understand its role in Scrum and Kanban.

- Learn the basics of Monte Carlo Forecasting.

- Apply Throughput to Healthcare and AI projects.

- Answer common interview questions.

1. Concept

What is Throughput?

Simple Definition

Throughput is the number of work items completed in a specific period of time.

It answers:

"How many items did we finish?"

Notice that Throughput measures count, not size.

2. Why Does Throughput Exist?

Imagine two Scrum teams.

Team A

Completed:

- 8 User Stories

Team B

Completed:

- 16 User Stories

At first glance, Team B seems faster.

But what if:

- Team A completed eight large stories.

- Team B completed sixteen very small stories.

Throughput only tells you how many items were completed, not how complex they were.

That is why Throughput and Velocity are complementary metrics.

3. Real-Life Analogy

Imagine a pharmacy.

During one day:

- 150 prescriptions are filled.

The pharmacist doesn't measure:

- How complex each prescription was.

They simply measure:

How many prescriptions were completed today?

That is Throughput.

4. Technical Explanation

Formula:

Throughput = Number of Completed Work Items

Time period examples:

- Per day

- Per week

- Per Sprint

- Per month

Example

Sprint:

2 weeks

Completed:

| Work Item | Status |
| --- | --- |
| Login | Done |
| Dashboard | Done |
| Reports | Done |
| PDF Upload | Done |
| AI Extraction | Done |

Throughput:

5 work items

5. Throughput vs Velocity

| Throughput | Velocity |
| --- | --- |
| Counts completed items | Counts Story Points completed |
| Doesn't consider complexity | Reflects estimated complexity |
| Common in Kanban | Common in Scrum |
| Easier to calculate | Requires estimation |
| Useful for flow | Useful for Sprint planning |

Example

Sprint A:

| Story | Story Points |
| --- | --- |
| Login | 3 |
| Dashboard | 8 |
| Reports | 5 |

Throughput:

3 stories

Velocity:

16 Story Points

Both metrics describe the same Sprint from different perspectives.

6. Healthcare Example

Project:

Hospital Management System

Completed this week:

- Patient Registration

- Appointment Booking

- Billing

- Lab Results

- Doctor Schedule

Throughput:

5 features

Even if one feature was much larger than another, Throughput simply counts completed items.

7. Pharmacovigilance Example

Project:

AI Pharmacovigilance Platform

Completed this Sprint:

- Duplicate Detection

- MedDRA Coding

- WHO Drug Coding

- PDF Upload

- Audit Trail

- User Management

Throughput:

6 completed work items

The Product Manager can compare this with previous Sprints to understand delivery trends.

8. AI Product Example

Project:

Medical AI Chatbot

Completed:

- Prompt Improvement

- Response Logging

- Feedback Screen

- Hallucination Detection

- Voice Input

Throughput:

5 completed features

If the team consistently completes around five items per Sprint, that becomes useful for forecasting.

9. Throughput Trend

Suppose a team's Throughput over six Sprints is:

| Sprint | Throughput |
| --- | --- |
| 1 | 5 |
| 2 | 6 |
| 3 | 5 |
| 4 | 7 |
| 5 | 6 |
| 6 | 5 |

Average Throughput:

(5 + 6 + 5 + 7 + 6 + 5) ÷ 6

= 5.67

You might forecast that the team will complete around 5–6 items per Sprint, assuming work items are of similar size.

10. Throughput and Forecasting

Suppose your backlog contains:

40 user stories.

Average Throughput:

5 stories per Sprint.

Estimated number of Sprints:

40 ÷ 5 = 8 Sprints

Remember:

This is an estimate, not a guarantee.

Changes in scope, team capacity, or story size can affect the outcome.

11. Introduction to Monte Carlo Forecasting

Many modern Agile tools use Monte Carlo Simulation for forecasting.

Instead of asking:

"Exactly when will we finish?"

It asks:

"Based on our historical delivery, what is the most likely completion window?"

Simple Analogy

Imagine tossing a coin thousands of times.

You can't predict the next toss with certainty.

But you can estimate probabilities.

Monte Carlo uses the same idea with historical delivery data.

Example

Historical Throughput:

- Sprint 1 = 5

- Sprint 2 = 6

- Sprint 3 = 4

- Sprint 4 = 7

- Sprint 5 = 5

Instead of saying:

"The release will finish in exactly 8 Sprints."

Monte Carlo may estimate:

- 70% probability: Finished within 8 Sprints.

- 90% probability: Finished within 9 Sprints.

This helps Product Managers communicate uncertainty more honestly.

12. Scrum vs Kanban

Scrum

Primary metric:

Velocity

Secondary metric:

Throughput

Kanban

Primary metric:

Throughput

Because Kanban teams often do not estimate Story Points, Throughput becomes one of the main measures of delivery.

13. Jira Example

Jira dashboards can show:

| Sprint | Completed Issues |
| --- | --- |
| Sprint 1 | 12 |
| Sprint 2 | 14 |
| Sprint 3 | 13 |
| Sprint 4 | 15 |

A Scrum Master can identify trends:

- Stable Throughput

- Increasing Throughput

- Declining Throughput

The focus should be on understanding why, not simply expecting higher numbers every Sprint.

14. Common Mistakes

Mistake 1

Comparing Throughput between different teams.

Different teams:

- Build different products.

- Handle different complexity.

- Define work items differently.

Direct comparisons are often misleading.

Mistake 2

Ignoring work item size.

Completing:

- 10 tiny tasks

is not necessarily better than completing:

- 3 large, high-value features.

Mistake 3

Chasing higher Throughput.

Teams may split work into many tiny tickets just to increase the metric.

This creates misleading data.

Mistake 4

Using Throughput to evaluate individuals.

Throughput is a team metric, not a personal performance measure.

15. Best Practices

✔ Track Throughput over multiple Sprints.

✔ Combine Throughput with Lead Time and Cycle Time.

✔ Keep work items reasonably consistent in size.

✔ Use Throughput for forecasting, not competition.

✔ Discuss unusual changes during Retrospectives.

16. Interview Questions

Q1. What is Throughput?

Answer:

Throughput is the number of work items completed during a specific period of time.

Q2. How does Throughput differ from Velocity?

Answer:

Throughput counts completed work items, while Velocity measures completed Story Points.

Q3. Why is Throughput important in Kanban?

Answer:

Kanban often doesn't use Story Points, so Throughput provides a simple measure of delivery and supports forecasting.

Q4. Can Throughput alone measure team performance?

Answer:

No. It should be interpreted alongside metrics such as Lead Time, Cycle Time, quality metrics, and business value delivered.

17. Mini Quiz

Q1.

Throughput measures:

A. Story Points

B. Completed work items

C. Team size

Q2.

A team completes 8 user stories this Sprint.

Their Throughput is:

A. 8 Story Points

B. 8 work items

C. 16 work items

Q3.

Which framework relies more heavily on Throughput?

A. Kanban

B. Scrum

C. Waterfall

Q4.

True or False:

Throughput should be used to compare individual developer performance.

18. Practical Assignment

For your AI Pharmacovigilance Platform, assume the following completed work items over five Sprints:

| Sprint | Completed Items |
| --- | --- |
| 1 | 6 |
| 2 | 5 |
| 3 | 7 |
| 4 | 6 |
| 5 | 8 |

Now answer:

- What is the average Throughput?

- If 36 user stories remain, how many Sprints would you estimate are needed?

- What factors could make your estimate inaccurate?

- Would you communicate this as a fixed date or as a forecast range? Why?

19. Lesson Summary

Today we learned:

- What Throughput is.

- How it differs from Velocity.

- Why Throughput is central to Kanban.

- How Throughput supports forecasting.

- The basics of Monte Carlo Forecasting.

- Healthcare, Pharmacovigilance, and AI examples.

- Best practices and common pitfalls.

Key Takeaways

- Throughput counts completed work items over time.

- It complements Velocity by focusing on quantity rather than estimated effort.

- Throughput is a core metric in Kanban and Lean environments.

- Historical Throughput helps forecast future delivery, especially when work items are similarly sized.

- Use Throughput to improve planning—not to compare teams or individuals.

Lesson 87: Work in Progress (WIP) (Masterclass)

Role Perspective: Business Analyst • Product Manager • Scrum Master • Agile Coach • Engineering Manager

One of the biggest mistakes Agile teams make is starting too much work instead of finishing work.

High-performing companies like Amazon, Microsoft, Spotify, Toyota, and many healthcare organizations focus on limiting Work in Progress (WIP) because it improves flow, quality, and predictability.

Learning Objectives

By the end of this lesson, you will be able to:

- Understand what Work in Progress (WIP) is.

- Learn why limiting WIP improves delivery.

- Understand Little's Law (in simple terms).

- Use WIP limits in Kanban and Scrum.

- Relate WIP to Lead Time, Cycle Time, Throughput, and Flow Efficiency.

- Apply WIP concepts to Healthcare, Pharmacovigilance, and AI products.

- Answer common interview questions.

1. Concept

What is Work in Progress (WIP)?

Simple Definition

Work in Progress (WIP) is the amount of work that has been started but not yet completed.

Think of WIP as unfinished work.

2. Why Does WIP Exist?

Imagine a developer starts:

- Login

- Dashboard

- Reports

- Notifications

- AI Module

All at the same time.

After one week:

Nothing is finished.

Customers receive zero value.

Now imagine another developer:

- Starts Login.

- Finishes Login.

- Starts Dashboard.

- Finishes Dashboard.

Customers begin receiving usable features much sooner.

This is why Agile emphasizes finishing before starting more work.

3. Real-Life Analogy

Imagine you're cooking dinner.

Scenario A:

You start:

- Rice

- Curry

- Chapati

- Dessert

- Soup

Everything is half done.

Dinner isn't ready.

Scenario B:

You prepare:

- Rice ✔

- Curry ✔

- Chapati ✔

- Soup ✔

- Dessert ✔

The meal is ready sooner, with less confusion.

The second approach keeps WIP low.

4. Technical Explanation

Example Kanban Board:

+------------+---------------+-----------+------+

| To Do      | In Progress   | Testing   | Done |

+------------+---------------+-----------+------+

| Login      | Dashboard     | Reports   | PDF  |

| Billing    | AI Search     |           |      |

| Audit      |               |           |      |

+------------+---------------+-----------+------+

Here:

- In Progress = 2 items

- Testing = 1 item

Current WIP = 3

5. Why High WIP is Dangerous

Imagine:

To Do

↓

Development

↓↓↓↓↓↓↓↓↓↓↓↓↓↓

20 Stories

↓

Testing

↓

Done

Developers start many stories.

Testing becomes overloaded.

Nothing gets completed.

Result:

- Longer Lead Time.

- Lower Flow Efficiency.

- Poor Sprint Predictability.

- Increased defects.

6. Low WIP Example

Development

Story 1

↓

Testing

↓

Done

↓

Story 2

Only a few items are active.

Benefits:

- Faster completion.

- Easier tracking.

- Better quality.

- Reduced context switching.

7. Healthcare Example

Project:

Hospital Management System

Poor WIP:

The team starts:

- Patient Registration

- Billing

- Appointments

- Pharmacy

- Insurance

All remain incomplete.

Doctors cannot use any feature.

Better approach:

Complete:

- Patient Registration

Release it.

Then continue with Billing.

Users receive value sooner.

8. Pharmacovigilance Example

Project:

AI Pharmacovigilance Platform

Instead of building all modules simultaneously:

- Login

- MedDRA Coding

- WHO Drug Coding

- Duplicate Detection

- Signal Detection

The team finishes:

- Login

- PDF Upload

- Basic MedDRA Coding

First.

This enables early user feedback and reduces integration risk.

9. AI Product Example

Project:

Medical AI Chatbot

Poor WIP:

Working simultaneously on:

- Voice Input

- Translation

- Image Analysis

- Hallucination Detection

- Analytics

None are finished.

Better WIP:

Finish:

- Hallucination Detection

Deploy.

Gather feedback.

Then begin Voice Input.

10. WIP Limits

Kanban introduces WIP Limits.

Example:

In Progress (Limit = 3)

✔ Login

✔ Dashboard

✔ Reports

No more work may enter this column until one item leaves.

This encourages teams to finish existing work before starting new work.

11. Why WIP Limits Improve Delivery

Benefits include:

- Shorter Lead Time.

- Better Flow Efficiency.

- Higher Throughput.

- Fewer defects.

- Less multitasking.

- Better collaboration.

12. Little's Law (Simple Explanation)

Little's Law is a foundational concept in Lean and Kanban.

Formula

Lead Time = WIP ÷ Throughput

Where:

- Lead Time = Time from request to completion.

- WIP = Number of items in progress.

- Throughput = Number of items completed per unit of time.

Example

Suppose:

- WIP = 20 stories

- Throughput = 5 stories per week

Lead Time:

20 ÷ 5 = 4 weeks

Now reduce WIP:

- WIP = 10

- Throughput = 5

Lead Time:

10 ÷ 5 = 2 weeks

Reducing WIP often reduces Lead Time.

Note: Little's Law assumes a relatively stable system with consistent arrival and completion rates. It's a useful guide, not an exact prediction for every project.

13. Relationship with Other Metrics

| Metric | Relationship with WIP |
| --- | --- |
| Lead Time | Higher WIP often increases Lead Time |
| Cycle Time | Excessive WIP can increase Cycle Time |
| Throughput | Moderate WIP can support stable Throughput, but excessive WIP often hurts it |
| Flow Efficiency | Lower WIP generally improves Flow Efficiency |
| Sprint Predictability | Lower WIP often improves Predictability |

14. WIP in Scrum

Scrum does not require formal WIP limits.

However, Scrum Teams often apply the same principle:

Instead of:

10 stories started

1 finished

Aim for:

3 stories started

3 stories finished

This supports the Sprint Goal and creates more frequent progress.

15. Jira Example

Jira Kanban Board:

In Progress (Limit = 4)

Login

Dashboard

Reports

AI Search

When four items are already in progress:

No new work should enter until one is completed.

Some teams configure Jira to highlight WIP limit violations.

16. Common Mistakes

Mistake 1

Believing busy people mean productive teams.

Reality:

Many active tasks can hide slow delivery.

Mistake 2

Starting new work whenever someone becomes free.

Sometimes it's better to help finish existing work.

Mistake 3

Ignoring bottlenecks.

If Testing is overloaded, adding more work to Development usually makes the problem worse.

Mistake 4

Using WIP limits as rigid rules.

WIP limits should encourage healthy flow, not prevent urgent work when exceptions are justified.

17. Best Practices

✔ Finish work before starting new work.

✔ Set realistic WIP limits.

✔ Keep user stories small.

✔ Swarm on blocked work (have team members collaborate to finish it).

✔ Monitor bottlenecks regularly.

✔ Review WIP during Daily Scrums.

18. Interview Questions

Q1. What is Work in Progress (WIP)?

Answer:

WIP is the number of work items that have been started but are not yet completed.

Q2. Why are WIP limits important?

Answer:

They help reduce multitasking, improve flow, shorten Lead Time, and encourage teams to finish work before starting more.

Q3. What is Little's Law?

Answer:

Little's Law relates Lead Time, Work in Progress, and Throughput:

Lead Time = WIP ÷ Throughput (under stable system conditions).

Q4. Does Scrum require WIP limits?

Answer:

No. WIP limits are a core Kanban practice, but Scrum Teams often adopt similar principles to improve flow.

19. Mini Quiz

Q1.

WIP stands for:

A. Work in Progress

B. Work Improvement Plan

C. Weekly Improvement Process

Q2.

High WIP usually leads to:

A. Shorter Lead Time

B. More multitasking and longer Lead Time

C. Automatically higher Velocity

Q3.

According to Little's Law, if Throughput stays the same and WIP decreases, Lead Time will generally:

A. Increase

B. Decrease

C. Stay exactly the same in every situation

Q4.

True or False:

A team should always start as many tasks as possible to maximize productivity.

20. Practical Assignment

For your AI Pharmacovigilance Platform, imagine this Kanban board:

| Stage | Items |
| --- | --- |
| To Do | 12 |
| Development | 8 |
| Testing | 7 |
| Done | 5 |

Answer:

- What is the current WIP?

- Which stage appears to be the bottleneck?

- If the Development WIP limit is 5, what action should the team take?

- As a Scrum Master or Product Manager, what process improvements would you suggest?

21. Lesson Summary

Today we learned:

- What Work in Progress (WIP) is.

- Why limiting WIP improves delivery.

- The basics of Little's Law.

- The relationship between WIP and other Agile metrics.

- How WIP limits work in Kanban and can benefit Scrum teams.

- Practical examples from Healthcare, Pharmacovigilance, and AI products.

Key Takeaways

- WIP is work that has started but is not yet finished.

- High WIP often creates delays, bottlenecks, and lower quality.

- Limiting WIP improves flow, focus, and predictability.

- Little's Law links WIP, Throughput, and Lead Time.

- Successful Agile teams prioritize finishing work over starting more work.

Lesson 88: Interpreting Agile Metrics & Charts Together (Advanced Masterclass)

Role Perspective: Business Analyst • Product Manager • Scrum Master • Agile Coach

In real organizations, nobody looks at one metric alone.

A senior Agile professional does not say:

"Velocity decreased, so the team is bad."

Instead, they connect multiple signals:

Velocity + Burndown + CFD + Lead Time + Cycle Time + Throughput + Quality Metrics

and understand the complete story.

Learning Objectives

By the end of this lesson, you will learn:

- Why one Agile metric is never enough.

- How to combine metrics for decision-making.

- How Scrum Masters analyze team health.

- How Product Managers use metrics for forecasting.

- How to interpret common chart patterns.

- Healthcare and AI product examples.

- Interview-level scenario analysis.

1. Concept

What does "Interpreting Metrics Together" mean?

It means:

Instead of asking:

"What does this one chart show?"

We ask:

"What story are all metrics telling together?"

Example:

Velocity decreased.

Is that bad?

Not necessarily.

Maybe:

- Story quality improved.

- Defects reduced.

- Team spent time fixing technical debt.

One metric alone can mislead.

2. Why Does This Exist?

Agile metrics are signals, not answers.

A metric tells you:

"Something is happening."

It does not automatically tell:

"Why it is happening."

The Agile professional investigates the reason.

3. Real-Life Analogy

Imagine a patient's health report.

Doctor does not look only at:

- Temperature

They check:

- Blood pressure

- Heart rate

- Blood tests

- Symptoms

- Medical history

One value is not enough.

Agile metrics work the same way.

4. Agile Metrics Relationship Map

BUSINESS VALUE

|

|

Product Outcomes

|

--------------------------------

|                              |

Delivery Flow                 Quality

|                              |

|                              |

Velocity                       Escaped Defects

Throughput                    Test Quality

Cycle Time

Lead Time

|

|

WIP

|

|

CFD

5. Scenario 1: Velocity Decreased

Situation

Previous Sprint:

Velocity = 40 points

Current Sprint:

Velocity = 25 points

A manager says:

"The team performance dropped."

Should we agree?

No.

Let's investigate.

Check Other Metrics

Burndown

Healthy?

✅ Yes

Work finished continuously.

Escaped Defects

Reduced:

20 → 5

Good.

Cycle Time

Reduced:

8 days → 4 days

Good.

Interpretation

The team may have delivered better quality with smaller stories.

Velocity reduction is not necessarily a problem.

6. Scenario 2: Velocity Increased But Customers Are Unhappy

Situation:

Velocity:

50 → 70 points

Looks good.

But:

Customer complaints increased.

Why?

Check:

Escaped Defects

Increased:

5 → 30

Problem.

Customer Satisfaction

Decreased.

Interpretation:

The team optimized output, not value.

They delivered more but poorer-quality features.

7. Scenario 3: Burndown Chart Is Flat

Observation:

Remaining Work

50

50

50

48

48

45

Looks bad.

Now check CFD.

CFD shows:

Testing column growing.

Meaning:

Development

████

Testing

██████████████████

Problem:

Testing bottleneck.

Solution:

- Add QA support.

- Improve automation.

- Reduce batch size.

8. Scenario 4: Throughput Decreased

Previous:

10 items/Sprint

Current:

5 items/Sprint

Is this bad?

Check:

Story Size

Maybe stories became larger.

Cycle Time

Reduced:

10 days → 5 days

Meaning:

Stories are completed faster.

Interpretation:

Throughput dropped because the team changed work sizing.

Not necessarily a problem.

9. Scenario 5: High WIP Problem

Metrics:

CFD

Development band increasing.

↓

Cycle Time

Increasing.

↓

Lead Time

Increasing.

↓

Throughput

Decreasing.

Complete story:

The team is starting too much work.

Solution:

Reduce WIP.

Focus on finishing.

10. Product Manager Perspective

A Product Manager asks different questions.

Not:

"Did developers complete enough points?"

Instead:

"Are we delivering customer value?"

They look at:

Delivery Metrics

- Velocity

- Throughput

- Cycle Time

Product Metrics

- User adoption

- Conversion

- Retention

- Customer satisfaction

Business Metrics

- Revenue

- Cost reduction

- Market growth

11. Healthcare Product Example

Product

AI Pharmacovigilance Platform

Metrics:

Velocity

45 → 35

Looks negative.

But:

Escaped Defects:

15 → 3

↓

Compliance Issues:

8 → 1

↓

Regulatory Approval Time:

Reduced.

Interpretation:

The team slowed down intentionally to improve safety.

In healthcare, quality is more important than speed alone.

12. AI Product Example

Product

Medical AI Assistant

Metrics:

Throughput increased

10 models tested/month

↓

20 models tested/month

Looks good.

But:

AI Accuracy

92% → 85%

Problem.

More output, lower quality.

Need balance.

13. Agile Health Dashboard Example

A mature Agile dashboard might contain:

Delivery

| Metric | Purpose |
| --- | --- |
| Velocity | Sprint capacity |
| Throughput | Delivery rate |
| Cycle Time | Speed |
| Lead Time | Customer waiting time |

Flow

| Metric | Purpose |
| --- | --- |
| WIP | Work overload |
| CFD | Bottlenecks |
| Flow Efficiency | Waste |

Quality

| Metric | Purpose |
| --- | --- |
| Escaped Defects | Production quality |
| Test Coverage | Engineering quality |

Product

| Metric | Purpose |
| --- | --- |
| Adoption | Usage |
| Retention | Customer value |
| Satisfaction | Experience |

14. Common Metric Traps

Trap 1

"More Velocity = Better Team"

Wrong.

Velocity is only capacity.

Trap 2

"More Features = More Value"

Wrong.

Users may not need those features.

Trap 3

"100% Resource Utilization"

Wrong.

Fully occupied teams create bottlenecks.

Trap 4

"Compare Teams Using Velocity"

Wrong.

Velocity is team-specific.

15. Interview Questions

Q1. Why should Agile teams avoid using one metric alone?

Answer:

Because individual metrics provide incomplete information. Multiple metrics together provide a more accurate view of delivery, quality, and business value.

Q2. Velocity decreased. How would you analyze this?

Answer:

I would check:

- Story size changes.

- Quality metrics.

- Defects.

- Cycle time.

- Throughput.

- Team capacity.

I would avoid immediately concluding performance problems.

Q3. What metrics would you show to executives?

Answer:

Executives usually need:

- Delivery predictability.

- Business value delivered.

- Release progress.

- Quality trends.

- Customer outcomes.

Not only Story Points.

Q4. How do you identify bottlenecks?

Answer:

I analyze:

- CFD.

- WIP.

- Cycle Time.

- Lead Time.

- Throughput trends.

16. Mini Quiz

Q1.

Velocity decreases but defects also decrease significantly. Is this automatically bad?

A. Yes

B. No

Q2.

A growing Testing column in CFD indicates:

A. Testing bottleneck

B. Faster development

C. More customers

Q3.

Which metric measures customer waiting time?

A. Lead Time

B. Velocity

C. Story Points

Q4.

True or False:

A good Agile leader uses metrics to improve systems, not punish people.

17. Practical Assignment

Analyze this AI Pharmacovigilance project:

| Metric | Previous | Current |
| --- | --- | --- |
| Velocity | 50 | 40 |
| Throughput | 8 items | 7 items |
| Cycle Time | 10 days | 6 days |
| Defects | 20 | 5 |
| Customer Satisfaction | 80% | 92% |

Answer:

- Is the team improving or declining?

- Which metrics are most important here?

- How would you explain this to management?

18. Summary

Today we learned:

- Metrics must be interpreted together.

- No single Agile metric tells the complete story.

- Delivery speed, quality, flow, and business value must be balanced.

- Senior Agile professionals look for patterns, not individual numbers.

Key Takeaways

- Metrics are signals, not judgments.

- Velocity alone does not measure success.

- Combine flow, quality, and value metrics.

- Use metrics to improve the system.

- Great Agile leaders ask "Why?" behind every number.